## 1. Title Page
| TG Events LTD | [12 empty] | TITLE PAGE
Epicycle - Hull 2017 | [5 empty] | Is this a MODEL [GENERIC] Risk Assessment ? | [5 empty] | NO
[6 empty] | DATE OF ASSESSMENT |  |  |  | DATE OF EVENT
[6 empty] | 2017-07-08 |  |  |  | 12&13th august 2017
ADDRESS
| 10 Meetinghouse Lane, Bolster Moor HD7 4NR | [7 empty] | tim@tgevents.co.uk
| EVENT LOCATION |  |  |  |  | RISK ASSESSED BY:
| West Park, Hull |  |  |  |  | Tim Garbutt
GROUPS PRESENT AT SITE
| performers |  | YES |  | Volunteers |  |  | YES
| crew |  | YES |  | security |  |  | YES
| technicians |  | YES |  | public |  |  | YES
| stewards |  | YES
| INDIVIDUAL HAZARDS PRESENT AT SITE | [11 empty] | Try to list the tasks in chronological order or as groups
| 1 | Transport to and from site |  |  |  |  | 9 | Football match on adjacent site
| 2 | Install barriers |  |  |  |  | 10
| 3 | Install power and generators |  |  |  |  | 11
| 4 | Install Lighting |  |  |  |  | 12
| 5 | Crowd Management |  |  |  |  | 13
| 6 | access and egress of vehicles |  |  |  |  | 14
| 7 | use of plant inc telehandler and crane |  |  |  |  | 15
| 8 | fire |  |  |  |  | 16
When certain hazards are present there are particular H&S Regulations and ACOP's which include specific risk assessment requirements or recommendations. Where a (specific) risk assessment has been carried out it is not necessary to repeat that assessment as part of this Activity Risk Assessment. However it is important to note the reference number of the associated risk assessment in this document.
ASSOCIATED SITE RISK ASSESSMENTS
| TYPE OF RISK ASSESSMENT |  |  | ASSESSMENT REF NO |  |  | TYPE OF RISK ASSESSMENT |  |  |  | ASSESSMENT REF NO
CIRK VOST risk ass
power supplier risk ass
Sound company risk ass
TDS company risk ass

## 2. Pre-assessment Info
| TG Events LTD | [6 empty] | 2. PRE-ASSESSMENT INFORMATION
| LOCATION |  |  |  | PROJECT DATE
West Park, Hull |  |  |  |  | 12&13th august 2017
[5 empty] | ASSESSMENT DATE | ASSESSORS
[5 empty] | 2017-07-08 | TimGarbutt
| DESCRIPTION OF THE SITE | AND EVENT |  |  |  |  | Give a brief description of the site being assessed
 Epicycle is a large scale touring outdoor circus show by CirkVOST, a collective of 13 people founded in 2007 by experienced circus artists (most of them coming from the famous company “les arts sauts”). The show is inspired by comic books and performed on a bespoke circus rig - a 13.5 m double circle rising from the ground. Within this 'wheel' eight acrobats and a live musician perform. The show has been touring since 2010 playing in indoor venues, outdoor locations or within a circus tent. Epicycle played in the UK as part of Piccadilly Circus Circus on 2 September 2012  The show is driven by the live music, performed by a musician housed within a sphere alongside the structure, while the rest of the cast perform on the rig using a range of aerial techniques. In Hull the show will be presented outdoors in West Park on Saturday 12th of August and Sunday 13th of August at 9:30pm. The show is suitable for all ages. 500 people can be accommodated in deckchair seating either side of the structure with a standing audience behind. The ideal maximum for the standing audience is 4,500 although the company is confident that a larger number can be accommodated with only minimal impact on the audience experience through reduced sightlines.
| SAFETY INFORMATION & GUIDANCE |  | Enter details of any instruction manuals, HSE guidance, industry standards etc. which were referred to when carrying out this assessment.
| TITLE |  |  | PUBLISHER |  | REFERENCE NUMBER
| Health and safety at work act 1974 |  |  | HSE
| Management of Health and Safety at work Regulations 1999 |  |  | HSE
| The Event Safety Guide |  |  | HSE |  | HSG 195
| Safety guidance for street arts, Carnival processions and large scale performances |  |  | ISAN
LOLER 1998
PUWER 1992
Use of portable appliances | [5 empty] | HSG 107
| Electricity at work regulations 1989 |  |  |  |  | HSR25
| Code of practice for temp dis systems for AC supplies for Entertainment etc |  |  |  |  | BS7909
| Construction, Plant competence scheme |  |  | CPCS
Regulatory Reform (Fire Safety) Order 2005
Note on B4: TGE:

## 3. Task Assessments
TG Events LTD
Location assessments first then activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 15
THE LOCATION/ACTIVITY | PREVENTION OF CRIME AND DISORDER | ENSURING THE SAFETY OF THE PUBLIC | PREVENTION OF PUBLIC NUISANCE | PROTECTION OF CHILDREN FROM HARM | AUDIENCE VIEWING AREAS | INSTALLATION OF LIGHT | PUBLIC ACCESS TO SITE | ELECTRICAL INSTALLATION | VEHICLES/PLANT ON SITE | DE HYDRATION/SUN STROKE | CROWD MANAGEMENT | TERRORIST ATTACK | FIRE RISK
HAZARDOUS EVENT activity that could lead to injury or illness | CRIME AND DISORDER ON SITE | PUBLIC SUBJECTED TO HARM OR ILLNESS | NOISE NUISANCE TO NEIGHBOURS | CHILDREN BEING HURT ON SITE | AUDIENCE ENTERING WIDER SITE | WORKING AT HEIGHT | PUBLIC ENTERING WORKING AREA DURING BUILD | CREW INSTALLING CABLES | DELIVERY TRUCKS ON SITE | CREW AND STAFF BEING DE HYDRATED | OVERCROWDING | TERROR ATTACK | USE OF GENERATORS
|  | PUBLIC ACCESSING SITE THROUGH STREET WORKS | LARGE VOLUMES OF TRAFFIC | CHILDREN BEING SEPERATED FROM GUARDIANS | AUDIENCE ENTERING MORE CONFINED SPACES WITHIN THE SITE | LIFTING EQUIPMENT |  | CREW PLUGGING IN EQUIPMENT | CONTRACTORS DROPPING OFF ON SITE | CREW AND STAFF SUFFERING SUN STROKE/BURN | CROWD DISTURBANCE |  | USE OF ELECTRICAL ITEMS
|  | PUBLIC ACCESSING SITE | LITTER | CHILDREN BEING ABDUCTED | CRUSHING/OVERCROWDING | USING ACCESS EQUIPMENT |  | PUBLIC MOVING AROUND SITE DURING INSTALLATION | PUBLIC PARKING |  | CROWD FLOW |  | USE OF VEHICLES
|  | FOOTBALL CROWD ACCESSING STADIUM |  | CHILDREN BEING HARMED | STRUCTURAL COLLAPSE |  |  | PUBLIC MOVING AROUND SITE AFTER EVENT IS OPEN | VEHICLES REVERSING |  | EMERGENCY EGRESS
[8 empty] | GENERATORS RUNNING | USE OF PLANT/TELEHANDLER/CRANE
PUBLIC ENTERING FENCED OFF AREA DURING BUILD
CONTRIBUTORY FACTORS Particular circumstances which could make it more likely that a HAZARDOUS EVENT will occur | CITY PARK LOCATION CLOSE TO NIGHT TIME ECONOMY | WORKING ON A SITE USED BY PUBLIC | PROXIMITY OF SPEAKERS TO NEIGHBOURS | THE EVENT IS IN A LARGE PARK | SEPARATE VIEWING AREAS. DECK CHAIRS AND STANDING | WORKING ON SITES WITH PUBLIC PRESENT | FENCES NOT BEING SECURE | PUBLIC SPACE BEING ALTERED FOR EVENT (AWARENESS) | LIVE HIGHWAYS | HOT WEATHER | ATTRACTIVE SHOW WHICH IS FREE | SITE IS IN AN OPEN PARK WITHOUT FENCING | SPILLAGE OF FUEL
|  | LARGE NUMBERS EXPECTED |  |  | TRIPPING OVER UN EVEN FLOOR SURFACE | POOR WEATHER | MALICIOUS DAMAGE | MALICIOUS DAMAGE OR MOVING SAFETY GUARDES/FENCES | THE SITE IS SHARED WITH THE PUBLIC | LONG DURATION OF WORK | CROWDS DRINKING ALCOHOL BEFORE ENTRY |  | WEAR AND TEAR ON CABLES
[5 empty] | SLIPPING ON WET SURFACES |  | PLANT MOVEMENT | GENERATORS CAUSING BURNS, ELECTRICUTION |  | SUNNY DAY | FOOTBALL CROWD ON SAT 12TH |  | SITE POORLY GUARDED
[5 empty] | EQUIPMENT FAILURE |  | FOOTBALL CROWD ON SAT 12TH |  |  | LACK OF WATER |  |  | ACCUMULATION OF LITTER
OVERCROWDING
TRAFFIC
TRIP OVER UNGUARDED CABLES
HAZARDS Refer to the HAZARD LIST for details of common HAZARDS | OUTBREAK OF CRIME AND DIS ORDER | PUBLIC BEING HARMED BY CONTRACTORS, FIRE, ILL HEALTH | CAUSE NOISE NUISANCE TO NEIGHBOURS | CHILDREN BEING HARMED | UNEVEN FLOOR SURFACES | LIFTING EQUIPMENT | VEHICLE MOVEMENT | BURN ON HOT ENGINE OF GENERATOR | COLLISION WITH VEHICLE AND PEDESTRIAN | STAFF BEING ILL WITH DE HYDRATION | CRUSHING | TERROR ATTACK WITH WEAPONS | Fire
|  | TRIPPING OVER STREET WORKS | LITTER CAUSED BY EVENT |  | TRIP HAZARDS | ELECTROCUTION | CABLES UN GUARDED DURING BUILD | ELECTRICUTION | PLANT LIFTING LOADS | STAFF SUFFERING FROM SUN STROKE | STAMPEDING | ATTACK USING VEHICLE AS WEAPON | Explosion
[5 empty] | POTENTIAL SLIPPERY FLOOR SURFACE | FALL FROM ACCESS EQUIPMENT |  | FIRE | CRANE LIFTING STRUCTURES | STAFF BEING SUN BURNED | FIGHTING | IED/RCIED
[5 empty] | FIRE | WORKING WITH PLANT | UNTIDY BUILD SITE |  |  |  | UNABLE TO EGRESS
[6 empty] | HIT BY FALLING EQUIPMENT | NO | NO | NO
Is a COSHH ASSESSMENT required ? |  |  |  |  | NO | NO |  | POWER SUPPLIER RISK ASS, TGE |  |  |  |  | NO
List any other SPECIFIC RISK ASSESSMENTS | [6 empty] | FENCE OFF BUILD OR RESTRICTED AREAS | FENCE OFF WORKING AREAS DURING BUILD | FENCE OFF BUILD AREAS |  |  |  | Power supplier risk ass. Lighting hire PAT certs, CONTRACTORS
CONTROL MEASURES The existing precautionary measures which are taken to control the HAZARDS ? | INFORM POLICE OF THE EVENT AND TAKE THEIR ADVICE | LIAISE WITH FIRE SERVICE | INFORM NEIGHBOURS OF THE PLANS THROUGH MEDIA | ENSURE THE EMP HAS A ROBUST LOST CHILDREN PROCEDURE | ENSURE STRUCTURES ARE BUILT BY COMPETENT CONTRACTOR | USE CREW WHO ARE TRAINED AND EXPERIENCED | ENSURE CREW AND CONTRACTORS WEAR APPROPRIATE PPE | COVER ALL CABLES IN PUBLIC AREAS WITH CABLE RAMP OR RUBBER MATTING TO PREVENT TRIPS OR WEAR AND TEAR | USE REVERSING ASSISTANT FOR REVERSING VEHICLES | ENSURE MAINS DRINKING WATER IS AVAILABLE OR BOTTLES | EVALUATE OCCUPANCY AND MONITOR CROWD BUILD UP | TAKE POLICE ADVICE ON INTELLIGENCE | ENSURE ONLY DIESEL FUEL USED IN DOUBLE BUNDED TANKS
| LIAISE WITH POLICE THROUGH THE ESAG GROUP | CO-OPERATE WITH LOCAL AUTHORITY THROUGH ESAG | POSITION SOUND AWAY FROM LOCAL RESIDENTS | REMIND GUARDIANS OF THEIR RESPONSIBILITIES | USE FENCES TO SEGREGATE AUDIENCE FROM WORK AREAS | BRIEF STAFF DAILY ON WORK METHODS | ENSURE ADEQUATE LIGHTING | USE COMPETENT ELECTRICAL CONTRACTOR | CURFEW FOR DELIVERIES AND WORKING | BRIEF STAFF ON DRINKING WATER POINT | USE STEWARDS TO CORDON AREAS IF NECESSARY | USE TRAINED STEWARDS | CHECK CONTRACTORS METHODS
| USE SIA STAFF WHERE THERE MAY BE CONFLICT | CORDON AREAS TO BE RIGGED DURING BUILD | GIVE NUMBER TO CALL IF THERE ARE COMPLAINTS | BRIEF STEWARDS ON THE PROCEDURES | COVER CABLES WITH CABLE RAMP | USE CORRECT PPE, WATERPROOFS ETC | GUARD AREA DURING BREAKS | LOCK GERNERATOR DOORS TO PREVENT UNAUTHORISED ACCESS | MAINTAIN AND CHECK FENCES | IDENTIFY SHADED AREAS | USE STEWARDS TO RE DIRECT PEOPLE IF NECESSARY | REMAIN VIGILANT | VISUAL CHECK BEFORE SHOW
| HAVE SUFFICIENT STEWARDING AND SECURITY | APPOINT AN EVENT SAFETY OFFICER | ORGANISE EFFECTIVE LITTER COLLECTION | DO NOT ALLOW UNACOMPANIED CHILDREN UNDER 14 | BARRIER OFF HAZARDOUS AREAS FROM AUDIENCES | USE CORRECT LIFTING TECHNIQUE | SAFETY OFFICER TO CHECK SITE BEFORE OPENING TO PUBLIC | MAKE REGULAR CHECKS ON SITE AND ELECTRIC INSTALL | ENSURE ONLY QUALIFIED STAFF USE PLANT | IDENTIFY SHOPS SELLING SUN SCREEN LOCALLY | USE SIA STAFF TO DEAL WITH INTOXICATED PEOPLE | GOOD HOUSEKEEPING ON SITE | ADEQUATE FIRE FIGHTING DEVICES AND TRAINED OPERATIVES
|  | USE COMPETENT AND TRAINED STEWARDS AND SECURITY | USE A COMPETENT SOUND CONTRACTOR | TRAIN STAFF IN SAFEGUARDING | ENSURE PATHS ARE MOSS FREE | USE ELECTRICIAN COMPETENT IN BS7909 2011 | ENSURE ADEQUATE FIRST AID | USE RCD AT 30MA | USE CRANE ON CONTRACT LIFT BASIS |  | ENSURE ADEQUATE FIRE EXITS FROM SITE |  | LOCKABLE SKIPS
|  |  |  | HAVE DEDICATED TRAINED AND CHECKED STAFF TO LOOK | ENSURE THERE IS ADEQUATE LIGHT INC BORROWED LIGHTING | DAILY BRIEFINGS AND TOOL BOX TALKS - COMMUNICATE | MAKE REGULAR CHECKS ON SITE | INSTALL USING BS7909 2011 |  |  | IDENTIFY BLUE/RED ROUTES |  | ADEQUATE FIRE BREAKS IN SITE DESIGN
|  | BARRIER OFF SITE DURING FOOTBALL MATCH |  | AFTER LOST CHILDREN | ENSURE ADEQUATE STEWARDING | NO LONE WORKING | ENSURE WORK AREA IS SEGREGATED FROM PUBLIC | SAFETY OFFICER TO CHECK SITE BEFORE OPENING TO PUBLIC |  |  | HAVE CONTROL OF SOUND SYSTEM FOR ANNOUNCEMENTS |  | SIGN OFF ELECTRICS TO BS7909 2011
[5 empty] | NO VEHICLE MOVEMENTS DURING EVENT |  | SLIPS, TRIPS, SKELETAL DAMAGE, MUSCULAR DAMAGE | ELECTROCUTION, SLIPS, TRIPS, SKELETAL INJURY, MUSCULAR INJURY | DEATH, MUSCULAR SKELETAL INJURY |  | INC BACK UP GENERATOR
[5 empty] | STEWARDS TO MONITOR CROWD DENSITY |  | 2 | 4 | 4 |  | HAVE A ROBUST EVENT MANAGEMENT PLAN
INJURIES, ILL HEALTH and SEVERITY The HARM which could be caused and its SEVERITY | MUSCULAR SKELETAL DAMAGE | ILLNESS, DEATH |  |  | LOW MUSCLE DAMAGE, SEVERE BURNS, CRUSH INJURIES | SEVERE MUSCULAR SKELETAL INJURIES, ELECTROCUTION | 2 | 2 | 2 | DEHYDRATION, SUN STROKE | MUSCULAR SKELETAL INJURY, CUTS, BRUISES | DEATH | Burns, death
SEVERITY of HARM from an uncontrolled HAZARD | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 8 | 8 | 3 | 4 | 4 | 4
LIKELIHOOD of HARM from a controlled HAZARD | 2 | 2 | 2 | 2 | 2 | 2 | more than 10 | more than 50 | more than 50 | 2 | 2 | 2 | 2
RISK RATING = SEVERITY x LIKELIHOOD | 8 | 8 | 4 | 8 | 8 | 8 | CREW, CONTRACTORS | TECHNICIANS, CREW, PERFORMERS, AUDIENCE, STEWARDS | TECHNICIANS, CREW, PERFORMERS, AUDIENCE, STEWARDS | 6 | 8 | 8 | 8
Nos OF PERSONS at RISK from a single incident | more than 50 | more than 50 | more than 50 | more than 50 | more than 50 | 1-10 | Often | Often | Often | more than 50 | more than 50 | more than 50 | more than 50
GROUPS AT RISK | PUBLIC, STAFF, CONTRACTORS | PUBLIC, STAFF, CONTRACTORS | PUBLIC, STAFF, CONTRACTORS | CHILDREN | TECHNICIANS, CREW, , AUDIENCE | TECHNICIANS | More than 2 hours | More than 2 hours | More than 2 hours | CREW, CONTRACTORS, OTHER STAFF | AUDIENCE, CREW, STAFF, STEWARDS |  | Audience, crew, artistes
FREQUENCY - how often the LOCATION used | Often | Often | Often | Often | Often | Often | MEDIUM | MEDIUM | MEDIUM | Often | Often | Often | Often
DURATION - the average DURATION of the TASK | More than 2 hours | More than 2 hours | More than 2 hours | More than 2 hours | Up to 2 hours | Up to 2 hours |  |  | SITE MANAGER TO MONITOR DELIVERIES | More than 2 hours | More than 2 hours | More than 2 hours | More than 2 hours
EXTENT OF RISK - estimate the level of RISK | MEDIUM | MEDIUM | LOW | LOW | MEDIUM | LOW | SAFETY OFFICER TO MONITOR WORK CARRIED OUT | SAFETY OFFICER TO MONITOR WORK CARRIED OUT |  | MEDIUM | MEDIUM | MEDIUM | LOW
ADDITIONAL CONTROLS or ACTIONS List any that can be adopted in order to further reduce the RISKS |  |  |  |  | ESTABLISH OCCUPANCY OF SITE AND EGRESS POINTS |  |  | ENSURE BREAKS ARE TAKEN TO REDUCE FATIGUE
[5 empty] | SEE EVENT MANAGEMENT PLAN FOR CALCULATIONS |  |  | ALLOW TIME CONTINGENCY TO REDUCE WORK PRESSURE
[5 empty] | STEWARDS/VOLUNTEERS TO GUIDE AUDIENCE |  |  | ADEQUATE STEWARDING AND FIRST AID
MONITOR AUDIENCE NUMBERS, MAKE ANNOUNCEMENTS

## 3a. Supplementary Assessments
TG Events LTD |  |  | 3a. SUPPLEMENTARY ASSESSMENTS
ACTIVITY | PROJECT DATE
Epicycle - Hull 2017 | 12&13th august 2017
| ASSESSMENT DATE | ASSESSORS
| 2017-07-08 | Tim Garbutt
Use this FORM to record the assessment of tasks which require more detail than can be included in TASK ASSESSMENTS SECTION
TASK
CONTEXT
HAZARDS AND RISKS
CONTROLS

## 4. Risk Groups
| TG Events LTD | [7 empty] | 4. SPECIAL RISK GROUPS
| ACTIVITY |  |  |  | PROJECT DATE
| Epicycle - Hull 2017 |  |  |  | 12&13th august 2017
[5 empty] | ASSESSMENT DATE |  | ASSESSORS
[5 empty] | 2017-07-08 |  | Tim Garbutt
GROUPS OF PERSONS WHO COULD BE AFFECTED BY, OR BE AT ADDITIONAL RISK FROM THE LOCATION
CONTROLS:
| PERSONS IN THE SAME WORKING AREA | YES
Warning signs and fences
| PERSONS ENTERING THE AREA DURING WORK BREAKS | YES
Security guards present during breaks and overnight
| INEXPERIENCED WORKERS | YES | Briefing to be given
| LONE WORKERS | NO
| VISITORS | YES | Press and Co workers workers
| PUBLIC | YES | During performance
THE FOLLOWING SECTION CONSIDERS PERSONS WHO BELONG TO PARTICULARLY VULNERABLE GROUPS.
IF THE ANSWER TO ANY OF THE QUESTIONS IS YES THEN PERSONS BELONGING TO THESE GROUPS MUST NOT UNDERTAKE THE ACTIVITY UNTIL A SUITABLE ADDITIONAL RISK ASSESSMENT HAS BEEN CARRIED OUT.
Use the SPECIAL RISK GROUP ASSESSMENT FORMS (Section 4a) as required.
COULD PERSONS WITH ANY OF THE FOLLOWING MEDICAL CONDITIONS BE AT SUBSTANTIAL ADDITIONAL RISK, COMPARED TO NORMAL WORK ACTIVITIES, IF THEY WERE TO UNDETAKE THIS ACTIVITY ?
| ASTHMA OR RESPIRATORY PROBLEMS |  |  | NO |  | SEVERE DEAFNESS |  | NO
| RESPERTORY SENSITISATION |  |  | NO |  | SEVERE VISUAL IMPAIRMENT |  | NO
| ALLERGIES |  |  | NO |  | SEVERE VISUAL IMPAIRMENT |  | NO
| MOBILITY DIFFICULTIES |  |  | NO |  | VERTIGO |  | NO
| SERIOUS MUSCULO-SKELETAL INJURY |  |  | NO
| HEART CONDITION |  |  | NO
ARE PERSONS FROM ANY OF THE FOLLOWING GROUPS REQUIRED TO BE PRESENT ON SITE ?
| CHILDREN (below the minimum school leaving age) |  |  | NO |  | YOUNG PEOPLE (under the age of 18 years) |  | NO
[6 empty] | EXPECTANT AND NEW MOTHERS |  | NO
| WOULD ANY OF THE HAZARDS ASSOCIATED WITH THE ACTIVITY POSE SIGNIFICANT ADDITIONAL RISKS TO A PREGNANT WOMAN, OR HER UNBORN CHILD, DURING THE FIRST 12 WEEKS OF THE PREGNANCY ? | [6 empty] | NO

## 4a. Risk Group Assessments
URBAN STRAWBERRY LUNCH | TG Events LTD |  |  |  | 4a. SPECIAL RISK GROUP ASSESSMENTS
| ACTIVITY |  | PROJECT DATE
| Epicycle - Hull 2017 |  | 12&13th august 2017
|  |  | ASSESSMENT DATE | ASSESSORS
|  |  | 2017-07-08 | Tim Garbutt
| GROUP or MEDICAL CONDITION | ITEM or TASK
| LONE WORKERS | All tasks
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION
| GROUP or MEDICAL CONDITION | ITEM or TASK
INEXPERIENCED WORKERS (if unsupervised)
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION
| GROUP or MEDICAL CONDITION | ITEM or TASK
PERSONS WITH CERTAIN MEDICAL CONDITIONS
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION
| GROUP or MEDICAL CONDITION | ITEM or TASK
DISABLED PERSONS
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION
| GROUP or MEDICAL CONDITION | ITEM or TASK
A NEW MOTHER OR HER CHILD
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION
| GROUP or MEDICAL CONDITION | ITEM or TASK
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION
| GROUP or MEDICAL CONDITION | ITEM or TASK
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION
| GROUP or MEDICAL CONDITION | ITEM or TASK
| ADDITIONAL RISKS | CONTROL MEASURE or ACTION

## End Page
FINEST HOUR | TG Events LTD | [11 empty] | END PAGE
| ACTIVITY |  |  |  |  | PROJECT DATE
| Epicycle - Hull 2017 |  |  |  |  | 12&13th august 2017
[6 empty] | ASSESSMENT DATE |  |  | ASSESSORS
[6 empty] | 2017-07-08 |  |  | Tim Garbutt
WILL THE SITE PRODUCE WASTE PRODUCTS
| DOES THE ACTIVITY PRODUCE SIGNIFICANT AMOUNTS OF WASTE ? |  |  |  |  | NO |  |  |  |  | IS THE WASTE HARMFUL? | NO
HOW IS THE WASTE HARMFUL ?
| HOW IS THE WASTE DISPOSED OF ? |  |  |  | Council cleansing
| COMMENTS on the completed assessment | [10 empty] | Insert any general comments on the assessment or the assessment process here
If the comments and actions within this risk asessment are implemented the risks will be reduced greatly to a reasonably practicable level
| ACTION LIST |  |  | See the relevant sections for more detail of individual action points
| SECTION | REF | ITEM |  |  |  |  | DATE COMPLETED |  | SIGNED OFF BY
One of the assessors and the appropriate line manager should sign the document as an acknowledgement that the assessment is complete and that it represents a suitable and sufficient assessment of the risks posed by the activity.
Assessors Signature | [6 empty] | Date
Managers Signature | [6 empty] | Date
Tim Garbutt
08/07/2017
Tim Garbutt
08/07/2017