## Sheet1
Royal Ballet: Opening the New
All Site Schedule as of 12/09/17
SITE |  | New Theatre |  |  |  |  | Queens Gardens | Trinity Square
In time | Out time | Activity | music | LX | VT | Dancers / Notes
WEDNESDAY 13/09/2017
9:00 | 13:00 | Prerig LX & Flown Masking
13:00 | 14:00 | Lunch
14:00 | 18:00 | Continue Prerig LX & Flown Masking / Rig Projector / Pianos Get in
14:14 |  | Andy Collett & Les Bone Train Arrival in Hull
18:18 |  | Technical Crew Train Arrival in Hull
THURSDAY 14/09/2017
9:00 | 13:00 | Start of day briefing
9:00 | 13:00 | Get in LX / Sprung Floor / Flown/ Wigs
13:00 | 14:00 | Lunch
14:00 | 18:00 | Lay Lino/ Production desks set-up / Prepare to focus
16:15 |  | Janie Valentine & Ross MacGibbon Train Arrival in Hull
18:00 | 19:00 | Supper
18:00 | 19:00 | Piano Tune
19:00 | 23:00 | LX Focus
FRIDAY 15/09/2017
8:00 | 16:00 | Camera set-up | [5 empty] | Ramp & Stage Build commences / 2 x SIA Security on site
9:00 | 13:00 | Lighting Plotting/ Sound design levels
10:01 |  | Kevin O'Hare Train Arrival in Hull
12:14 |  | Dancers/Musicians & Broadcast Team Train Arrival in Hull |  |  |  | COMPANY TRAIN PHOTO OP |  | L&P Team Train Arrival in Hull & Check-in to Holiday Inn
13:00 | 14:00 | Lunch
13:00 | 14:00 | Pigeon rehearsal on stage
14:00 | 18:00 | Lighting Plotting
14:00 | 18:15 | Pigeon rehersal in Dock
16:00 | [7 empty] | Dance schools arrive & into costume
16:15 | 18:30 | [6 empty] | Bevvy of Swans vols called
16:30 | 18:30 | [6 empty] | Full Take Flight Dress Rehearsal until 18:30
16:30 | 17:00 | Set stage/ Barrers and Rehersal Piano
16:30 | 17:00 | Stage available for dancers
17:00 | 18:00 | Crew Supper
1700 | 18:15 | Class on Stage | [5 empty] | B32:I36I25D34:I36A32:I36
18:15 | 18:30 | Set for Rehearsals
18:18 |  | Rachel Vickers / Stage Management & Wardrobe Train Arrival
18:30 | 18:50 | [6 empty] | Dance Schools depart for New Theatre Dress Rehearsal
19:00 | 22:30 | Technical Rehearsal 1 (final curtain call, stgae + piano, Violin, CD1, with costumes wig hair and makeup | Stage + Piano/Violin/CD1 |  |  | With audience, press, media. In performance order.
20:00 | 0:00 | [6 empty] | 2 x SIA Overnight Security on site
SATURDAY 16/09/2017
0:00 | 8:00 | [6 empty] | 2 x SIA Overnight Security on site
8:00 | 17:00 | [6 empty] | 6 x SIA Security on site
9:00 | 13:00 | Technical work / Set Barrers and Rehearsal Piano
9:45 | 11:45 | [6 empty] | Bevvy of swans vols called
10:00 | 17:00 | [6 empty] | 3 x Traffic Management Crew On site
10:00 | 11:45 | [6 empty] | Final Take Flight Rehearsal including mass warm up on site
12:00 | 13:00 | Rehersal time for NAPA and Skelton Hooper
12:14 |  | Alex Beard Train Arrival in Hull
13:00 | 14:15 | Class on stage
13:00 | 14:00 | Crew Lunch Break
14:00 | 18:00 | [6 empty] | 2 x additional SIA Security + 2 Medics on site
14:15 |  | Set for Technical Rehearsal set (strike piano and Barres)
14:30 | [7 empty] | ALL Performer Call (Dance Schools & Vols) - meet back in holding spaces
14:30 | 17:30 | Technical Rehearsal 2 | Musicians in position, Stage + Piano/Violin/CD2 |  |  | Stage + Piano / No Costume + Wigs
15:00 | 15:30 | [6 empty] | Dancer Warm-up
15:30 | [7 empty] | Set for performance One
15:36 | [7 empty] | Prelude begins
15:45 | 16:00 | [6 empty] | Take Flight Performance One
16:00 | 16:30 | [6 empty] | Break
16:36 | [7 empty] | Prelude begins
16:45 | 17:00 | [6 empty] | Take Flight Performance Two
17:00 | [7 empty] | Performance ends
17:30 | [7 empty] | All dancers off site
17:30 | 20:30 | [6 empty] | Site Breakdown
17:30 |  | Reset for performance |  |  |  | No wigs Hair/ Costumes as required. + make up in performance order.
17:30 | 18:30 | Supper
18:00 |  | Doors FOH set
18:00 |  | Piano Tune
!8:30 |  | Doors open
18:55 |  | Half Hour Call
19:00 |  | Standby Theatre doors open
19:26 | 19:29 | [5 empty] | GARDENS: GARY AVIS & KOFI INTRO: PROGRAMME FIRST HALF
19:29 | 19:30 | [5 empty] | HOLDING SLIDE
19:15 | 19:20 | Stand By call
19:30 | 19:32 | Kevin on stage to welcome |  |  |  |  | Programme 1 running sim.
19:32 | 19:43 | The Vertiginous Thrill Of Exactitude | Recorded Music: Franz Schubert |  |  | Choreography: William Forsythe. Dancer: Marianela Nuñez, Beatriz Stix-Brunell, Akane, Takada, James Hay, Valentino Zucchetti
19:43 | 19:46 | Film Montage of dancers |  |  | Film
19:46 | 19:51 | Ballet 101 | Recorded music |  |  | Dancer: Xander Parish
19:51 | 19:57 | Heart’s Furies | Music: Leoš Janáček Kate Shipway (piano) |  |  | Choreography: Andrew McNicol Dancers: Demelza Parish, Lukas Bjørneboe Brændsrød, Calvin Richardson
Introduction to Piece and dancer..(TBC)
19:57 | 20:05 | The Shakespeare Suite (allowance of 8 mins) | Music: Duke Ellington, Billy Strayhorn |  |  | Choreography: David Bintley, Joseph Caley
20:05 | 20:10 | Méditation from Thaïs | Music: Jules Massenet, live |  |  | Choreography: Frederick Ashton: Dancers : Yuhui Choe, Ryoichi Hirano
20:10 | 20:18 | Tarantella
20:18 | 20:27 | A Dancer’s Story
20:27 | 20:33 | The Two Pigeons
20:35 |  | INTERVAL (in Gardens) |  |  |  |  | INTERVAL (in Gardens)
20:35 | 20:45 | Kofi and Gary Avis in the gardens talking about what its like to be a dancer, the Royal ballet and the programme |  |  |  |  | Kofi and Gary Avis in the gardens talking about what its like to be a dancer, the Royal ballet and the programme
20:45 | 21:00 | Film loop starting with HC&L adds and making off finishing with 8 months VT from Hull 2017. |  |  |  |  | Film loop starting with HC&L adds and making off finishing with 8 months VT from Hull 2017.
|  | INTERVAL Finishes in Gardens finishes at 21:15 |  |  |  |  | INTERVAL Finishes in Gardens finishes at 21:15
21:00 | 21:08 | Swan Lake
21:08 | 21:13 | Death of the spoken Word
21:13 | 21:19 | Qualia
21:15
21:19 | 21:22 | The Dying Swan |  |  |  |  | Programme part 2 running
21:22 | 21:31 | Romeo and Juliet
21:31 | 21:39 | After the Rain
21:39 | 21:48 | Sylvia
21:48 | 21:53 | Czárdás Tap Dance
21:53 | 22:01 | Le Corsaire
22:01 | 22:10 | Finale and bows/ Kevin on stage again.
22.1 | 22:20 | ON THE BUS TO THE GARDENS,
22.2 | 22.3 | [5 empty] | Intro:Gary Avis & Kofi: Bow in Queens Gardens
22.3 | 22.35 | [5 empty] | Dancers back to NT.

## Sheet2
Start at QG | 19:26 | 19:29 | Part one: 2.5 mins.
| 19:29 | 19:30 | Holding screem
Start Interval | 20:25 | 20:35 | Kofi and Gary
| 20:35 |  | Film loop ads
Hull Film : dance
8 months