## Guidance
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure to deliver the project on time/gain access to the location | Reputation at risk - including artist, partners, funders and City of Culture. | Annabel | 1 | 5 | 5 | Cross-referencing timeline. Annabel has dedicated the year to the project and has put other commissions on the backburner to ensure success. | 2 | 3 | 6 | Open
2 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | Annabel/Jane | 2 | 5 | 10 | Additional Insurance has been sort and taken out by both Cut Ltd. and Annabel McCourt. This will be cross-referenced with Holy Trinity's policy. Electrical items will be PAT Tested on site and a guarantee of manufacture will be sort from Pearlgreen Engineering. | 0 | 5 | 0 | Open
3 | Location changes mind on religious grounds | The Diocese could, in theory, pull the plug on the project |  | 2 | 5 | 10 | Ensure clear and open communication with the decision-makers via Jane Owen - Events Programmer | 1 | 4 | 4 | Open
4 | Location building works | Date for works and scope/impact not yet identified | Jane - Holy Trinity | 4 | 5 | 20 | Constant monitoring of situation - designing and building the fence so that it is portable and can be relocated around the building, in order to avoid building work if, when and where it might occur. | 2 | 5 | 10
5 | Design & manufacture of the fence - unknown quantity | Exact installation position within the location (still not determined due to building works) will impact on the overall design. The stability of the structure will have to be tested. Bolting to the ground in a Grade 1 listed structure is not a possibility. The uneven medieval flooring also presents a challenge. | Annabel/Strata | 3 | 5 | 15 | Professional engineers Pearlgreen Engineering - part of the Strata group, have been commissioned to design and manufacture the Fence structure. They are aware of the challenges and are going to manufacture a prototype to test for rigidity/stability, as well as adhering to the tech & aesthetic requirements of the artist and her team. | 1 | 5 | 5
6 | Tech team don't deliver sound design solution | Reputation at risk - including artist, partners, funders and City of Culture. Limited interactivity. | Annabel/Tech Team | 1 | 5 | 5 | The very best possible team has been employed to ensure the project delivers user interactivity. The additional ACE funding has enabled this to become a reality. | 1 | 5 | 5 | Open
7 | Conflict of design aesthetics vs acoustics | The compromise of one element over another - thus not achieving the best possible outcome/balance | Annabel | 2 | 4 | 8 | Prototypes and testing ahead of schedule, regular dialogue and meetings between partners | 1 | 4 | 4 | Open
8 | Project Invigilation - increase in tech could potentially increase maintenance requirements | Risk identified due to the fact that this is not a gallery/museum setting with a dedicated tech team present. The technology is new and has an element of unpredictability. Could impact on budget if volunteers are not available/capable | Annabel/Tech Team | 3 | 5 | 15 | Tech dev is underway very early to test capabilities and reliability. As soon as the final version is identified, a simplified 'start up' and 'shut down' procedure will be devised, aiming to limit these to minimal steps. An operational & maintenance manual will then be created and that it is hoped that some volunteers/invigilators and church staff can be identified and trained to follow this. The artist will also be on standby to jump into this role. | 1 | 5 | 5 | Open
9 | Installation 'interupts' regular church services and activities | It could annoy regular churchgoers as well as staff. | Annabel/Jane | 3 | 4 | 12 | Test audio levels, increase random nature of sound. Simplify 'start up' and 'shut down' procedures so that it can be easily turned off and on if required i.e. for a wedding - but this must be agreed with the artist in advance! | 2 | 4 | 8 | Open
10 | Vandalism or over-enthusiastic interaction | Potential for the installation to be vandalised due or damaged - inoperable and potential for injury. | Annabel/Jane | 2 | 5 | 10 | Insured, volunteer invigilators, church staff will monitor - (potential for web cam monitoring). Solid construction, all electronics locked and enclosed within the structure (including specially designed cabinet housing and racking). | 1 | 5 | 5 | Open
11 | Failure to attract audience | Failure to achieve objectives | Annabel | 2 | 4 | 8 | Full and approved MarComms plan | 1 | 4 | 4 | Open
12 | [5 empty] | 0 |  |  |  | 0
13 | [5 empty] | 0 |  |  |  | 0
14 | [5 empty] | 0 |  |  |  | 0
15 | [5 empty] | 0 |  |  |  | 0
16 | [5 empty] | 0 |  |  |  | 0
17 | [5 empty] | 0 |  |  |  | 0
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...