Saturday 8th August 2017

2pm to 8pm

- Priory Primary School, Hull

- Completed by Julia Mitchell, Kath Roe and Louisa Waldron

- Deputy Head Teacher, Priory Primary School

- Head teacher Priory Primary School

- Class Teacher, Priory Primary School

- Version 1

- To ESAG on ??????

Distribution List

| ESAG (E) HCC Arts and Events Manager – Paul Holloway paul.holloway@hullcc.gov.uk HCC Health & Safety – Amanda Gill (E) Amanda.gill@hullcc.gov.uk HCC Highways –Graham Lownsborough (E) Graham.lownsborough@hullcc.gov.uk HCC Public protection- Mark Willoughby (E) & Gill Smith (E) Mark.willoughby@hullcc.gov.uk Gill.smith@hullcc.gov.uk HCC Licensing – Keith Fenner (E) Keith.fenner@hullcc.gov.uk HCC Legal – Stephen Turner (E) Stephen.turner@hullcc.gov.uk YAS – Sinead Howell, David Howell (E) Sinead.howell@yas.nhs.uk David.howell@yas.nhs.uk HCC Bridges M & E Engineer Pete Curry (E) Peter.curry@hullcc.gov.uk Humberside Fire Brigade – John Broadley (E) jbroadley@humbersidefire.gov.uk Humberside Police Karl.corcoran@humberside.pnn.police.uk Darren.wildbore@humberside.pnn.police.uk Ian.goode@humberside.pnn.police.uk Ian.schramm@humberside.pnn.police.uk Alexander.weeks@humberside.pnn.police.uk operationsplanning@humberside.pnn.police.uk | HCC Parks and Gardens– Andrew Wilson and Simon Race Andrew.wilson@hullcc.gov.uk Simon.race@hullcc.gov.uk HCC Civic One/ CCTV -Martin Walker Martin.walker@hullcc.gov.uk HCC Passenger transport – Kerry Ryan Kerry.ryan@hullcc.gov.uk HCC Environmental Health Michael Fish - Food Safety michael.fish@hullcc.gov.uk jenny.best@hullcc.gov.uk HCC Trading Standards – John Sandford John.sandford@hullcc.gov.uk HCC Press Office – Jenny Langrick jenny.langrick@hullcc.gov.uk HCC Tourist Information – Shaun Marshall Shaun.marshall@hullcc.gov.uk HCC Parking – Andy Umpleby, Bernard Wareham Andy.umpleby@hullcc.gov.co.uk Bernard.wareham@hullcc.gov.uk HCC Civic Office – karen.park@hullcc.gov.uk Security and Car Parking - Prestige Support Ltd justine@prestigesupport.co.uk Infrastructure - All Occasions - Mike Harrison sales@marquees4alloccasions.co.uk KWL – Carl Lewis carl.lewis@kingstownworks.co.uk |
| --- | --- |

Contents

- Event Background

- Catering

- Consultation

- Emergency Services

- Equipment Services

5.1 Internal Providers

5.2 External Providers

- Health and Safety

- Licensing

- Staffing

- Event Guides

- Programme

- Publicity and Marketing

- Venue Site and Design

- Useful Contacts

1.	Event Background

‘The People of Priory Festival’ is a Hull City of Culture Creative Communities Project.  This is its first year!  The event is funded by Hull City of Culture and Priory Primary school . The event is a free ticketed event.

All community partners are invited to the event and in the run up to the day various projects have been undertaken with local artists, community members and the children from Priory Primary School.

Priory Primary School are coordinating the event working with Hull City of Culture and in close consultation with Hull City Council Events team.

There will be a range of activities at the event some paid and some free.

The event itself takes place at Priory Primary School on Saturday 8th July from 2pm to 8pm.

2. 	Catering

- The public catering for this event is being supplied by the following.

| Contact Name | Local Authority | Concession |
| --- | --- | --- |
| Steph Braysmith | Hull | Hull Pie |
| Dennis Harrison | Hull | Ice Cream |
| Julian Hackford | ERYC | I love Hog Roast |
| TBC | TBC | TBC |
| Steph Benn | TBC | Candy Floss Cart |

All of the caterers are registered with their local authority environmental health teams and have adequate levels of insurance, public liability and risk assessments. Copies of which are available in the event file upon request.

All of the units have their own power supply and they are responsible for the removal and safe disposal of all their own waste. No units will be allowed to dispose of any rubbish at the venue and any waste spillages will be cleaned up immediately.

- Consultation

Event Safety Advisory Group – Initial information on the event was reported on at the ESAG meeting on ??? 2017 and the Event Manual and Risk Assessment have been emailed to all members on ???? 2017.

Discussions have taken place in the lead up to the event with all partners involved in the planning of the event which has included Hull City Council Events team and Hull 2017.  The programme on the day is inclusive for age groups and abilities. There are a number of organisations represented at the event.

- Emergency Services

All of the emergency providers have been consulted in respect to this event via the ESAG group. Other than medical cover there are no specific requirements for any of the blue light services at the event.

First Aid will be provided by North East Medical and this consist of 4 First Aid staff, 1 Event Medical Technician and 1 Paramedic and this will all be positioned on the school field.

Lost Children will be provided by Priory Primary School this provision will be within a gazebo on the school field.  There will be clear lines of communication when a child is found with the lost child station and we will make this clear on the day.

Protection of children from harm at this event is a multi agency approach with all   of your activity supplier’s child related and they all have a good understanding of the issues that arise from activities of this type and all will be briefed to be constantly vigilant.  All Priory Primary School staff are trained to at least Level 1 safeguarding.  Children will be parent supervised, and will remain the responsibility of parents / carers on the day when accessing all activities.

Stewards – Prestige Support will be providing 8 staff –2 x SIA to cover bar area

2x SIA to cover the front stage area, 2 x SIA plus 2 x Stewards to cover the two entrée gates assisting the staff from the school and City of Culture Volunteers

Event Control – This will be located in a gazebo next to Lost children. Julia Mitchell, Kath Roe and Louisa Waldron will be available on mobile telephones and radios on the day and a member of school staff will be in the Event Control gazebo.

- Equipment

Most of the providers at the event will be totally self sufficient and will bring all of their own equipment to the event and will be responsible for the safe use / risk assessment and security of this equipment. Priory Primary School will not accept any responsibility for the loss or damage of any equipment at the event.

5.1 Internal providers: - The Events Team will be providing support for the event as listed in the staffing section of this document. In addition Julia Mitchell will be the designated events officer for the entire event, any issues should be directed to her so that she has an overall view of the event at all times. In the event of Julia  not being available Kath Roe or Louisa Waldron will be in the Event Control and have full knowledge of the event.  All three members of the team will have radios and mobile phones making them contactable during the event.

Priory Primary School will be supplying 24 bins for the event which will be located around the school field.  Rubbish will be emptied throughout the day and placed into the school skip which will be emptied in advance of the day.

Priory Primary School will be providing all the gazebos on site and will be erecting and dismantling them for the event.

Fire Extinguishers – 1 x powder and 1 x water will be provided by Priory Primary School and will be positioned in the Event control gazebo (next to Lost Children)

5.2External Providing:-

All Occasions will be providing chairs and tables for use outside the bar area and food vendors

Addplant will be supplying 8 Unisex and 2 Disabled toilet units to the event these will be positioned outside the FS building near the entrance to the event.  Except for one unit which will be positioned for the vendors to use.

Participants in the event will also be providing their own equipment as part of their sites and are responsible for the safety of their area.

- Health and safety

Insurances and Risk Assessments – Each participant has supplied copies of Public Liability Insurance and a Risk Assessment for their attraction.  Priory Primary School also holds public liability insurance for the public attending the event and an overall Risk Assessment – currently checking this with insurers

Wet Weather - There is no wet weather plan for this event.  If the weather is inclement certain activities may be cancelled where the safety of the visitors is considered at risk. In extreme weather the event may finish early or have to be cancelled completely at the discretion of and in consultation with the lead contact from Priory Primary School (Julia Mitchell).

- For full event risk assessment please see appendix 1- to be done

Evacuation This event is made up of family groups that could become separated in the case of an evacuation the stewards will be briefed on managing the evacuation and to try and keep family members together.

The evacuation from site will be via both sets of front gates. There is also sufficient space on the school site to move participants at the event safe evacuation areas depending on the nature and risk of the danger presented. (See event map)

Traffic Management Plan

Access and egress for vehicles will be via the gate at the side of the school playground off the main drive.

Event set up will commence at 8:30am and traffic will be managed by school staff when traffic is entering and moving around the site.

There will be no traffic movement on site after 1:30 pm and before 8:30 pm

The exception to this will be the South Cave Falconry company who will be guided on and off the site by staff from Priory Primary School

- Parking for exhibitors, performers and staff :-

- All exhibitors will be able to use the school car park on the day and will be provided with parking passes prior to the event

7. 	Licensing

Alcohol- TENS licence has been obtained for the event

Live Music – TENS licence has been obtained for the event

Noise  – Local residents have been informed of the event through a leaflet drop and telephone number for contact on the day has been provided.  Prestige security will be supervising the stage area on the day and will direct guests away from the speakers if necessary

Odours – Odours will be minimal from the food vendors who are all located together on the site

Litter – The event creates a small amount of litter throughout the day this will be monitored by the staff on site and the rubbish bins will be emptied at regular intervals.

Obstruction - the event set up is as such that people will be allowed to flow freely around the field to allow for access to all of the attractions.

8. 	Staffing

- Staffing for the event is made up of school staff and a number of other agencies as 	detailed below

| Organisation | Name | Area of work |
| --- | --- | --- |
| Priory Primary School |  | Parking |
|  |  | Gates (Entrance and Exit) |
|  |  | Litter |
|  |  | Lost children |
|  |  | Bar staffing |
|  |  | Finance |
|  |  | Face Painting/ tattoos/ glitter |
|  |  | Sweet stall |
|  |  | Event management |
|  |  | Stage Management |
| Hull CoC Volunteers |  | Information gathering for evaluation |
|  |  | Stage Management runner |
|  |  | Support at entrance and exit points |
|  |  | Support throughout the day by being around the site, sign-posting people and providing help as needed. |
| Prestige Security | Justine | Security |
| North East Medical | Chris Bilton | First Aid |
| Hull Pie | Steph Braysmith | Catering |
| Love Hog Roast | Julian Hackford | Catering |
| Lowes | Steve Lowe | Fair ground rides |
| Judy’s Attic | Pru ???? | Craft Tent |
| South Cave Falconry | Peter and Ann | Birds of Prey |

9. Event Guides

- Maps of the event with programming will be provided on the day.  City of Culture volunteers will be available to direct the public around the event.

10. Programme

The event opens to the public at 2pm and the programme of activity is continuous until 8pm. All of the activities mentioned below will be set up and ready to operate by 2pm.

Events Programme

| Organisation | Activity | When | Contact person |
| --- | --- | --- | --- |
| Judy’s Attic | Craft Tent | Throughout event |  |
| South Cave Falconry |  |  |  |
| Football (Mally)? |  |  |  |
| Sportsability? |  |  |  |
| Hull Pie |  |  |  |
| Ice Cream |  |  |  |
| I love Hog Roast |  |  |  |
| TBC |  |  |  |
| Candy Floss Cart |  |  |  |
| Bar |  |  |  |
| Fairground rides |  |  |  |
| Stage |  |  |  |

Stage Programme

| Performer | Time | Contact person |
| --- | --- | --- |
| TBC | 2:00- 2:20 |  |
| Water Wars | 2:20 – 2:40 |  |
| Fates | 2:50 – 3:15 |  |
| Stevie Mould | 3:25 – 3:50 |  |
| Cowboy DC | 4:00 – 4:25 |  |
| Sweet Street Band | 4:35 – 5:00 |  |
| Quick Silver Kings | 5:20 - 6:10 |  |
| DJ Red Eye Phoenix | 6:20 – 6:50 |  |
| Bud Sugar | 7:00 – 8:00 |  |

11. Publicity and Marketing

The event has been advertised in a number of formats as listed below; in addition the organiser will try and attract media and press to the event.

Twitter @priory_primary

Facebook The People of Priory Festival Page

Local Primary Schools – Appleton, Bricknell, Wold, Ainthorpe

YHCLT Partner Schools – St George’s Pirmary

Hull 2017 – Programme Freedom Season, CCP Brochure

Hull Box Office Website

BBC Radio Humberside

12. Venue site and design

GRID REFERENCE FOR SITE PLAN

| Site Number | Activity provider/ name of Organisation | Activity | Space required | Marquee Required | Tables, chairs, barriers |
| --- | --- | --- | --- | --- | --- |

13. Useful Contacts

| Julia Mitchell | Priory Primary School Event Management | 07733320660 |
| --- | --- | --- |
| Kath Roe | Priory Primary School Event Management | 07818063356 |
| Louisa Waldron | Priory Primary School Event Management | 07791014403 |
| Phil Naulls | Priory Primary School Site Manager | 07837566525 |
| Julie Swallow | Priory Primary School Business Manager | 07791678573 |
| Justine Peacock | Prestige Support | 07886838597 |
| Chris Bilton | North East Medical | 07872058590 |
| Steph Braysmith | Hull Pie | 07964539064 |
| Julian Hackford | I Love Hog Roast |  |
| Steph Benn | Candy Floss |  |
| Mike Beadle | Bar Manager | 07580042859 |
| Denis Harrison | Ice Cream vendor |  |
| Food Vendor | TBC |  |
| Birds of Prey |  |  |
| Steve Lowe | Fair Ground Rides |  |
| Adele (PCSO) | Police |  |
|  | Fire Service |  |
|  | Ambulance Service |  |
|  | Addplant |  |
| James Hoggarth | BBC Radio Humberside |  |
| Bachary Bax | Bud Sugar |  |
| Quicksilver Kings |  |  |
| Selene | Sweet Street Band |  |
| Stevie Mould | Stevie Mould |  |
|  | Cowboy DC |  |