## PID
Project name | Place des Anges
Last updated | 2016-03-16 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience |  | 12000
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | Y
[8 empty] | national |  | N
Dates | [7 empty] | international |  | N
Project start date | 2016-03-07 |  | Project live date |  | 2016-07-02 |  |  | children (<16) |  | Y
End of Live date | 2016-07-02 |  | End of eval. date |  | 2016-07-15 |  |  | young people (16-25) |  | Y
[8 empty] | families |  | Y
Categories | [7 empty] | older people (60+) |  | Y
Type | Hull 2017 Production |  |  | Strand |  | Curtain Raiser 2016 |  | self-identify as disabled |  | Y
Season | n/a |  |  | Digital requirements |  | Medium |  | BME |  | Y
[8 empty] | NEET |  | N
Finance | [6 empty] | # temporary jobs created |  | 2
Total project budget |  | 150000 |  |  |  |  | # freelance contracts created |  | c. 1
Hull 2017 contribution |  | 30000 |  |  |  |  | # participation opportunities |  | 0
Analysis/project code(s) | [6 empty] | of which for school age |  | 0
[7 empty] | # commissions |  | 1
[7 empty] | Objective |  | Met | Notes
Use arts and cultural activity to animate and transform the public realm and to increase the sense of pride people have in their city
People
Project Lead | Katy Fuller |  |  | Volunteering lead |  | Shaun Crummey
Producer | Liam Rich |  |  | Education lead |  | Ian Read | To promote the Yorkshire Festival, the Amy Johnson Festival and Hull2017.
Assistant Producer | Hannah Williams Walton |  |  | Marketing lead |  | Laura Smith
Production Manager | Adam Long (Freelance) |  |  | Community Eng lead |  | James McGuire | To capture data on audiences for the benefit of future marketing campaigns.
|  |  |  | Evaluation lead |  | Elinor Unwin
Forms part of the Now or Never engagement campaign to encourage participation.
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
Yorkshire Festival and Hull 2017 present Place des Anges as the finale of the Yorkshire Festival 2016, in association with the Amy Johnson Festival. Gratte Ciel and Production company contracted directly by Hull 2017. Yorkshire Festival is contributing £75k. No financial contribution from Amy Johnson Festival. | [6 empty] | 2 July 2016 - a large-scale artistic interventions at a key landmark in the city. Advertised to start at 9.45pm at Queens Gardens (centred around the Wilberforce Memorial outside Hull College). Access to the show is ticketed but free. All ages are welcome although the lateness of the show may dissuade parents with younger children.
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
The process of selecting Gratte Ciel is exempt from procurement process because the decision is a curatorial act. Note required here about procurement process regarding TG Events (production co) and companies they work with... | [6 empty] | None planned
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
Data capture
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
Approximately 20 volunteers required as stewards (details to be confirmed in June 2016) including box office type duties. | [6 empty] | As night falls across the city of Hull, a number of angels begin to appear, high up on the rooftops. The angels start to glide down into the audience, releasing white feathers which float across the sky. Once the last angel has taken flight, the crowd will be showered with a spectacular explosive display of feather fireworks. A playful, visual spectacle that will enchant audiences of all ages.
Version control
Date | Changes and/or approvals
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize