SLung Low

Produced by: 	Joanna Resnick

Date:		13th December 2016

Victoria Dock Half Tide Basin Site Tests, 6th January 2017

PROJECT OVERVIEW

Flood by James Phillips, is an epic adventure about the end of our world, set in the future, told in many parts. It is the story of what happens to Hull when the waters come.

Produced by Slung Low and Hull UK City of Culture, Flood uses live performance, special effects, digital manifestations and other platforms to tell a story across an entire year.

Throughout 2017 a series of live performances will take place on floating platforms and boats in the half tide basin at Hull’s Victoria Dock. Audiences will watch from the dry land along the perimeter of the water’s edge, listening in on the action through the company's headphone system which allows the actor's slightest breath to be heard.

The site tests detailed below in the method statement and risk assessment are an essential part of the event safety management planning.

METHOD STATEMENT

Please note – no power is required for our planned activity on site on 6th January. The site tests are solely reliant on the provision of access to the pontoon and water.

Upon arrival on site, the RIB (rigid inflatable boat), boat safety gear and tools will be unloaded onto the pontoon and Slung Low’s transit van will be parked in their allocated parking space. Two members of staff will launch the boat onto the water. A third member of staff will remain on dry land to provide assistance as required and answer any questions from passing public and residents.

The boat crew will measure the depth of the water at regular intervals to produce a detailed underwater survey of the site.

Following the end of activity, the Slung Low team will pack away all materials, ensuring that the site is left in the same condition as it had been found.

RISK ASSESSMENT

MATRIX

| Severity Index |  |  |  | Likelihood Index |  |  |  | Risk Rating Matrix |  |  |  |  |  | Residual rating |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Catastrophic | Serious | Significant | Minor | Insignificant |  |  |
| Catastrophic | Fatality, major injury, fire or loss of property | 5 |  | Certain | Harm is certain or near certain | 5 |  | Certain | 25 | 20 | 15 | 10 | 5 | 6 or less | Risks adequately controlled - no further actions required |
| Serious | Over 3 day injury, long term damage to health, serious property damage | 4 |  | Likely | Harm will occur frequently (3/4 times per year) | 4 |  | Likely | 20 | 16 | 12 | 8 | 4 | 6 - 12 | Major accident possible - further control measures required |
| Significant | Hospital treatment likely, some significant property damage | 3 |  | Possible | Harm may occur (1/2 times per year) | 3 |  | Possible | 15 | 12 | 9 | 6 | 3 | Above12 | Control measures ineffective, possibility of major accident high, immediate further action required, possibly suspend work |
| Minor | Slight injury, minor property damage | 2 |  | Unlikely | Harm will seldom occur (once every 2-3yrs) | 2 |  | Unlikely | 10 | 8 | 6 | 4 | 2 |  |  |
| Insignificant | No injury or damage | 1 |  | Improbable | Harm difficult to foresee (less than once in 3yrs) | 1 |  | Improbable | 5 | 4 | 3 | 2 | 1 |  |  |

RISK ASSESSMENT

general elements

| Activity/Area | Hazards | Persons at risk | Severity | Likelihood | Rating | Precautions | Severity | Likelihood | Rating | Residual rating | Management Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity on site and access to the pontoon | Risk of cuts, strains, sprains from trips/slips on wet surfaces | Staff Public | 3 | 4 | 12 | Activities will take place during daylight hours and there is existing public lighting across Victoria Dock to illuminate any potential ground hazards. Suitable boots with good grips will be worn by staff. Any tools, ropes will be stored neatly and away from public walkways when not in use. The pontoon gate will be locked behind staff using the pontoon and basin. Signage will clearly mark that public access to the pontoon is not permitted. | 3 | 2 | 6 | 6 or Less | Slung Low |
| Movement of Van and Launch of Boat | Risk of collisions with van / trailer resulting in crushing, broken bones | Staff Public | 4 | 3 | 12 | The company’s transit van will be driven onto site, via South Bridge Road, to unload the boat and other tools. Vehicle hazard warning lights will be used when on site and movement will be restricted to 5mph. Members of the public will be guided away from the moving vehicle by staff in high-vis vests. Once unloaded, the van will be parked at the allocated parking space at 84 South Bridge Road. | 4 | 1 | 4 | 6 or less | Slung Low |
| Manual Handling | Risk of back injury due to incorrect lifting techniques Risk of injury if items dropped onto feet | Staff | 3 | 3 | 9 | Staff to be briefed on correct manual handling techniques. No heavy lifts expected. Larger objects to be broken down into their component parts and trolleys to be used where possible. Gloves to be worn as necessary. Steel toe capped boots to be worn if risk of injury to feet. | 3 | 2 | 6 | 6 or less | Slung Low |
| Use of boats (manual and engine-powered) | Risk of injury due to incorrect handling and falling into water | Staff | 4 | 3 | 12 | Staff carrying out the site tests are RYA Powerboat Level 2 and Safety Boat crew. Crew must wear properly fitting buoyancy aids, suitable footwear and outdoor waterproof clothing. Staff are required to work in groups/pairs and to be vigilant of each other. The RIB (rigid inflatable boat) will be powered by an electric Torqueedo outboard so no diesel/petrol will be required. Electric motors do not produce greenhouse gasses or any form of pollutants such as carbon dioxide and nitrogen oxide. The Torqeedo motor program works in the safe low-voltage range up to 42 V. For this reason there is no danger of explosions or electrical shocks. Boat will carry oars for use in the event of engine failure to enable crew to return to the pontoon. One member of staff will remain on dry land at all times in the event of an emergency. Ropes will be stored neatly to prevent trip hazards. Tools will be tethered onto the boat or individuals. | 4 | 1 | 4 | 6 or less | Slung Low |
| Noise | Hearing damage | Staff Public | 3 | 2 | 6 | The Torqueedo electric motors have low noise emission and are significantly quieter than comparable combustion motors. Activity will be carried out between 9am and 7pm to avoid disturbing local residents. | 2 | 1 | 2 | 6 or less | Slung Low |
| Working outdoors | Risk of discomfort due to lack of welfare facilities Risk of fatigue | Staff | 3 | 3 | 9 | Staff will have access to toilet, shower and refreshment facilities a production base which overlooks the basin (84 South Bridge Road). Staff to take regular breaks. Individuals to know their own limitations and not to carry out any activity that they are not comfortable or properly trained to do. The nature of the activity is not strenuous. Appropriate outwear and PPE will be worn by staff. | 3 | 2 | 6 | 6 or less | Slung Low |
| Medical emergency | Injuries and illness | Staff | 4 | 3 | 12 | All Slung Low staff on site are qualified first aiders. A first aid kit will be kept on the pontoon whilst activity is carried out on the water. In the event of serious injury or pre-existing conditions an ambulance will be called. All injuries or accidents on site, however minor, must be recorded in the accident book which will be located in Slung Low’s production base which overlooks the basin (84 South Bridge Road). The Producer will be responsible for reporting directly to the Heath & Safety Executive as necessary under the Reporting of Injuries, Diseases and Dangerous Occurances Regulations (RIDDOR) 2013. | 4 | 1 | 4 | 6 or less | Slung Low |

Ongoing Risk Assessment

We acknowledge that a risk assessment is a live document and that assessing risk is an ongoing process, this table is for including any additional risks identified during the site visit:

| Activity/Area | Hazards | Persons at risk | Severity | Likelihood | Rating | Precautions | Residual rating | Severity | Likelihood | Rating | Management Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Other important risk assessments to consider are:

Documents Prepared by    . . . . . . . . . . . . . . . . . . . . . . . . . . .  	Date . . . . . . . . . . . . . . . . . . . . . . . . . . .