## Sheet1
IN WITH A BANG EVENT LOG
TIME | EVENT | TIME | EVENT CLOSED/RESOLUTION
15.3 | Event Control Operational
15.53 | Road Closure in place on Plimsoll way
15.53 | 2 x people on the roof of Warehouse 13 (unrelated to the event)
16 | MIH First Underpass show commenced
16.1 | Road Closure in place on Kingston Street
16.19 | Police investigating people on rooftop of Warehouse 13
16.23 | Report from CCTV on A63 west to east carriage way - 1 traffic management vehichle East to west no transport management vehicle on site unlikely to close within the next 10 mins - need to man the crossings | 16.26 | MIH control inform CCTV that A63 due to close at 5pm
16.31 | Stewards briefing complete - stewards deployed across the site
16.41 | Query re road closures underneath underpass Disabled access allowed - lot of cars coming through alongside these | 16.44 | Event control check re when all vehicle access stops
16.45 | Informed all roads closed at 4pm - except access for residents ceasing at 5pm | 16.46 | Informed that at 5pm full road closures will be in place - only blue light access All vehicles with access requirements were informed to be in situ by 5pm
16.49 | CCTV informed that all management vehicles in place for road closures on A63
16.57 | Westbound on A63 now closed Eastbound on A63 will be closed in 5 minutes (17.02)
17 | TM asked about blue badge drivers on Westbound A63 - confirmation needed re blue badge access | 17.01 | 20 minute grace period given for blue badge drivers to enter site
17.04 | Vehicles blocking Kingston Street. Gary Beestone confirmed Kingston Street is fully closed
17.06 | Eastbound A63 now closed
17.07 | Two TM vehicles waiting to move into position on A63. TM require confirmation of road closures | 17.07 | Gary Beestone confirmed A63 is now closed off to all vehicles excluding blue badge vehicles, which closes at 17.20
17.11 | No stewards on far side of Spencer field. Require confirmation
17.11 | GB informed stewards letting people in on Railway Street | 17.11 | event contro contact JP to stop access on Railway Street
17.13 | event control communicated to ticket gates operators that gates are not to be opened until 18.00 not before
17.13 | A63 now fully closed both directions
17.14 | TM request for full closure of Humber Street | 17.14 | Event Control confirmed
17.15 | Railway Street barriers being breached | 17.15 | Police investigating this
17.15 | TM vehicles to move into position on A63
17.16 | event control communicated to JP lack of stewards at Spencers Field and breaches on Railway Street | 17.17 | JP confirmed they had passes until 17.00. Event Control confirmed this access should now be stopped
17.18 | The Bridge and The Deep now in show positions and locked down
17.18 | Event control confirmed JP to investigate Spencers Field
17.18 | GB confirmed ZS is doing a sweep of the site prior to event
17.2 | Sound crew with vehicles on A63 requesting access | 17.2 | Event Control confirmed they can only gain access if they are accredited staff. TM confirmed they are staff from HPSS. ZS - confirmed HPSS can access if it's a production critical vehicle. TM confirmed they are road closures vehicles
17.21 | TM confirmed all road closures are now in place
17.23 | ZS no volunteers at ticket gates as of yet
17.24 | Bronze reported people climbing over barriers between Swing Bridge and Dock street | 17.24 | GB checking
17.25 | GB redeployed stewards to Swing Bridge and confirmed there is one steward missing | 17.26 | Event Control to contact security
17.26 | Event control communicated steward redeployment to security
17.27 | TM reported request for resident vehicle access | 17.28 | GB confirmed no resident vehicles are allowed access to site past 17.00
17.29 | GB confirmed stewards are now in place on Swing Bridge
17.3 | Event control communicated volunteer deployment to ticket gates to commence
17.31 | Event Control confirmed Gate volunteers are now on Channel 8
17.31 | All gates are closed to everyone excluding residents
17.31 | MM confirmed no more Blue badge cars expected through the road closure | 17.32 | Event control confirmed 20 minutes grace period allowed further access and is now closed to all
17.32 | GB requested a call to JP security re her expected arrival in event control | 17.32 | Event Control communicated to JP Security
17.34 | MM requested for Pete Curry to investigate vessel in front of Minerva Pier and to advise on exclusion zone about to be in place
17.36 | Event Control requested contact details for Pete Curry | 17.36 | GB to chase up Pete Curry
17.37 | CR confirmed there is nobody stood on the footpaths near the sheds on Wellington Street West
17.39 | JP Security arrived at Event Control
17.4 | Vessel moored up near Minerva pier - FYI | 17.41 | Event control contacting harbour master and will advise once more information has been received
17.43 | Swing bridge being monitored via CCTV no one allowed to cross - confirmed Opposite Holiday Inn
17.48 | Event control called ticket gate staff - any issues ahead of opening ahead of 6pm | 17.48 | Ticket gate 1 - No issues ready to proceed Ticket gate 2 - no issues ready to proceed Ticket gate 3 - no issues ready to proceed Ticket gate 4 - no issues ready to proceed
17.53 | Event control -stand by to tickets gates for opening at 6pm
17.56 | Approx 12 moving Vehicles on Lowgate on to Posterngate then on to Princes Dock Stree attempting to access the A63 | 17.59 | Event control
17.57 | Assistance required a Kingston Street | 17.57 | Event control - confirmed at Ice Arena - should be no road closures in that area
18 | All tickets gate on channel 5 and ready to go all stewards and volunteers in place on ticket gates
18 | GB gave notice to open the tickets gates
18.01 | Event control spoke to traffice management to check on posterngate traffic
18.02 | Event control notified all tickets gates that they are OK to open
18.03 | Event control confirmed to Zoe all gates have been advised to open
18.04 | Posterngate confirmed as all clear
18.04 | Police advised that vehicles blocking both eastbound and westbound ends of A63 are not in place | 18.04 | Event control investigated with ELT ELT to call CCTV
18.08 | Event control confirmed all tickets gates open | 18.08 | All tickets gates confirmed they have opened
18.09 | GB allowing access for residents only on swinge bridge - ticket holders being sent around the long way round
18.1 | Police confirmed only one lorry on west end of the A63 and nothing on the east end | 18.12 | Gary Beestone investgating location of vehicles
18.12 | MIH event control confirmed that Ferens Art Gallery alarm is off
18.13 | Police confirmed lorries on the Garrison road of A63 - two on the flyover | 18.14 | GB confirmed vehicles in wrong position - both vehicles moved into correct position at both ends of the A63
18.16 | Drivers on A63 need to be repositioned | 18.17 | GB confirmed happening
18.25 | Drivers of HPSS do they need to stay with vehicles | 18.25 | GB confirmed HPSS do not need to stay with vehicles - Direct Traffic Management do need to stay with vehicles
18.27 | GB agreed with Bronze - 1 vehicle blocking A63 with no driver - and 1 blocking with driver to allow access for emergency vehicles
18.27 | Tickets gates quiet | 18.27 | DW confirmed a large amount of people in QVS so gates should prep
18.28 | Asked for confirmation West bound carriage way maintained for emergency access and East bound blocked completely - A63 | 18.5 | Confirmation of vehicles in place
18.3 | Event Control requested information on crowds at tickets gates | 18.35 | Tickets gates all clear excluding Gate 4 which is busy, but manageable
18.42 | Security currently clearing people off the sheds by Mr Choo's
18.44 | Ticket gates confirmed no re-entry to site
18.57 | Confirmed both vehicles are now in position on the A63 | 18.57
19.02 | Security spotters reported there is congestion outside Green Bricks | 19.04 | Event Control communicated this to Gate 3 who confirmed the crowd are under control
19.06 | GB requested scan number on his laptop | 19.08 | Event Control confirmed the scanned number was 7511
19.14 | MIH - group of 50/60 people on walkway not moving - check if this is a firework viewing area | 19.15 | GB confirmed that area will be cleared prior to fireworks
19.15 | Toilet block near C4Di - have asked for a response team barrier near toilet | 19.15 | Event control confirmed Prestige response team on way
19.17 | West side HI along water - tower light out - should be on | 19.18 | Confirmed priority to resolve - and more stewards required
19.19 | People on wall on Humber Dock Basin - East Swing and Minverva need to confirm if Heras line been broken - unconfirmed reports of people standing on the wall | 19.2 | Someone sent to investigate
19.24 | Message to TM company - road closure down High Street is too far down need to move to junction of Liberty Lane and High Street | 19.24 | Event control called to advise of the change required
19.24 | Tower light reinstated - corner of Holiday Inn
19.25 | Query from stewards re drones around the event site | 19.26 | DW confirmed drones COC on Pier - steward confirmed this is the area of the drones
19.29 | Security - breaking barrier at C4Di near office - people breaching barrier and getting into event site | 19.29 | GB contacting Justine Peacock at Presige security to attend the scene
19.3 | Request of Stewards and volunteers in front of the Minerva - ask audience to use the swing bridge and not Minerva entrance - bottle neck at bottom of Henry Vernon Court | 19.31 | Event control advised to deal with locally as dealing with multiple barrier breaches
19.33 | Sean - confirmed that the closure on High Street has been moved to Liberty Lane
19.33 | Last projection on Deep completed - ask for confirmation whether Deep area needs to be cleared | 19.35 | Confirmed clearing of Deep area is 19.45
19.37 | Event control relayed instructions that stewards will be clearing the The Deep walkway at 19.40
19.39 | 11600 total scanned into site
19.4 | Lord Mayor requested where his seats are | 19.42 | JP confirmed Lord Mayor is positioned on the pier with steward looking after him
19.44 | Tower light reported to be out near Commerical Road behind the Holiday Inn | 19.46 | GB to check with stewards. GB confirmed tower light is on
19.47 | Barriers reported to broken between Humber Street and Wellington Street | 19.47 | JP to send additional stewards to that area
19.5 | Event Control asking ticket gates whether they have experienced ticket holders wishing to swap zones | 19.51 | Tickets gates confirmed tickets holders must be in the zone as specified on the ticket
19.52 | Event Control confirmed no queues at the ticket gates
19.54 | 15499 total scanned into site
19.55 | Police asked tie wrapped heras fencing at Humber Street to be chained | 19.58 | Stewards confirmed that the area is secure. Event production are happy it's secure
19.58 | Reports of large queue by Ice Arena
19.59 | Swing Bridge near Gate 2 to be opened to relieve congestion | 20 | Bronze are aware and JP to inform stewards
20.03 | Event control suggested that Humber st clear and leave with stewards | 20.04 | Luke confirmed happy area is secure
20.04 | Humber dock street gate 3 - steward assistance requested Non-ticket holders blocking the gates need to clear Large amounts of people at First Aid point West Spencer Land | 20.07 | event control -radio to gate 3 - issue with non ticket holders - have asked security to act
20.05 | GB confirmed that show now live and running
20.08 | Current scanned 16,838
20.11 | Prestige extra stewards sent to Gate 3 to clear the blockage
20.12 | Event controlled confirmed to Gate 3 security en route to gate and asked for Gate 3 to confirm when resolved
20.18 | GB confirmed Swing Bridge needs to be closed for egress | 20.19 | GB and JP discussed and confirmed egress route
20.19 | 3minutes to pyro
20.19 | Gate 3 continued issue with non-ticket holders blocking access | 20.19 | Prestige to respond asap
Stewards have physically escorted ticket holders on to site
20.31 | GB asked for confirmation of Swing bridge closure with security | 20.33 | Closure of swing bridge confirmed
20.33 | 1 minute to the end of pyro - egress expected
20.35 | Security requested minimal gate infrastructure to assist with egress | 20.35 | Event Control confirmed
20.36 | Gate 1 clear
20.36 | Security reported Swing Bridge is closed and security advising public to take a different route | 20.37 | Public sent down Kingston Street next to Warehouse 13 to exit via Commercial Road
20.37 | Public breached Swing Bridge for egress | 20.38 | GB investigating
20.39 | Security reported unable to stop public from breaching swing bridge | 20.43 | Swing Bridge closed
20.39 | Event Control asking whether The Deep projections can recommence at 20.43 | 20.42 | GB gave the go ahead as long as egress is flowing smoothly
20.43 | More stewards are being deployed to the Swing Bridge
20.44 | Security redirecting crowd to exit via Kingston Street
20.44 | GB reopened Swing Bridge
20.45 | Event control confirmed stewards are aware of congestion at Swing Bridge | 20.46 | GB supervising Swing Bridge egress
20.48 | GB confirmed Swing Bridge needed to be opened as it was a safety issue for it to be closed | 20.49 | GB and Bronze happy with the egresss situation on the Swing Bridge
20.49 | Event control requested for stewards to manage vehicle access on High Street and Liberty Lane - no vehicles should be moving until instructed by event control | 20.51 | JP requested more information on High Street road closures
20.51 | Max Power drivers requested ETA for movement of vehicles | 20.52 | Event control suggested approximately 30 minutes
20.52 | Stewards confirmed vehicles exiting only from High Street/Liberty Lane | 20.53 | JP requested more information on where the traffic is coming from
20.53 | Vehicles coming from Blackfriargate | 20.54 | JP requested total number of vehicles
20.54 | HPSS requested information on timings for moving the vehicles blocking A63
JP confirmed there are no vehicles are parked on Blackfriargate so the cars must be coming from a zone. JP suggested they must be blue badge
20.55 | Silver standing down
20.55 | Event control requested go ahead for vehicle deterrence vehicles to be moved from A63
20.56 | Swing Bridge egress is complete, no issues. The decision to open it was made with GB physically being there
20.59 | GB confirmed that he's happy to allow audience to the Deep as long as numbers managable | 21 | Security and stewards briefed
20.59 | Event Control requested the number of people treated by first aid | 21.01 | 4 people seen and 1 person treated
21.03 | Heras has been removed for egress from the Deep viewing passageway
21.05 | Pedestrian flow around H.Samuels is normal
21.1 | GB gave go ahead for removal of vehicle blockades |  | Event control conveyed message to Direct Traffic Management to remove blockades but to not reopen the roads
21.11 | Direct Traffic Management confirmed the vehicle blockades will only move once gritters arrive after 21.30
21.12 | Request for status of A63 |  | Event control confirmed A63 will open after 21.30 once the gritters have arrived
21.12 | Vehicle movement from High Street
21.12 | GB requested JP to redeploy stewards to walk vehicles out | 21.14 | JP to send extra stewards to C4Di car park to ensure cars do not turn onto A63
21.13 | DTM confirmed stewards are allowing traffic outboung from High Street | 21.13 | GB confirmed
21.15 | Stewards on route to C4Di location
21.18 | GB confirmed no crimes reported during the event
21.2 | Request for ETA on stewards for C4Di car park area | 21.21 | JP confirmed 2 stewards at the C4Di car park
21.22 | Site cleared and de-rig commenced
21.22 | Security on site until 21.45
21.24 | Event control confirmed happy to open A63 once gritting complete
21.34 | Large queues at Parliament street and Quay street | 21.35 | FGH looking into it
21.38 | Request on ETA for gritters | 21.38 | Any minute
21.39 | Event control end