## Sheet 1 - Table 1
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Thursday 6th | Ben Arrives |  |  |  | Ground prepared |  |  |  | Ben R
|  | PICK UP TRAILER |  |  | Secure space for Kit + wood |  |  |  | Chris H
|  | START WOOD COLLECTION |  |  | Start wood unload
Secure fire site
Chris H arrives
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Friday 7th | Pete M arrives Lunchtime | [7 empty] | Ben R
| Mandy arrives Evening | WOOD COLLECTION |  |  | WOOD ARRIVAL |  |  |  | Chris H
| Martha arrives Evening | START BUILD/LAYOUT | [6 empty] | Pete M
| Cara Smyth Evening | [7 empty] | Mandy D
| COOK/COUPLE, Anne and Pat | [7 empty] | Martha B
Cara S
Cook/couple
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Saturday 8th | Gavin Arrives Lunch time | [7 empty] | Gavin L
|  | Continue to build | [6 empty] | Ben R
| Jo Galbraith |  | Arrive |  | Bonfire building |  |  |  | Chris H
| Flick Ferdinando | [7 empty] | Mandy D
| Jack Stoddart | [7 empty] | Martha B
| Vic Llewellyn | [7 empty] | Pete M
Vic L
Flick F
Jack S
Jo G
Cook/couple
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Sunday 9th |  | Continue build | Rehearse, practice with Samovar |  | Bonfire building | Any Host volunteers? | Rehearse any tech for Samovar |  | Gavin L
Ben R
Chris H
Mandy D
Martha B
Pete M
Vic L
Flick F
Jack S
Jo G
Cook/couple
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Monday 10th |  | Continue build | Rehearse in morning | Teatime 3-7 Activity | Bonfire Bilding | Any Host volunteers |  |  | Gavin L
Ben R
Chris H
Mandy D
Martha B
Pete M
Vic L
| Cook becomes 1 | [7 empty] | Flick F
Jack S
Jo G
Cook
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Tuesday 11th | No change |  |  |  | Bonfire Building |  |  |  | Gavin L
|  | Continue Build | Rehearse in morning | Teatime 3-7 activity |  | Any Host volunteers? In morning, or early afternoon |  |  | Ben R
Chris H
Mandy D
Martha B
Pete M
Vic L
Flick F
Jack S
Jo G
Cook/couple
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Wednesday 12th | No change | Continue build | rehearse in morning | Teatime 3-7activity | Bonfire Building | dance groups, shoal,rivers morning or early afternoon |  |  | Gavin L
Ben R
Chris H
Mandy D
Martha B
Pete M
Vic L
Flick F
Jack S
Jo G
Cook
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Thursday 13th | Looper/sound person arrives | Finish off build | rehearse | Teatime 3-7 Activity | Start prep for rehearsals next day | Yes times to be TBC |  |  | Gavin L
Ben R
Chris H
Mandy D
Martha B
Pete M
Vic L
Flick F
Jack S
Jo G
Cook
Sound 1
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Friday 14th | Tim Hill band master arrives at lunch time | Complete build rehearse mechanisms, start Pyro Prep | rehearsals on main field |  | Complete build, put in staging, Pa, putlocks etc | Rehearse all community |  |  | Gavin L
| Gavin away for the day | [7 empty] | Ben R
| Jo Galbraith away for the day | [7 empty] | Chris H
Mandy D
Martha B
Pete M
Vic L
Flick F
Jack S
Jo G
Cook
Sound 1
Tim H
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Saturday 15th | Full Crew | Priming and pyro onto structure and site |  |  |  | Yes on and off all day |  |  | Gavin L
Ben R
[5 empty] | Rehearsing |  |  |  | Chris H
[5 empty] | Heras down |  |  |  | Mandy D
[5 empty] | Security for pyro site |  |  |  | Martha B
Pete M
Vic L
[5 empty] | Welfare for community and Brass band | Brass band rehearse from 6 un til show |  |  | Flick F
Jack S
[5 empty] | Parking.... |  |  |  | Jo G
Cook
Sound 1
Tim H
Cara S
DATE | CREW/TEAM | BONFIRE | FIRE-SMITHS | Engagements | MAIN-SITE (Adam) | COMMUNITY REHEARSALS | Tech | Meals | Accom
Sunday 16th
|  | Clear up and leave |  | Fellowship come down and rake through ashes.