|  |  |
| --- | --- |
| **Name of Individual / Organisation** | BAMM North |
| **Name of Project** | Fly to Freedom |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| 30 July 2016 |  | Planning meeting to finalise design |  |  |
| August 2016 | September 2016 | Book/confirm workshops venues and artists |  |  |
| August 2016 | October 2016 | Draw and cut background/supports |  |  |
| August 2016 |  | Finalise exhibition location |  |  |
| October 2016 |  | Planning meeting2 /Start Facebook page to record project progress |  |  |
| October 2016 | July 2017 | BAMM artists make their own mosaic pieces |  |  |
| October 2016 | March 2017 | Obtain materials for workshops |  |  |
| September 2017 | March 2017 | Meet up with Age UK, LGBT, St Vincent church, Beverley Road mosque and other groups/venues to promote project and recruit workshop participants |  |  |
| January 2017 | March 2017 | Design, print and put up posters |  |  |
| April 2017 | June 2017 | Run 5 workshops in Hull to make 50 mosaics |  |  |
| July 2017 |  | Grouting of mosaics made by the pubic |  |  |
| August 2017 |  | Bring all the pieces together and finalise design and artwork |  |  |
| August 2017 |  | Press release |  |  |
| September 2017 |  | Installation |  |  |
| October 2017 | December 2017 | Write evaluation and report |  |  |