## PID
Project name | The Land of Green Ginger
Last updated | 2016-01-18 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience |  | 100000
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | N
[8 empty] | national |  | N
Dates | [7 empty] | international |  | N
Project start date | 2016-02-25 |  | Project live date |  | 2016-07-01 |  |  | children (<16) |  | Y
End of Live date | 2018-02-28 |  | End of eval. date |  | 2018-03-31 |  |  | young people (16-25) |  | Y
[8 empty] | families |  | Y
Categories | [7 empty] | older people (60+) |  | Y
Type | Hull 2017 Production |  |  | Strand |  | Land of Green Ginger |  | self-identify as disabled |  | Y
Season | Thru 2017 |  |  | Digital requirements |  | High |  | BME |  | Y
[8 empty] | NEET |  | N
Finance | [6 empty] | # temporary jobs created |  | 2
Total project budget |  | 1400000 |  |  |  |  | # freelance contracts created |  | c. 10
Hull 2017 contribution |  | 1400000 |  |  |  |  | # participation opportunities |  | TBC
Analysis/project code(s) | [6 empty] | of which for school age |  | TBC
[7 empty] | # commissions |  | 7
[7 empty] | Objective |  | Met | Notes
Use arts and cultural activity to animate and transform the neighbourhoods where people live and to increase the sense of pride people have in their area
People
Project Lead | Katy Fuller |  |  | Volunteering lead |  | Shaun Crummey
Producer | TBC |  |  | Education lead |  | Ian Read | Engage people in inclusive community activity to feel more connected to others
Assistant Producer | TBC |  |  | Marketing lead |  | Laura Smith
Production Manager | Freelance PM |  |  | Community Eng lead |  | James McGuire | Encourage people to travel across the city to see and take part in activity elsewhere
|  |  |  | Evaluation lead |  | Elinor Unwin
Increase people's sense of personal wellbeing through participation
Pilot a new collaborative model for commissioning linked creative activity across a whole city and a period of 18 months
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
This is a Hull 2017 project, conceived, produced and delivered by the team with additional freelance capacity. Artists and the wider creative team will be identified, commissioned and contracted directly by Hull 2017. | [6 empty] | July / August 2016 - 7 x artistic interventions in 7 different neighbourhoods across the city. Throughout 2017, at least 7 further interventions/projects in neighbourhoods and a small number of citywide interventions. 2018 - publication distributed. All sub-projects to be developed as part of the process. Currently the intention is that projects will be free at the point of access.
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
Artists will be identified through their response to a brief. The process is exempt from procurement process because the decision will be a curatorial act. | [6 empty] | The whole project is predicated on creative residencies in the residential neighbourhoods of the city. By taking work directly to people's area, placing it in the public realm or easily accessible spaces and offering a range of opportunities to interact and be part of the process we anticipate building audiences for this project and the wider programme. Across the cohort of artists and range of projects there will be a selection which will work directly with the education programme.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
TBC | [6 empty] | Health and wellbeing outcomes Building new audiences Connecting individuals and communities across the city
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
Modest requirements during July / August 2016 (details to be confirmed in May 2016). Requirements for 2017 interventions will be clarified as the project proposals are developed in Autumn 2016. | [6 empty] | See Project Outline document
Version control
Date | Changes and/or approvals
2016-01-19 | Greenlit at Board
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize