## Sheet1
Crate appearances | Project Live dates |  | WEEK COMMENCING
 | time axis 2017-02-27 to 2018-02-19
| Prologue | Seasons 2&3 brochure | bar: 2017-03-06
| Prologue | Initial newspaper article | bar: 2017-04-03
| Prologue | Institute operational - crate movement | bar: 2017-04-10 to 2017-04-17
Periplum | Heralding | Crate appears | 2017-04-17: 22
Periplum | Engagement | Horses and ash people appearances | bar: 2017-04-24 to 2017-05-01
Periplum | Event | Live | bar: 2017-05-01
| Interlude | Institute commentary | bar: 2017-05-08 to 2017-05-15
Joshua | Heralding | Crates appear and smoke incident | 2017-05-22: 27
Joshua | Engagement | Campaign for the nose return | bar: 2017-05-29 to 2017-06-05
Lone Twin | Heralding | "Margaret" reports her find | bar: 2017-06-05
Joshua | Event | Nobody Nose Live | 2017-06-12: 17
Lone Twin | Engagement | Participant work | bar: 2017-06-12 to 2017-07-03
| Interlude | Institute reveal Voice Cocoon pictures/plans | bar: 2017-06-19
Lone Twin | Event | Performances and end | bar: 2017-07-10 to 2017-07-17
| Interlude | Institute uproar. | bar: 2017-07-24
| Interlude | Plaques found - Preston Road and Longhill | bar: 2017-07-24
Aswarm | Heralding | Crates appear and voices are collected | bar: 2017-08-07 to 2017-08-14
Joshua | Event | Parade and ending | bar: 2017-08-14
| Interlude | Institute discuss meaning of plaques | bar: 2017-08-14
Aswarm | Heralding | Vessels left in neighbourhood / with groups | bar: 2017-08-21 to 2017-09-11
Aswarm | Event | Installation of voice vessels | bar: 2017-09-18 to 2017-09-25
| Interlude | Institute start to draw together parallels | bar: 2017-09-25
McGuires | Heralding | crates, tiny things, banner appear | bar: 2017-09-25 to 2017-10-02
McGuires | Event | Live | bar: 2017-10-09 to 2017-10-16
| interlude | Institute - readying to leave | bar: 2017-10-23
Macnas | Heralding | Giant crate | bar: 2017-10-23
Macnas | Event | Parade | bar: 2017-11-06
| Ending | Institute conclusion | bar: 2017-11-13