## Original Plan
|  | Task | Notes
Week 28 | 22nd August to 28th August
|  | Think Ins structure | the plan for how open/invited thinkins will work
|  | Plan of Attack | the schedule from Henri/how we programme.
|  | Circle of Friends | Preparation for the next meeting
|  | Marketing and Comms | What do we want from Marketing and Coms.
|  | Book in Think ins | Booking public space
|  | Hairdressers | Have a chat with haire dressers on Newland how to gather
Week 27 | 29th August to 4th September
|  | Think in Meeting | Planning and Prep
|  | Marc Comms | Meeting
|  | City Hall Visit | MO to take lots of photos
Week 26 | 5th Sept to 11th September
|  | POW WOW | Meeting with LH, BR, MO CoF and Think ins
|  | Meeting with Barbara | How to documment the process
|  | WOW Core activities | Mentors etc.
|  | Circle of Friends | Tasks and outreach for CoF
Week 25 | 12th Sept to 18th Sept
|  | Think Ins | Dates confirmed and marketing signed off
all venues confirmed.
|  | Programming | Schemes for feedback and promotion
Meeting with Heads up/BFI/ Hull Truck
|  | Bradford | Meeting with Evie Manning
|  | Marketing | Website
Week 24 | 19th Sept to 25th Sept
|  | Education | Campaign and activities for schools
|  | Volunteers | Confirm volunteer support thinkins
|  | Digital Launch | with 2017 launch?
|  | Thinkins | Structure and equipment signed off
Week 23 | 26th Sept to 2nd Oct
|  | Thinkins | First Thinkins and feedback/ data feedback
|  | Headliners | Meeting and Short list of Headliners
|  | Review? | Review points
|  | Programming | Performances/Artists - Rash Dash/Ethel Leginska etc
Week 22 | 3rd Oct to 9th Oct
|  | Circle of Friends | Meeting - Report on First thinkins/Bradford and the rest of the programme
|  | Thinkins | Next Thinkins's and feedback/ data feedback
|  | Programming | Headliners and Performances on going
Schedule programme - Wow core activites
Week 21 | 10th Oct to 16th Oct
|  | Thinkin | Next Thinkins's and feedback/Big Think in Structure
|  | Programming | Draft Programming proposal
Headliners/Performances/
Subjects and Speakers Long list
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
City Hall Dress up Ideas and Planning - Campaign to launch at big thinkin
|  | Marketing | Pushing Big Thinkin
Week 20 | 17th Oct to 23rd Oct
|  | Thinkin | Next Thinkins's and feedback/ data feedback
|  | Programming | Meeting with HD,LH,BP to go over draft programme for WOW Southbank
Subject and Speakers Shortlist
Legacy impact?
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
City Hall Dress up Ideas and Planning - Campaign to launch at big thinkin
|  | Marketing | Pushing Big Think In
Week 19 | 24th Oct to 30th Oct
|  | Programming | WOW Southbank 1st Deadline
|  | Thinkins | Next Thinkins's and feedback/
Compile Data Feedback
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
Week 18 | 31st Oct to 6th Nov
|  | Thinkins | Big Think in
|  | Programming | Headliners update/Performances
|  | Circle of Friends | Meeting and repoting on the draft programme
|  | WOW Bradford | Attend, learn and represent Hull WOW
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
Week 17 | 7th Nov to 13th Nov
|  | Thinkin evalautation | Evaluation and research
Investigation on feedback for Thinkin
Programming
|  | Idea | Crafts Call Out? Community element
Week 16 | 14th Nov to 20th Nov
|  | Programming | Market Place Ideas and List
Workhop and Hull Bites
Headliners/Performances/Speakers/Talks update
Workshops/Hull Bites Provisional Lists
Commissions
Week 15 | 21st Nov to 27th Nov
|  | Programming | Headliners Confirmed
Speakers Confirmed - Marketing Copy
Performances Confirmed - Marketing Copy
Draft Schedule completed.
|  | Marketing | Draft WOW Brochure
Week 14 | 28th Nov to 4th Dec
|  | Programming | Panel speakers confirmed
Hull Bites Scheduled
|  | Circle of Friends | Circle of Friends meetings
|  | Marketing | WOW Brochure
Week 13 | 5th Dec to 11th Dec
|  | Programming | 2nd South Bank Deadline
|  | Marketing | WOW Brochure Signed Off
Week 12 | 12th Dec to 18th Dec
|  | Planning | Event plan the festival
Week 11 | 19th Dec to 25th Dec |  | Christmas Break
Week 10 | 26th Dec to 1st Jan |  | Christmas Break
Week 9 | 2nd Jan to 8th Jan
|  | Event | Commissions
Community Craft making
Production Meeting - requirements
|  | Marketing | Digital Campaign
Distribution
Week 8 | 9th Jan to 15th Jan
|  | Event | Commissions
Community
Production - Staffing
Week 7 | 16th Jan to 22nd Jan
|  | Event | Commissions
Community
Production - Staffing
Week 6 | 23rd Jan to 29th Jan
|  | Event | Commissions
Community
Production - Staffing
Week 5 | 30th Jan to 5th Feb
|  | Event | Commissions
Community
Production - Staffing
Week 4 | 6th Feb to 12th Feb
|  | Event | Commissions
Community
Production - Staffing
Week 3 | 13th Feb to 19th Feb
|  | Event | Commissions
Community
Production - Staffing
Week 2 | 20th Feb to 26th Feb
Week 1 | 27th Feb to 5th March
Production Week
6th March to 12th March
13th March to 19th March
20th March to 26th March

## Adjusted Plan
| Dates | Areas | Actions | Person | Status | Deadline
Week 14 | 28th Nov to 4th Dec
| Deadlines | 1ST PROGRAMME SOUTHBANK
| Programming City Hall | Headliners | Jo Brand approached - waiting to hear back - List of Music Acts to approach | HD | Ongoing
|  | Panels and Chairs | Confirm list of A Lister to approach | MO | Ongoing
|  |  | Confirm list of local people to approach | MO | Ongoing
|  | Installation | Deadline for Revolutionary Makers 4th December | SMH | Ongoing
|  | Market Place | Two lists made up in MO Programming Strands for Information Stalls and National Organisations | SMH | Ongoing
|  | Food Offer | Discussion and outline for food offer through YUM Festival | AL/LH/JH | Ongoing
|  | Additional Events | List added to MO Programming Strands - Dome Space Programme and Pop Up Programme | MO/AL | Ongoing
| Programming Ferens | Live Performance | Final programme to be confirmed and deal memo completed. | MO/HD
|  | Exhibition | Look at exhibition options - Lee Tsang, Jacky Flemming, Art Celebrating Equality
| Programming Other | Princes Quay | Potential programme for Princes Quay drawn up including pop up cinema and exhibit? | MO
|  | Pop Up Cinema | Update from Anna Plant. | AP
| WOW Southbank |  | Programme deadline - discuss the programme and get feedback | MO/LH/HD/SMH
| Learning and Participation |  | Agreed proposals and budget allocated. | IR/HD/MO
| Digital |  | Trailblazers and circle of friends list drawn up, schedule. | MO/EC
| Marketing & Comms |  | Marc Comms plan confirmed/audience for WOW/Burnsy Plan | RC
| Production |  | City Hall chase
| Circle of Friends |  | Agenda drawn up for the Circle of Friends.
| Event Management |  | Time line agreed.
| Box Office |  | Ticket Prices and Free Ticket Allocation
Week 13 | 5th Dec to 11th Dec | Programming |  |  |  |  | Panel speakers confirmed
| Deadlines | [5 empty] | Hull Bites Scheduled
| Programming City Hall | Headliners | Confirm Jo Brand | HD
|  |  | Approach to Skunk Anasie, Corinne Bailey Rae, Beth Ditto | LH
|  | Panels and Chairs | Approach to Alisters
|  | Installation | Interview artists for Revolutionary Makers - who is interviewing the artists? What day? | IR, HD, MO, AL
|  | Market Place | Check the space available. |  |  |  | Circle of Friends meetings
|  | Food Offer | Chase City Hall - food proposal |  |  |  | WOW Brochure
|  | Additional Events | Who can do what where?
| Programming Ferens | Live Performance | Deal memos sent out.
|  | Exhibition | Lee Tsang exhibit find out more
| Programming Other | Princes Quay | Meeting with Alan Raw and Princes Quay - exhibtion, pop up cinema. |  |  |  | 2nd South Bank Deadline
|  | Pop Up Cinema |  |  |  |  | WOW Brochure Signed Off
| WOW Southbank |  | Adjusted programme and
Learning and Participation
Digital
| Marketing & Comms | [5 empty] | Event plan the festival
Production
Circle of Friends
Event Management
| Box Office | [5 empty] | Christmas Break
Week 12 | 12th Dec to 18th Dec
| Deadlines | HEADLINERS
| Programming City Hall | Headliners | Acts confirmed |  |  |  | Christmas Break
|  | Panels and Chairs | Schedule confirmed
|  | Installation | ?
|  | Market Place | Expressions of Interest to market stall holders
Food Offer
|  | Additional Events | Proposal for additional events drawn up.
| Programming Ferens | Live Performance | Times and Demos confirmed
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 11 | 19th Dec to 25th Dec
| Deadlines | 1ST PROGRAMME SOUTHBANK
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 10 | 26th Dec to 1st Jan
| Deadlines | 1ST PROGRAMME SOUTHBANK
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 9 | 2nd Jan to 8th Jan
| Deadlines | 1ST PROGRAMME SOUTHBANK
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 8 | 9th Jan to 15th Jan
Deadlines
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 7 | 16th Jan to 22nd Jan
Deadlines
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 6 | 23rd Jan to 29th Jan
Deadlines
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
| Marketing & Comms |  | FINAL PROGRAMME DEADLINE
Production
Circle of Friends
Event Management
Week 5 | 30th Jan to 5th Feb | Event
| Deadlines | 1ST PROGRAMME SOUTHBANK
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 4 | 6th Feb to 12th Feb | Event
Deadlines
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
| Marketing & Comms |  | PROGRAMME RELEASED
Production
Circle of Friends
Event Management
Week 3 | 13th Feb to 19th Feb | Event
| Deadlines | 1ST PROGRAMME SOUTHBANK
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 2 | 20th Feb to 26th Feb
| Deadlines | 1ST PROGRAMME SOUTHBANK
| Programming City Hall | Headliners
Panels and Chairs
Installation
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 1 | 27th Feb to 5th March | Production Week
Deadlines
| Programming City Hall | Headliners | Green Rooms set up and artist liason
|  | Panels and Chairs | Panel Liason
|  | Installation | INSTALLATION into CITY HALL
Market Place
Food Offer
Additional Events
| Programming Ferens | Live Performance | Get Ins.
Exhibition
| Programming Other | Princes Quay
Pop Up Cinema
WOW Southbank
Learning and Participation
Digital
Marketing & Comms
Production
Circle of Friends
Event Management
Week 0 | 6th March to 12th March

## MO Work to Date and Availabilit
Calendar
MO WORK
| SEPT | Sunday | 4th
|  | Monday | 5th
|  | Tuesday | 6th
|  | Wednesday | 7th
|  | Thursday | 8th
|  | Friday | 9th |  | MO WOW
| 25 | Saturday | 10th
|  | Sunday | 11th
|  | Monday | 12th
|  | Tuesday | 13th
|  | Wednesday | 14th
|  | Thursday | 15th
|  | Friday | 16th
| 24 | Saturday | 17th
|  | Sunday | 18th
|  | Monday | 19th |  | MO WOW
|  | Tuesday | 20th
|  | Wednesday | 21st
|  | Thursday | 22nd
|  | Friday | 23rd |  | MO WOW
| 23 | Saturday | 24th
|  | Sunday | 25th
|  | Monday | 26th
|  | Tuesday | 27th
|  | Wednesday | 28th |  | MO WOW
|  | Thursday | 29th |  | MO WOW
|  | Friday | 30th
| Oct | Saturday | 1st
|  | Sunday | 2nd
|  | Monday | 3rd |  | MO WOW
|  | Tuesday | 4th
|  | Wednesday | 5th
|  | Thursday | 6th
|  | Friday | 7th | CIrcle of Friends | MO WOW
| 21 | Saturday | 8th
|  | Sunday | 9th
|  | Monday | 10th
|  | Tuesday | 11th | Thinkin | MO WOW
|  | Wednesday | 12th | Thinkin | MO WOW
|  | Thursday | 13th |  | MO WOW
|  | Friday | 14th
| 20 | Saturday | 15th
|  | Sunday | 16th
|  | Monday | 17th | Thinkin | MO WOW
|  | Tuesday | 18th
|  | Wednesday | 19th | Thinkin | MO WOW
|  | Thursday | 20th | Thinkin | MO WOW
|  | Friday | 21st
| 19 | Saturday | 22nd
|  | Sunday | 23rd
|  | Monday | 24th |  | MO WOW
|  | Tuesday | 25th
|  | Wednesday | 26th
|  | Thursday | 27th
|  | Friday | 28th |  | MO WOW
| 18 | Saturday | 29th
| November | Sunday | 30th
|  | Monday | 31st |  | MO WOW
|  | Tuesday | 1st
|  | Wednesday | 2nd
|  | Thursday | 3rd
|  | Friday | 4th | Circle of Friends | MO WOW
| 17 | Saturday | 5th |  | MO WOW
|  | Sunday | 6th |  | MO WOW
|  | Monday | 7th
|  | Tuesday | 8th
|  | Wednesday | 9th
|  | Thursday | 10th |  | MO AWAY
|  | Friday | 11th |  | MO AWAY
| 16 | Saturday | 12th |  | MO AWAY
|  | Sunday | 13th |  | MO AWAY
|  | Monday | 14th |  | MO AWAY
|  | Tuesday | 15th
|  | Wednesday | 16th |  | MO WOW
|  | Thursday | 17th
|  | Friday | 18th
| 15 | Saturday | 19th
|  | Sunday | 20th
|  | Monday | 21st |  | MO WOW
|  | Tuesday | 22nd
|  | Wednesday | 23rd
|  | Thursday | 24th
|  | Friday | 25th |  | MO WOW
| 14 | Saturday | 26th
|  | Sunday | 27th
|  | Monday | 28th |  | MO NB
|  | Tuesday | 29th
|  | Wednesday | 30th |  | MO WOW
| December | Thursday | 1st
|  | Friday | 2nd |  | MO WOW
| 13 | Saturday | 3rd
|  | Sunday | 4th
|  | Monday | 5th |  | MO WOW
|  | Tuesday | 6th
|  | Wednesday | 7th
|  | Thursday | 8th
|  | Friday | 9th
| 12 | Saturday | 10th
|  | Sunday | 11th
|  | Monday | 12th |  | MO WOW
|  | Tuesday | 13th
|  | Wednesday | 14th
|  | Thursday | 15th
|  | Friday | 16th
| 11 | Saturday | 17th
|  | Sunday | 18th
|  | Monday | 19th |  | MO WOW
|  | Tuesday | 20th
|  | Wednesday | 21st
|  | Thursday | 22nd
|  | Friday | 23rd |  | MO WOW
| 10 | Saturday | 24th |  | XMAS BREAK
|  | Sunday | 25th
|  | Monday | 26th
|  | Tuesday | 27th
|  | Wednesday | 28th
|  | Thursday | 29th
|  | Friday | 30th
| 9 | Saturday | 31st
| January | Sunday | 1st
|  | Monday | 2nd |  | MO WOW
|  | Tuesday | 3rd |  | MO AF
|  | Wednesday | 4th |  | MO AF
|  | Thursday | 5th |  | MO AF
|  | Friday | 6th |  | MO WOW
| 8 | Saturday | 7th |  | MO AF
|  | Sunday | 8th
|  | Monday | 9th |  | MO WOW
|  | Tuesday | 10th |  | MO AF
|  | Wednesday | 11th |  | MO AF
|  | Thursday | 12th |  | MO AF
|  | Friday | 13th |  | MO WOW
| 7 | Saturday | 14th |  | MO AF
|  | Sunday | 15th
|  | Monday | 16th |  | MO AF
|  | Tuesday | 17th |  | MO AF
|  | Wednesday | 18th |  | MO AF
|  | Thursday | 19th |  | MO WOW
|  | Friday | 20th |  | MO WOW
| 6 | Saturday | 21st
|  | Sunday | 22nd
|  | Monday | 23rd |  | MO WOW
|  | Tuesday | 24th | AF LAUNCH | MO AF
|  | Wednesday | 25th |  | MO WOW
|  | Thursday | 26th |  | MO AF
|  | Friday | 27th |  | MO WOW
| 5 | Saturday | 28th
|  | Sunday | 29th
| February | Monday | 30th |  | MO WOW
|  | Tuesday | 31st |  | MO WOW
|  | Wednesday | 1st |  | MO WOW
|  | Thursday | 2nd |  | MO AF
|  | Friday | 3rd |  | MO WOW
| 4 | Saturday | 4th |  | MO AF
|  | Sunday | 5th
|  | Monday | 6th |  | MO WOW
|  | Tuesday | 7th |  | MO WOW
|  | Wednesday | 8th |  | MO WOW
|  | Thursday | 9th |  | MO AF
|  | Friday | 10th |  | MO WOW
| 3 | Saturday | 11th |  | MO AF
|  | Sunday | 12th
|  | Monday | 13th |  | MO WOW
|  | Tuesday | 14th |  | MO WOW
|  | Wednesday | 15th |  | MO AF
|  | Thursday | 16th |  | MO AF
|  | Friday | 17th |  | MO WOW
| 2 | Saturday | 18th
|  | Sunday | 19th
|  | Monday | 20th |  | MO WOW
|  | Tuesday | 21st |  | MO AF
|  | Wednesday | 22nd |  | MO WOW
|  | Thursday | 23rd |  | MO WOW
|  | Friday | 24th |  | MO WOW
| 1 | Saturday | 25th
|  | Sunday | 26th
|  | Monday | 27th |  | MO WOW
| March | Tuesday | 28th |  | MO WOW
|  | Wednesday | 1st |  | MO WOW
|  | Thursday | 2nd |  | MO WOW
|  | Friday | 3rd |  | MO WOW
| 12 | Saturday | 4th |  | MO WOW
|  | Sunday | 5th |  | MO WOW
|  | Monday | 6th
|  | Tuesday | 7th
|  | Wednesday | 8th |  | MO WOW
|  | Thursday | 9th
|  | Friday | 10th
| 11 | Saturday | 11th
|  | Sunday | 12th
|  | Monday | 13th |  | MO WOW
|  | Tuesday | 14th
47 Days