|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Selina Slater/Hull Music Hub |
| **Name of Project** | Albemarle Saturdays |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETED / ON-TIME / BEHIND |  |
| September 2016 | February 2017 | Booking workshop leaders,musicians. Employ caretaker, create publicity and website. Planning and developing sessions and building a network of music service staff and local musicians and groups.  |  |  |
| 11/03/2017 | 11/03/2017 | Saturday 1 |  |  |
| 8/04/2017 | 8/04/2017 | Saturday 2 |  |  |
| 13/05/2017 | 13/05/2017 | Saturday 3 |  |  |
| 10/06/2012 | 10/06/2012 | Saturday 4 |  |  |
| 8/07/2017 | 8/07/2017 | Saturday 5 |  |  |
| 12/08/2017 | 12/08/2017 | Saturday 6 |  |  |
| 9/09/2017 | 9/09/2017 | Saturday 7 |  |  |
| 14/10/2017 | 14/10/2017 | Saturday 8 |  |  |
| 11/11/2017 | 11/11/2017 | Saturday 9 |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances