## Budget (hidden)
Thursday 7 December
Budget
Venues
Fruit | 800
Hull Minster | 450
Warehouse | 400
Vue |  | in film budget
Content
For Luke
Production
Aidan
Estimate | 10000
Access
BSL | 2000
Marketing
Design flyers for delegates | 500
Capture on the day (Photographer) | 600
Flyer design/print | 350
Intercity advertising (Poster sites) | 1000
EDM (with data from others) | 500
Other | 1500
Catering
Breakfast | 600 | £3 x 200
Lunch | 2000 | £10 x 200
Total | 20700
Total Budget | 35000 | Dependant on what Luke has spent already
Remaining | 14300 | For panels/keynotes/travel/accomm

## Timeline
Timeline
2017-07-24
2017-07-31 | Venues confirmed
2017-08-07 | 1/3 of partners in place/Sessions confirmed.
2017-08-14 | Website complete on Hull2017 site
List of key attendees drawn up
2017-08-21 | Budget complete
2017-08-28
2017-08-30 | Hull 2017 Programme Announcement
At least half of the sessions announced and partners in place
Invites land to key attendees
Tickets on sale
2017-09-04
2017-09-11
2017-09-18
2017-09-25
2017-10-02 | Guardian panel annonced, Boiler Room, Vice announce
2017-10-09
2017-10-16
2017-10-23
2017-10-30 | Full programme for Substance announced. Including weekend.
2017-11-06
2017-11-13
2017-11-20
2017-11-27
2017-12-04
2017-12-11
2017-12-18

## Partners
Organisation/Person | Contacting | Notes | Session Lead
The Guardian | Luke B | Helen Pidd, John Harris
Luke suggesting Anna nmeeting Sam/Martin over Freedom Festival |  | The AND and AND argument
Vice | Luke B | The Northern underground or its Grime up North, the new Grime from the North like Bugzy Malone.
Awaiting update
Noisey | Luke B
Being chased
Huffington Post | Luke B
Being chased
LADbible | Sam
Contacted/getting back to us
Boiler Room | Martin A | Panel with the new electronic underground - Rival Consoles etc
Will talk to them about Future Forum after securing Warp.
BBC3 (Jeremy Evans) | Martin A followed up | Is this the right partner?
Luke waiting for further email from Jeremy. Sam to follow up to Radio 3 head honcho.
The Creative Society (Martin Bright) | Luke B
Awaiting Update
C4DI hosted panel - | Martin/Luke | Will five bars of internet make people less lonely. What is a creative industry?
Martin followed up. Steering groups commenced - working on a question.
The Arts Council – Rebecca Horn. Sir Nicolas Serota will be there on the Tuesday night. | Martin A first contact
Luke in conversation with currently. | Sam in contact with Jessica Farmer/Luke in contact with Rebecca Horn
Designers Republic | Luke B | How do we sell the north?
Update required
The Northern Fiction Alliance / Wrecking Ball Press | Luke B | NFA Luke confirmed and going to speak to Shane
Martin Bedford (Leeds), Sean O'Brien (set in Newcastle and Hull) |  | The role of a northern voice / future northern novellists / how can joined up publishing
Salon North | Luke B | Notions of identity
Wellcome Trust | Martin/Luke | Arts role in public health. Someone from Hull Uni to research? |  | https://www.theguardian.com/culture/2017/jul/19/arts-can-help-recovery-from-illness-and-keep-people-well-report-says?CMP=share_btn_tw
| Not contacted yet | CCG
The Space |  | How does a city or town's cultural product hit a global audience?
CANVAS | Sam H
With Boiler Room / The Space
Frank Cottrell Boyce keynote speech | Luke B | keynote speech on Northern culture, post-Brexit
Why?
Paul Morley: host/chair | Luke B
Confirmed
Humber LEP | Martin A | Ensure that the Humber capitalises on the economic opportunities offered by Hull: UK City of Culture 2017.
Tim Rix |  | Be on a panel addressing this specific issue and how that is happening.
sIEMENS, gREEN pORT |  | Work with Hull: UK City of Culture 2017 to ensure that the ‘place’ context is wider than Hull and encompasses and capitalises on the Humber opportunities. The Investment and Delivery Plan requests LGF funding to support Quality of Place Investment and a Gallery, Conference and Exhibition Centre in Hull. LGF support is also requested in the Investment and Delivery Plan to significantly enhance the economic and social benefits of the Humber Bridge visitor offer.
Miranda Sawyer | Luke B
Almost confirmed
Culture Liverpool / Cities of the North | Martin A | Chris working from Cities of the North has confirmed. ShOuld choose who to get from Culture Liverpool and add to what makes a City of Culture a success?
Council of the North |  | Will the Council of the north succeed where previous inititatives haven't and why?
What we want to build is a representative a body of council leaders, businesses and MPs – alongside trade unions and the community and voluntary sector.
Andy B
University of Hull |  | Logistics?
Hack and Host |  | ‘artists as political activists’ in coversation with Jeremy Deller
Policy North |  | Contact by MA
Andy Burnham? keynote speech | Prescott office to approach
Hull2017 - John Pywell / Martin Green | Martin Atkinson | The next 25 years of Culture in Hull
George Osborne | Martin Green
Confirm other panels and find reason to include.
Wilberforce Society
Blast Theory
Luke
Hold off
Martin/Sam

## Schedules
Thursday 7 December
Main Space Panels/Provocations/Keynotes
Time | Venue | Title of Panel | Speaker / Panelists | Question | Session Lead | Chair | Panelist 1 | Panelist 2 | Panelist 3 | Panelist 4 | Panelist 5
9:00 | Butler Whites/Church | Welcome | Martin Green & younger voice
10:00-10:45 | Hull Minster | Keynote 1 | Culture, creativity and future of the north from young strong northern artist - Lauren Laverne, Kate Tempest, Maxine Peake - similar)
11:00-12:00 | Fruit | Session 1 | Hack and Host: Jeremy Deller | How the creative sector is a vehicle for political, social and economical change?
11:30-12:30 | The Warehouse | Session 2 | C4DI | What is a Creative Industry? Will 5 bars of wifi eradicate loneliness? |  | C4DI
12:30 - 13:30 | Hull Minster | Lunch
14:00 | Fruit | Session 4 | Arts Council | What will the arts council look like in 2097? Discussion on Arts Council research (economic impact of culture on cities like the north). How can the arts council activity coolaborate further with artists and businesses?
15:00 | Fruit | Session 5 | British Council / Cities of Culture / Martin Green / Culture Liverpool | How to make a successful city of culture?
15:00 | C4DI Theatre | Session 6 | NFA / Wreckjing Ball Press / Penguin Random House | Sense of place in writing
15:00 | Warehouse | Session 7 | University of Hull / Wellcome / CCG | Arts and Culture in improving a town/cities/place health
16:00 | The Warehouse | Session 8 | Siemens / Wykeland / KCOM / Sewells / Strata / Assemble / Partnerships | How can arts and culture humanise business and promote business activites? Arts and Business: a working relationship with benefits beyond the obvious.
16:15 | Fruit | Session 9 | The Space/Boiler Room/Canvas | How does a city or town's cultural product hit a global audience, and what benefit does that bring to a place?
17:15 | Break | Hull Minster
18:00 | Summing Up | Hull Minster | The Guardian | Panel of individuals gathered together by the Guardian to sum up and publish an article of the summing up
19:00 | Sessions end
20:00 | Fruit | Performance
15 minutes Provocations with 15 mins Q&A (smaller capacities)
Time | Venue | Title of Session | Speaker | Chair
11:30 | C4DI Theatre
12:30 | C4DI Theatre
13:30 | C4DI Theatre
14:30 | C4DI Theatre
15:30 | C4DI Theatre
16:30 | C4DI Theatre
17:30 | C4DI Theatre
11:00-12:00 | The Warehouse
A session around the impact of site specific or large scale outdoor work and the benefit they bring to place.