|  |  |
| --- | --- |
| **Name of Individual / Organisation** | All Star Entertainment |
| **Name of Project** | M62 Creative Corridor Youth Empowerment Programme (Block Party) |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETED / ON-TIME / BEHIND |  |
| 18/08/16 | 28/10/16 | Research and Development of project. Putting Project plans in place. Speaking with partners. Putting recruitment plans in place. Securing venues and workshop spaces. Recruiting artists/ trainees etc. Putting marketing and communication plans in place. Putting evaluation plans in place |  |  |
| 22/11/16 | 22/11/16 | Press Release out  |  |  |
| 01/12/16 | 01/12/16 | Launch Event |  |  |
| 07/11/16 | 10/12/16 | **BLOCK PARTY! 1** Tasters/workshops and sharing event **Birkenhead/Wallasey** |  |  |
| 16/01/17 | 18/02/17 | **BLOCK PARTY! 2** Tasters/ workshops and sharing event - **Knowsley** |  |  |
| 06/03/17 | 08/04/17 | **BLOCK PARTY! 3** Tasters/ workshops and sharing event - **Warrington** |  |  |
| 24/04/17 | 20/05/17 | **BLOCK PARTY! 4** Tasters/ workshops and sharing event - **Bradford** |  |  |
| 17/06/17 | 17/06/17 | **BLOCK PARTY! 5** Tasters/ workshops and main event - **HULL 2017** |  |  |
| 14/09/17 | 14/09/17 | Evaluation and sharing from programme gathered by this date |  |  |
| 14/09/17 | 14/09/17 | Launch of Hull Young Creatives Collective |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances