**Humber Bridge Test 2**

|  |  |  |
| --- | --- | --- |
| **Date & time** | **Activity** | **Notes** |
| **August 30th**09:0014:00 | Prepare LED strings for rigging at Bridge workshopRope Access crew arrive onsite:* Project briefing
* Site induction
* Go to top of Hessle tower
* Access the main cable
 | Roger Barrett / StarDamian Walsh and crew / Hull 2017 |
| **August 31st**09:0016:0019:0022:00(approx) | Traffic Management installedEast footpath closedRope access crew prep kitTest rig LEDs on hangers near Hessle towerTM removed and site clear by this timeOnsite to connect power and control equipment\*power required from Hessle Tower\*Lighting testTest EndsFootpath remains closed overnight | TM contractorStarHull 2017 / StarHBB |
| **Sept 1st**09:0016:00 | **Contingency Day**Install TM in work areaInstall as per schedule for 31st (if no rigging possible on 31st)ORDering LEDsTM removed by this time and site clearEast Footpath reopens (if derig is complete) | TM ContractorStarStar |
| **Sept 2nd** 09:0016:00 | **Contingency Day 2 – required if de rig does not happen on Sept 1st**Install TM in work areaDe rig LEDsTM removed by this time and site clearEast Footpath reopens | TM contractorStar |