## Sheet1
PROJECT NAME | Lilian's Lament
DATE | 16.12.16
Rehearsal Schedule |  |  |  |  | Times | Technical in Guildhall | Notes
W/C | Note | Location | Activity | #
2017-06-12
2017-06-13 |  | Manchester/Hull | Casting of Professional Cast
2017-06-14 |  | Manchester/Hull | Casting of Professional Cast
2017-06-15
2017-06-16
2017-06-17 |  | Holy Apostle | Community Cast Auditions |  |  |  | 3 sessions of 20-25 people
2017-06-18 |  | Holy Apostle | Community Cast Auditions |  |  |  | 3 sessions of 20-25 people
2017-06-19
2017-06-20 |  | Manchester/Hull | Casting of Professional Cast
2017-06-21 |  | Manchester/Hull | Casting of Professional Cast
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26
2017-06-27
2017-06-28 |  | Manchester/Hull | Casting of Professional Cast
2017-06-29
2017-06-30
2017-07-01
2017-07-02
2017-07-03
2017-07-04 |  |  | Casting of Professional Cast
2017-07-05 |  |  | Casting of Professional Cast
2017-07-06
2017-07-07
2017-07-08 |  | Holy Apostle | Community Cast Auditions |  |  | Sarah Not available | 3 sessions of 20-25 people
2017-07-09 |  | Holy Apostle | Community Cast Auditions |  |  |  | 3 sessions of 20-25 people
2017-07-10 | [6 empty] | Imogen not availble until 22 Aug
2017-07-11
2017-07-12
2017-07-13
2017-07-14
2017-07-15
2017-07-16
2017-07-17
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02
2017-08-03
2017-08-04
2017-08-05 |  | Holy Apostle | Community Cast Rehearsals | 1 |  |  | Imogen not available 10 July - 22 Aug.
2017-08-06 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-08-07
2017-08-08
2017-08-09
2017-08-10
2017-08-11
2017-08-12 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-08-13 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-08-14
2017-08-15
2017-08-16
2017-08-17
2017-08-18
2017-08-19 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-08-20 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-08-21
2017-08-22 | [6 empty] | Imogen not available
2017-08-23
2017-08-24
2017-08-25
2017-08-26 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-08-27 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-08-28
2017-08-29
2017-08-30
2017-08-31
2017-09-01
2017-09-02 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-03 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-10 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-17 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-24 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-09-25
2017-09-26
2017-09-27
2017-09-28
2017-09-29
2017-09-30 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-10-01 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-10-02 | Rehearsal Week 1 | Manchester | Professional Cast rehearse in Manchester
2017-10-03 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-04 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-05 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-06 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-07 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-10-08 |  | Holy Apostle | Community Cast Rehearsals | 1
2017-10-09 | Rehearsal Week 2 | Manchester | Professional Cast rehearse in Manchester
2017-10-10 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-11 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-12 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-13 |  | Manchester | Professional Cast rehearse in Manchester
2017-10-14 |  |  | Community Cast Rehearsals | 1
2017-10-15 |  |  | Community Cast Rehearsals | 1
2017-10-16 | Rehearsal Week 3 | Holy Apostle | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm |  | Composer / MD rehearse in Hull (2 Days)
2017-10-17 |  | Holy Apostle | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm
|  | Holy Apostle | Joined by Community Cast in the evening | 1 | 6 - 9 pm |  | NB First time for whole company to be together - professional & community cast
2017-10-18 |  | Holy Apostle | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm
2017-10-19 |  | Holy Apostle | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm |  | Full Council Meeting 9am - 4pm Chamber
|  | Holy Apostle | Joined by Community Cast in the evening | 1 | 6 - 9 pm
2017-10-20 |  | Holy Apostle | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm
2017-10-21 |  | Holy Apostle | Professional Cast rehearse in Hull |  | 10am - 5pm
|  | Holy Apostle | Joined by Community Cast all day | 1 | 10am - 5pm
2017-10-22 |  |  | FREE |  | No Call
2017-10-30 | Tech Week | Reh Sp 2 | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Technical Work | Composer/MD rehearse in Hull (full week)
|  | Reh Sp 2 | Joined by Community Cast | 1 | 5 - 9pm
2017-10-31 |  | Reh Sp 2 - AM Guildhall - PM | Technical Rehearsals: Professional Cast |  | 10am - 5pm; 6 - 9pm | Tech Sessions | call times for community cast TBC - as many will be working during day
|  | Guildhall | Joined by Community Cast | 1 | 5 - 9pm
2017-11-01 |  | Guildhall | Technical Rehearsals: Professional Cast |  | 10am - 5pm; 6 - 9pm | Tech Sessions
|  | Guildhall | Joined by Community Cast | 1 | 5 - 9pm
2017-11-02 |  | Guildhall | Technical Rehearsals: Professional Cast |  | 10am - 5pm; 6 - 9pm | Tech Sessions
|  | Guildhall | Joined by Community Cast | 1 | 5 - 9pm
|  | Guildhall | Full Band Call |  | 10am - 5pm; 6 - 9pm |  | Noise & timings to be confirmed with Guildhall; Guildhall business in process to 4pm
2017-11-03 |  | Guildhall | Dress Rehearsal - Full Company Call (Cast, Band, Community) |  | 1 - 5pm | Tech Session AM | Noise & timings to be confirmed with Guildhall; Guildhall business in process to 4pm No Weddings - Guildhall to keep clear of bookings
|  | Guildhall | Performance PREVIEW | 1 | 7.30pm
2017-11-04 |  | Reh Sp 2 | Full Company Call |  | 1 - 3.30pm | Technical Work
|  | Guildhall | Full Company Call |  | 3.30 - 5pm
|  | Guildhall | Performance PREVIEW | 1 | 7.30pm
2017-11-05 |  |  | Total Perfs | 2
2017-11-06 | Performance Week 1 | Guildhall | Tech Work; |  |  | Technical Work
No call Professional cast, community cast, band.
2017-11-07 |  | Guildhall | Technical Rehearsals: Professional cast and community cast |  | 2 - 5; 6 - 9pm
2017-11-08 |  | Guildhall | Technical Rehearsals: Professional cast and community cast |  | 2 - 5pm
|  |  | Performance | 1 | 7.30pm
2017-11-09 |  | Guildhall | Performance PRESS | 1 | 7.30pm
2017-11-10 |  | Guildhall | Performance | 1 | 7:30pm
|  | Guildhall | Performance | 1 | 7:30pm
2017-11-11 |  | Guildhall | Performance | 1 | 5:30pm
|  | Guildhall | Performance | 1 | 8:30pm
2017-11-12 |  |  | Performance | 1 | 5:30pm
|  |  | Performance | 1 | 8:30pm
|  |  | Total Perfs | 8
2017-11-13 | Performance Week 2 |  | No Call
2017-11-14 |  |  | No Call
2017-11-15 |  | Guildhall | Performance | 1 | 7.30pm
2017-11-16 |  | Guildhall | Performance | 1 | 6pm
|  | Guildhall | Performance | 1 | 7.30pm
2017-11-17 |  | Guildhall | Performance | 1 | 6pm
|  | Guildhall | Performance | 1 | 7:30pm
2017-11-18 |  | Guildhall | Performance | 1 | 5:30pm
8:30pm
2017-11-19 |  | Guildhall | Performance FINAL | 1 | 5:30pm
|  |  | Total Perfs | 7 | 8:30pm
GET OUT
2017-11-20 |  |  | GET OUT CONT
2017-11-21
2017-11-22
2017-11-23
2017-11-24
|  |  | Community Rehearsal Days / Sessions | 22
|  |  | Professional and Community Rehearsal Days / Sessions | 7
|  |  | Performances in total | 17 | 14 in budget.
Composer / Music
Astronmoical twilight 5:31pm