**Hull 2017
Project Plan**Hull 2017
***Ballad of Big Lil***
by Maxine Peake

Music & Lyrics Adrian McNally & The Unthanks
Director Sarah Frankcom

**Summary**

Inspired by the women who campaigned for better and safer working conditions on Britain’s trawler ships, the Ballad of Big Lil is a site specific project with a strong mix of music, movement and text. The production explores Hull’s heritage as a port city, and celebrates the hard and dangerous life of trawlerman ruled by a feudal system of ship owners in a voracious capitalist system. At the heart of the story is Lillian Bilocca, a women who dared to speak out and take action to improve conditions for men at sea. With a community chorus, live music and an open bar, the evening will be a visceral, joyous evening of song, music & theatre.

**Venue** TBC

A civic space with the faded grandeur of the past.
Current options being considered include the Guildhall, Hull

**Music** New works written by Adrian McNally and The Unthanks. To be performed live by the Unthanks.
One song, the Ballad of Big Lil, to have lyrics by Maxine Peake, with original music by Adrian McNally and the Unthanks.

**Cast & Band**  Maximum cast size = 7

Maximum band size = 4

**Project Timeline**

June 16 Brief delivered to Hull 2017 by Maxine Peake

July 16 Commission the script,
Secure director, Confirm details of RET involvement

August 16 Site scouting & site to be identified.
Secure dramaturg, designer, choreographer, sound & lighting designer production manager

22 Sept 16 Hull 2017 UK City of Culture Launch

10 -14 Oct R&D in Manchester.
To be arranged by Michelle Hickman from Manchester
Royal Exchange with actors from Streetcar.
In attendance: Maxine Peake
 Sarah Frankcom
 Adrian McNally

Oct 16 First full draft of the script delivered.
Image & copy generated

Nov 11 Confirm site – venue contracts

Jan 17 Final script delivered

 Sign off brochure page

April 17 Prelim designs & outline costings

 Casting & stage management team

July 17 Casting of Community Cast

 Final designs & detailed costings

Sept 17 Pre-Production – build & prep venue

Oct 17 Rehearse

 Install at venue

Nov 17 Tech, open & perform

Dec 17 Close

 **The following details describe the production parameters which reflect the project budget

Creative Team**
Writer Maxine Peake
Director Sarah Frankcom
Music & lyrics Adrian McNally & The Unthanks TBC

Set & Costume Designer Amanda Stoodley TBC
Lighting Designer Chris Davey TBC
Sound Designer Peter Rice TBC
Casting Director

Dramaturg Steven Greenhorn TBC
Associate Director (Comm Cast) to be Hull based

Consultant Rupert Creed TBC

**Production Team**
Production Manager
Company Manager
DSM
ASM
Sound Op
LX Op
Dresser
Technician
Production Sound

Production LX
Costume Supervisor

FOH Manager
Box Office Manager & Assistant

Stewards
Security
Access Performance Interpreter

Bar staff Licensee & Operator TBC

**Production Schedule**
All dates to be discussed and confirmed with MP/SF

Rehearsals Week 1 w/c 2 Oct 2107 Reh in Manchester
Rehearsals Week 2 w/c 9 Oct Reh in Manchester
Rehearsals Week 3 w/c 16 Oct Reh in Hull
Rehearsals Week 4 w/c 23 Oct Reh in Hull

Production / Tech Week w/c 30 Oct
First Preview Fri 3 Nov
Second Preview Sat 4 Nov
Performance Week 1 w/c 6 Nov

Press Night Tues 7 Nov or Wed 8 Nov

Perf Week 2 w/c 13 Nov

Perf Week 3 w/c 20 Nov

Perf Week 4 w/c 27 Nov
Final Performances Sat 1 Dec 2017

Proposal for possible Comm Ensemble process:
Community Cast To be 16 + years old
 Overall Group of 30 – for min 20 per perf
 Rehearsals In Hull
 3 sessions a week, evenings & weekend
 6 sessions during Tech Week, daytime, evening & Sat
 6 performances per week during run

Min 6 performances per week inc one matinee.