## places des anges
Item | Supplier | 1 Show Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | Order address | Telephone | email | Order wording | Order cost exVAT | Insurance values
FEES
Handling fee | TGPS | 1500 |  |  | Handling fee | [7 empty] | -------------
FEES SUB-TOTAL |  |  |  | 1500
CREW | [12 empty] | -------------
get-in/out crew | YEC | 3828 |  |  | 4 crew for 4 hrs Mon, 6 crew Tues, Weds and 8 crew Sun | inc. crew boss rate and travel | ordered 01/06 | [5 empty] | -------------
gen crew | YEC | 1066 |  |  | 2 men Thurs, Fri, Sat | general duties - fencing, power etc | ordered 01/06 | [5 empty] | -------------
Follwspot crew | YEC | 1680 |  |  | 8 crew for 3 x 4 hour calls @ £70 per call - tech, dress & 2 shows |  | received quote 29/02 | [5 empty] | -------------
Blower crew |  | volunteers |  |  | 10 Crew for set-up, Dress & 1 show | tech, dress and 2 x shows 4 hr call only Volunteers? | [6 empty] | -------------
angel crew |  | volunteers |  |  | 2 crew to assist with Angel - dress & 2 shows | Volunteers? | [6 empty] | -------------
crowd control |  | volunteers |  |  | 12 people to assist company moving thru crowd | Volunteers or Stewards? | [6 empty] | -------------
CREW SUB-TOTAL |  |  |  | 6574
PA HIRE
main PA | 3d | 5600 |  |  | 2 x show days & 2 x rehearsal days |  | ordered 24/05 | [5 empty] | 560000
delays | 3d | 1200 |  |  | for gardens |  | ordered 24/05 | [5 empty] | inc above
rehearsal pa | 3d | 300 |  |  |  |  | ordered 24/05 | [5 empty] | inc above
Pa towers | 3d | 1000 |  |  | inc decks for delays |  | ordered 24/05 | [5 empty] | inc above
Pa crew | 3d | 1800 |  |  |  |  | ordered 24/05 | [5 empty] | inc above
crew transport | 3d | 144 |  |  |  |  | ordered 24/05 | [5 empty] | inc above
crew accomodation | 3d | 195 |  |  | charged at £65 per night |  | ordered 24/05 | [5 empty] | inc above
PA delivery | 3d | 320 |  |  |  |  | ordered 24/05 | [5 empty] | inc above
PA HIRE SUB-TOTAL |  |  |  | 10559
LIGHTING HIRE
Lighting | HSL | 3018.44 |  |  | 22 x G-spots and 10 x p2's |  | ordered 24/05 | [5 empty] | 216500
F/spots | TSS | 4210 |  |  | 8 x f/spots @ £315 per week |  | ordered 24/05 | [5 empty] | 178399
Lighting desk | TSS | 690 |  |  | Grand Ma2 Lite | inc delivery | ordered 24/05 | [5 empty] | inc in N25
cable allowance | HSL | 401.9 |  |  | to cover cabling required |  | ordered 24/05 | [5 empty] | inc in N24
wireless DMX | HSL | 280 |  |  |  |  | ordered 24/05 | [5 empty] | inc in N24
DDA cable ramp | IDE | 400 |  |  | 80 panels | to cover blower cable | ordered 24/05 | [5 empty] | inc in N45
comms - O1 | Warehouse | n/a | 1321 |  | radio comms | 10 x headsets | received quote 08/03 | [5 empty] | -------------
comms - O2 | Stage electrics | n/a | 554 |  | radio comms | 8 x wireless headsets & 4 x wired | received quote 31/03 | [5 empty] | -------------
Comms | 3d | 300 | 300 |  | 10 sets of wired comms |  | ordered 24/05 | [5 empty] | inc in N14
Lighting delivery | HSL | 500 |  |  | 17t |  | ordered 24/05 | [5 empty] | -------------
Battery operated floods | PaBoom | 130 |  |  | for gates and launch sites | [7 empty] | 800
LIGHTING HIRE SUB-TOTAL |  |  |  | 9800.34
POWER & DISTRO
Main Generators | generator power | 590 |  |  | 2 x 200KVA sync sets | inc cabling | ordered 01/06 | [5 empty] | 65000
fuel tank | generator power | 30 |  |  | 2000l tank |  | ordered 01/06 | [5 empty] | 3000
police station backstage generator | generator power | 0 |  |  | 40KVA road tow | hard power in garage | cancelled 11/06 | [5 empty] | -------------
fuel tank | generator power | 28.57 |  |  | towable fuel bowser |  | ordered 01/06 | [5 empty] | 2500
Guildhall generator | generator power | 100 |  |  | 40KVA | to get 32-3 up tower | ordered 01/06 | [5 empty] | 12000
police station show generator | generator power | 100 |  |  | 40KVA |  | ordered 01/06 | [5 empty] | 12000
Round tower generator | generator power | 100 |  |  | 40KVA |  | ordered 01/06 | [5 empty] | 12000
Guildhall cabling | IDE | inc below |  |  | 100m 63-3 & distro | maybe start at 63-3 | ordered 24/05 | [5 empty] | 35181.76
distro | IDE | 740 |  |  | distro as required |  | ordered 24/05 | [5 empty] | inc in N45
cabling | IDE | 474 |  |  | 3 phase cabling as required |  | ordered 24/05 | [5 empty] | inc in N45
Delivery | IDE | 320 |  |  |  |  | ordered 24/05 | [5 empty] | -------------
7909 sign off | TGPS | 300 | [10 empty] | -------------
Fuel | generator power | 1400 |  |  | ESTIMATE | charged after event | received quote 25/02 | [5 empty] | 3500
Delivery | generator power | 1180 |  |  |  |  | received quote 25/02 | [5 empty] | -------------
POWER & DISTRO SUB-TOTAL |  |  |  | 5362.57
STRUCTURES
Disabled viewing platform | 3d | 0 |  |  | Don't need, use roped off area by FOH |  | ordered 24/05 | [5 empty] | inc in N14
F/spot platforms | 3d | 200 |  |  | 5 no. 8x8 @ 2m |  | ordered 24/05 | [5 empty] | inc in N14
FOH position | 3d | 300 |  |  | 4m x 2m @ 1m | uncovered for dress & shows? | ordered 24/05 | [5 empty] | inc in N14
staging delivery | 3d | 1000 |  |  |  |  | ordered 24/05 | [5 empty] | inc in N14
build crew | 3d | 1496 |  |  |  |  | ordered 24/05 | [5 empty] | inc in N14
FOH cover | TGPS | 50 |  |  | 3m pop-up with ballast | delivered Weds 29th, de-rigged with others | received quote 09/02 | [5 empty] | 500
tech marquee | TGPS | 50 |  |  | 3m pop up | [7 empty] | 500
Staircase | B & A | 1895 |  |  |  |  | ordered 02/06 | [5 empty] | -------------
STRUCTURES SUB-TOTAL |  |  |  | 4991
Item | Supplier | 1 Show Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | Order address | Telephone | email | Order wording | Order cost exVAT | Insurance values
MISCELLANEOUS
skips | transwaste Ltd | 200 |  |  | 1 large skip | for college carpark | just need to pay invoice | [5 empty] | 3500
ballast | transwaste Ltd | inc above |  |  | 16t ballast, in skip |  | just need to pay invoice | [5 empty] | 1600
ballast | JP concrete | 893 |  |  | 2 x 1t & 2 x 2t concrete blocks | inc delivery | ordered 30/05 | [5 empty] | 238
Helium | BOC | 739.85 |  |  | 25m3 helium | 3 x L size @ £225.68 per bottle | ordered 14/06 | [5 empty] | 950
Delivery | BOC | inc above |  |  | delivery and collection of bottles | £52.55 delivery, £14.40 collection | ordered 14/06 | [5 empty] | -------------
street lighting | KWL | 868 |  |  | charge to turn off street lights |  | ordered 2/06 | [5 empty] | -------------
radio Comms | Hull Events team | FOC | [10 empty] | 24000
extra comms | 900 communications | 94.72 |  |  | 10 x noise cancelling headsets & 20 x fist mics |  | ordered 24/05 | [5 empty] | 1417
Artistic lodge | College | 0 |  |  | dressing room/base for company for duration of stay. c/w mirrors furniture, fridges etc | use 1 of the buildings Helen talked about using as a control room | [6 empty] | -------------
catering eqpt | College | 0 |  |  | fridges, urns etc for lodge | inc mirrors & furniture | [6 empty] | -------------
mirrors | ?? |  |  |  | 15 mirrors for dressing room
clothes rails | ?? |  |  |  | 3 cossie rails | with 30 hangers
chairs | All occasions | 150 |  |  | 80 x chairs for accessible area | inc delivery | ordered 1/06 | [5 empty] | 960
Parking costs | Hull CC | 470 |  |  | to suspend all 47 bays on Guildhall road |  | asked Tracey for an invoice 06/06 | [5 empty] | -------------
Timber | various | 100 |  |  | for spreaders as per spec | inc 2 x 2.4m railway sleepers | [6 empty] | 100
Flares | Pa Boom | 25.5 |  |  | 3 x flares, as per rider | [7 empty] | 25.5
pond/air con covering | B&A | 400 |  |  | 8 no. 3m x 50m rolls @ £50 per roll | Look at rigging | ordered 02/06 | [5 empty] | 400
backstage/build toilets | Add Plant | 200 |  |  | 2 x plastics behind police station | 2 week hire | ordered 02/06 | [5 empty] | 1200
Public toilets | Add Plant | 910 |  |  | 15 x plastics and 2 x disabled | delivered Saturday am | ordered 02/06 | [5 empty] | 11400
servicing | Add Plant | 40 |  |  | service Thursday |  | ordered 02/06 | [5 empty] | -------------
delivery collection | Add Plant | 230 |  |  |  |  | ordered 02/06 | [5 empty] | -------------
Cleansing | council | 754.94 |  |  | Show & FOH cleansing after show and after get-out |  | ordered 02/06 | [5 empty] | -------------
MISCELLANEOUS SUB-TOTAL |  |  |  | 6076.01
PLANT & BARRIERS
Forks | Nixons | 250 |  |  | 10.5m telehandler | 1 week | ordered 24/05 | [5 empty] | 42000
delivery |  | 260 |  |  | £130 e/w |  | ordered 24/05 | [5 empty] | -------------
barriers | Event solutions | 300 |  |  | 200 Fixed leg crowd barriers | £1.50 per panel | ordered 24/05 | [5 empty] | 7620
Fencing | Event solutions | 75 |  |  | 50 Heras sets | £1.50 per panel | ordered 24/05 | [5 empty] | 2208
Delivery/collection | Event solutions | 300 |  |  | for above | £150 e/w | ordered 24/05 | [5 empty] | -------------
PLANT & BARRIERS SUB-TOTAL |  |  |  | 1185
STEWARDING
Stewarding | Prestige | 6728.5 |  |  | as per spreadsheet |  | ordered 13/06 | [5 empty] | -------------
additional stewarding | Prestige | 580 |  |  | for rigging of wires |  | ordered 13/06 | [5 empty] | -------------
security | Prestige | inc above | [10 empty] | -------------
STEWARDING SUB-TOTAL |  |  |  | 7308.5
TM
road closures | council | 0 | [10 empty] | -------------
TM | Centurion | 2350 |  |  | advance signage, 1 man Tues, Weds, Thurs & Fri, 2 men sat Sun |  | ordered 01/06 | [5 empty] | -------------
TM SUB-TOTAL |  |  |  | 2350
H&S
structural engineer | Star Events | 1 |  |  | star providing FOC | [7 empty] | -------------
Rigging check | Star Events | 0 |  |  | star providing FOC | [7 empty] | -------------
insurance | HULL17 | [11 empty] | -------------
police station edge protection | B&A | 1486 |  |  |  |  | ordered 08/06 | [5 empty] | -------------
Medical | St Johns | 1192 |  |  | show cover |  | received 01/06 | [5 empty] | -------------
Medical | St Johns | 550 |  |  | rehearsal cover |  | received 01/06 | [5 empty] | -------------
Lost kids provision | Prestige | 126 |  |  | 2 people to look after lost kids |  | ordered 13/06 | [5 empty] | -------------
Fire extinguishers | TGPS | 100 |  |  | Extinguishers as required | [7 empty] | 1500
H&S SUB-TOTAL |  |  |  | 3455
TOTALS Ex Contingency - EX VAT |  | 59291.42
CONTINGENCY | VARIOUS | 2208.58
TOTALS inc Contingency - EX VAT |  | 61500 |  | 59161.42 | [7 empty] | 0 | 1200999.26
TOTALS - INC VAT |  | 73800

## TGE Fees
Item | Supplier | Cost ex vat | Description | Notes
Production Prep time | TGE | 1755 | 9 Days @ £195 per day | 1 day to be charged to a separate budget
H&S prep time | TGE | 780 | 5 Days @ £195 per day | Not including meetings
Tim provisional site visit | TGE | 0 | 1 day @ £195 | Charged to a separate budget
Adam site visits | TGE | 0 | 2 Days @ £195 per day | Charged to a separate budget
meetings | TGE | 1200 | 12 Meetings charged at £100 meeting
Site/production manager | TGE | 2450 | 7 Days @ £350 per day | Monday - Sunday
on site H&S | TGE | 840 | 2 Days @ £420 per day | dress rehearsal & show days
mileage | TGE | 720 | 12 Round trips of 150 miles @ £0.40 per mile
accomodation | TGE | TBP | ? Rooms for ? Nights
Lighting crew | TGE | 2470 | lighting crew charged @ £190 pppd | 2 men Weds, 4 men Thurs, 2 men Fri, 1 man Sat, 4 men Sn
Light crew PD's | Tge | 260 | charged at £20pppd | 13 man days
TGE TOTAL Ex VAT |  | 10475
In addition, Hull 2017 will provide and pay for:
Hotel accommodation for Site / Production Manager and Safety Manager as required over the build / event period
Catering or per diems (depending on arrangements) for Site / Production Manager, Safety Manager