## BUDGET
Hull Children's Literature Festival
VENUE | East Park
DATES | June - 10 days
SHOW TIMINGS | 10am to 8pm
NOTES
Capacity | 1000
ELEMENTS
Information Point | Tent
Lost Children and Vulnerable Adults | Tent
Picnic area | Picnic area
Toilets - baby change
1x large structure | Big top | Potential to host a large awards dinner one night at the start of the run
4x smaller structures | inflatable
Backstage storage area
Dressing
Security
First aid
Power
AV in tents
H&S equipment
NOT INCLUDED IN BUDGET
Branded covers | 4000
Production Management staffing
Parks fee
Insurance
Incidentals
Contingency
BUDGET
Production
AREA 1 | ITEM | HIRE PERIOD | UNIT PRICE | NUMBERS
Large Big top - also available for awards evening
| 42m round blacked out Big Top plus flooring (board/carpet) | 12 days |  |  |  | 12000
| Flooring |  |  |  |  | 6550
Awards Production | Staging/Lighting/Sound - Awards Ceremony | 2 days |  |  |  | 12000
| Stage management |  |  |  |  | 800
| Chairs |  | 4 | 500 |  | 2000
AREA 2
Picnic Area | Picnic tables | 10 days | 30 | 50 |  | 1500
AREA 3
1x 10mx10m inflatable cube | Hire of inflatable cube | 11 days | 650 |  |  | 7150
| Flooring |  | 500 | 1 |  | 500
| Heater |  | 150 | 1 |  | 150
| Lighting |  | 120 | 1 |  | 120
| PA system |  | 500 | 1 |  | 500
AREA 4
1x 10mx10m inflatable cube | Hire of inflatable cube | 11 days | 650 |  |  | 7150
| Flooring |  | 500 | 1 |  | 500
| Heater |  | 150 | 1 |  | 150
| Lighting |  | 120 | 1 |  | 120
| PA system |  | 500 | 1 |  | 500
AREA 5
1x 10mx10m inflatable dome | Hire of inflatable dome | 11 days | 650 |  |  | 7150
| Flooring |  | 500 | 1 |  | 500
| Heater |  | 150 | 1 |  | 150
| Lighting |  | 120 | 1 |  | 120
| PA system |  | 500 | 1 |  | 500
AREA 6
1x 10mx10m inflatable dome | Hire of inflatable dome | 11 days | 650 |  |  | 7150
| Flooring |  | 500 | 1 |  | 500
| Heater |  | 150 | 1 |  | 150
| Lighting |  | 120 | 1 |  | 120
| PA system |  | 500 | 1 |  | 500
AREA 7
Backstage | 6m x 9m Event Control/Production tent |  | 360 |  |  | 720
| Cabin | Secure store | min. 4 week hire |  |  | 426
| Fencing |  | 64m Heris |  |  | 130
| Scrim |  |  |  |  | 800
| seating and tables |  |  |  |  | 150
AREA 8
Welfare | 6mx 3m white clearspan marquee |  | 200 |  |  | 400
Information | 3mx3m white clearspan marquee |  | 150 |  |  | 300
Seating and tables | [5 empty] | 400
71856
Site/Event
Toilets | 14x single unit |  | 38 | 14 |  | 532
| 4x Baby change/accessible |  | 80 | 4 |  | 320
| 6x services |  | 200 | 6 |  | 1200
Waste Management | 6x 1100 euro bins | 6x empties |  |  |  | 900
| Litter pickers |  |  |  |  | 1056
Welfare - Lost Children's | [5 empty] | 2420
Water - staff | [5 empty] | 500
Staff/Crew/Artist Catering | [5 empty] | ??
Power | 1x 13 KvA | Backstage | 450 |  |  | 900
| 1x 13 KvA | 1x cube | 450 |  |  | 900
| 1x 13 KvA | 1x cube | 450 |  |  | 900
| 1x 13 KvA | 1x dome | 450 |  |  | 900
| 1x 13 KvA | 1x dome | 450 |  |  | 900
| 1x 45 KvA | 1x Bigtop | 650 |  |  | 1300
| Fuel |  |  |  |  | 2000
Security | [5 empty] | 19992
First Aid | [5 empty] | 4510
Crew | [5 empty] | 3400
Fencing | Perimeter | 549 | 3.5m Heris |  |  | 1066
Communication | 8x Radios |  |  |  |  | 200
Plant | Telehandler |  |  |  |  | 750
Fire fighting equipment | 2x extinguishers per smaller structure | 8 |  |  |  | 320
| 6x extinguishers for bigtop | 6 |  |  |  | 240
| 1x extinguisher per gen | 6 |  |  |  | 240
| 2x extinguisher Backstage area | 2 |  |  |  | 80
45526
Signage/Dressing/Branding
Area flags
2x per small structure |  |  | 150 |  |  | 1500
4x for large structure |  |  | 150 |  |  | 600
1x lost children's | [5 empty] | 150
1x first aid | [5 empty] | 150
Festival flags - picnic area | [5 empty] | 600
Bunting |  |  | 225m custom print |  |  | 700
Signage |  | Toilets, entrance, exit, etc |  |  |  | 250
3950
[5 empty] | TOTAL | 121332 | EXC VAT

## SCHEDULE
SCHEDULE
DRAFT

## STAFF
STAFFING
DAY
[16 empty] | RIG | RIG | RIG | SHOW | SHOW | SHOW | SHOW | SHOW | SHOW | SHOW | SHOW | SHOW | SHOW | SHOW | DERIG | DERIG
| SECURITY | HR | NO | COST PER HR |  | FIRST AID |  |  | LITTER PICKERS |  |  | LOST CHILDRENS WORKERS |  |  | CREW | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
DAY -3 | 08:00 - 18:00 | 10 | 2 | 14 | 280 | SHOW ONLY | 2x plus medium first aid unit
| 18:00 - 08:00 | 14 | 2 | 14 | 392
DAY -2 | 08:00 - 18:00 | 10 | 2 | 14 | 280 | [9 empty] | 400
| 18:00 - 08:00 | 14 | 2 | 14 | 392
DAY -1 | 08:00 - 18:00 | 10 | 2 | 14 | 280 | [9 empty] | 600
| 18:00 - 10:00 | 16 | 4 | 14 | 896
DAY 1 | 09:30 - 20:30 | 11 | 6 | 14 | 924 | 12.5 | 2 | 410 | 8 | 2 | 96 | 10 | 2 | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 2 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 3 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 4 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 5 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 6 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 7 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 8 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 9 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 09:30 | 13 | 4 | 14 | 728
DAY 10 | 09:30 - 20:30 | 11 | 6 | 14 | 924 |  |  | 410 |  |  | 96 |  |  | 220 | 200
| 20:30 - 08:00 | 12.5 | 4 | 14 | 728
DAY 11 | 08:00 - 18:00 | 10 | 2 | 14 | 280 |  |  | 410 |  |  | 96 |  |  | 220 | 400
| 18:00 - 08:00 | 14 | 2 | 14 | 392
DAY 12 | 08:00 - 18:00 | 10 | 2 | 14 | 280
[5 empty] | 19992 |  |  | 4510 |  |  | 1056 |  |  | 2420 | 3400