## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | The Project is not delivered on time | Inability to deliver project; Significant legal, financial and reputational repercussions for all partners | John Hunter | 1 | 4 | 4 | Agreed project milestones/ deliverables to be established between both parties. The Project Manager will oversee milestones and the overall project schedule and will flag any arising issues with Hull 2017 and Aarhus 2017 and Aarhus 2017 for discussion. If for any reason a particular project date cannot be met/ needs to be moved, the communications team will manage the public messaging around this in consultation with Hull 2017 and Aarhus 2017 and Aarhus 2017. Regular communication between both parties will be maintained throughout the project. | 1 | 3 | 3
2 | A particular project milestone or deliverable is not met | Additional pressure on core team | John Hunter | 4 | 2 | 8 | The Project Manger will oversee milestones and deliverables and will flag any issues or changes with Hull 2017 and Aarhus 2017 in a timely manner | 2 | 2 | 4
3 | Project Exceeds budget | Inability to deliver project as intended | John Hunter | 2 | 4 | 8 | Ample contingency has been allocated to ensure the project does not exceed budget. The budget will be reviewed monthly by the Lead Artist, Project Manager and Administrator at Blast Theory. The project scope / outputs will be reviewed continuously throughout the project to ensure they are achievable within allocated budget and resources. In the event that the scope of the project needs to be amended due to budget constraints/ implications, BT would raise this with Hull 2017 and Aarhus 2017 for further discussion | 1 | 3 | 3
4 | Lead Artist becomes unwell / is unable to deliver the project | Works takes longer than necessary | John Hunter | 2 | 3 | 6 | In the event that the Lead Artist is unable to work on the project, another artist at Blast Theory would be allocated to this role. The Lead Artist will ensure that other team members are appropriately briefed on the project so that they can provide support / cover if required | 2 | 2 | 4
5 | Other key project team members become unwell / are unable to deliver the project | Works takes longer than necessary | John Hunter | 2 | 3 | 6 | Key project team members would be replaced with alternative staff. The project is well documented to enable easy handover to new/other team members. Contingency money could be used to provide additional staffing support if necessary | 2 | 2 | 4
6 | Project does not meet brief / desired objectives | Reputational damage with creative team, stakeholders and general public | Nick Tandavanitj | 2 | 4 | 8 | Agreed project outputs and milestones have been agreed between parties to make sure expectations are clear. Regular communication between both parties will be maintained throughout the project. A concept/ synopsis for the films and other major project outputs will be shared with Hull 2017 and Aarhus 2017, to ensure both parties are happy that the brief is being met – prior to production. | 1 | 3 | 3
7 | Inappropriate or poor quality project outputs | Reputational damage with creative team, stakeholders and general public | John Hunter | 1 | 4 | 4 | Project outputs will be monitored and a sign off process will be established to ensure both organisations are happy. The intended project outputs/ materials are family friendly and not offensive or inflammatory. The communications teams at BT and Hull 2017 and Aarhus 2017 will continue to have an overview on the project and advise on public perception / sensitivities etc. | 1 | 2 | 2
8 | Audiences do not engage with the project as desired | Failure to achieve project objectives and Hull 2017 and Aarhus 2017 KPIs | Nick Tandavanitj | 3 | 3 | 9 | The communications teams at Hull 2017 and Aarhus 2017 and BT will promote the events and wider project on an ongoing basis to encourage engagement. The nature of the project encourages community involvement and ongoing engagement. | 2 | 2 | 4
9 | Audience figures do not meet desired targets | Failure to achieve project objectives and Hull 2017 and Aarhus 2017 KPIs | Chloe Barker | 3 | 3 | 9 | All three parties' communications teams will work together in agreeing targets and actions, reviewing these regularly and taking additional action where necessary. All teams working with experienced communications and PR professionals with a combination of community, national and international reach. | 2 | 3 | 6
10 | Target numbers for Workshop participants are not reached | Failure to achieve project objectives and Hull 2017 and Aarhus 2017 KPIs | Nick Tandavanitj | 3 | 2 | 6 | Blast Theory will employ a Community Liaison Officer to reach groups for the workshops. | 1 | 2 | 2 | Closed
11 | Technology Issues could result in elements of the project not working (e.g. website, film screenings etc.) | Failure to deliver some aspects of the project | Nick Tandavanitj | 3 | 4 | 12 | BT are experienced working in interactive/ technology-based projects. Appropriate technical support will be allocated to the project. Most technical issues could be resolved without any major impact or implications to the project. | 1 | 3 | 3
12 | Data collection issues / breach of sensitive information | Significant legal, financial and reputational repercussions for all partners | John Hunter | 1 | 4 | 4 | Data collection policy implemented and data protection practices developed through previous work on data-sensitive projects. | 1 | 3 | 3
13 | IT issues could result in lost project documents / planning documents | Additional pressure on internal project team; work takes longer and key deadlines could be missed. | John Hunter | 1 | 4 | 4 | Mission-critical documents backed-up to cloud and sensitive documents backed up to internal redundant backup. | 1 | 1 | 1
14 | Disagreements between aspects of joint delivery with co-commissioners of 2097 | Relationships sour; work takes longer than necessary | Kirsty Jennings | 2 | 3 | 6 | Memorandum of Understanding in place between the two co-commissioners. | 1 | 3 | 3
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, e.g. all permissions are secured, all parties are contracted...