turner prize, Glasgow 2015 – key deadlines

|  | Task Description | Deadline | Responsible |
| --- | --- | --- | --- |
| 1 | Marketing strategy written | 25 November 2015 | Glasgow Life |
| 2 | Title lock provided by Tate | 15 January 2015 | Tate |
| 3 | Write copy for nominations on Tate web page | 12 March 2015 | Tate |
| 4 | Announce call for public nominations | 16 March 2015 | Tate |
| 5 | Public nominations close, list sent to the jury | 13 April 2015 | Tate |
| 6 | Jury submit long list (six artists) for discussion | 28 April | Tate |
| 7 | Jury meet to select artists | 5 May 2015 | Tate |
| - 8 | - Artists participation agreed | 5 May 2015 | Tate |
| - 9 | - Research artists, write and sign off press release and artist biographies | 5 – 12 May 2015 | Glasgow Life/ Tate |
| - 10 | - Lead press & marketing images selected and copyright cleared | 5 May – 5 June 2015 | Glasgow Life/ Tate |
| - 11 | - Internal press briefing pack compiled and circulated | 8 May | Glasgow Life/ Tate |
| - 12 | - Press conference to announce the four shortlisted artists | 12 May 2015 | Tate |
| 13 | Select/ agree top three awards ceremony presenters | 12 May 2015 | Glasgow Life/ Tate |
| 14 | Artists briefing meeting including Tramway site visit | 22 May 2015 | Glasgow Life/ Tate |
| 15 | Artist contracts signed | 01 June 2015 | Glasgow Life |
| 16 | Marketing identity developed and signed off by Tate |  |  |
| 17 | Exhibition content discussed with artists and agreed | End June 2015 | Glasgow Life |
| 18 | Loan letters sent | End June 2015 | Glasgow Life |
| 19 | Awards ceremony presenter confirmed | End June 2015 | Tate |
| 20 | Exhibition design submitted to Tate for review | Mid July 2015 | Glasgow Life |
| 21 | Artist films made | 19 June 2015 | Glasgow Life |
| 22 | Press event and opening night reception planned |  | Glasgow Life |
| 23 | Events guest lists compiled | 24 July 2015 | Glasgow Life/ Tate |
| 24 | Invitations to opening events designed and sent | 24 August 2015 | Glasgow Life |
| 25 | Curatorial media training (if required) |  | Glasgow Life |
| 26 | Press Preview Event for the Exhibition | 30 September 2015 | Glasgow Life |
| 27 | Private Reception/Opening event for the Exhibition | 30 September 2015 | Glasgow Life |
| 28 | Exhibition opens to the public | 1 October 2015 | Glasgow Life |
| 29 | Awards ceremony planned | 1 Oct – 1 Dec 2015 | Glasgow Life |
| 30 | Awards ceremony guest lists compiled | 02 October 2015 | Glasgow Life/ Tate |
| 31 | Invitations to opening events designed and sent | 19 October 2015 | Glasgow Life |
| 32 | Awards ceremony detailed event schedule and briefing pack signed off | 27 November 2015 | Glasgow Life/ Tate |
| 33 | Jury meet to decide Turner Prize winner (am) Awards Ceremony (pm) | 7 December 2015 | Glasgow Life |
| 34 | Exhibition closes | 10 January 2016 | Glasgow Life |