## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure of Blast Theory to deliver. | Significant legal, financial, and reputational repercussions for all partners. | Sam Hunt | 4 | 5 | 20 | Excellent reputation of Blast Theory with experience delivering artistic projects & project management. Clear contractual relationship based on devolved delivery model. Clear roles, responsibilities & deliverables outlined in the contract. | 3 | 5 | 15 | Open
2 | Artistic content not representative of vision. | Reputational damage with creative team, stakeholders, creative partners and general public. | Sam Hunt | 4 | 4 | 16 | Excellent reputation of Blast Theory, nationally and internationally. Scope & vision of content agreed between Blast Theory & EP. Well managed creative process - artistic assets approved by EP. | 3 | 3 | 9 | Open
3 | Artistic vision drift over course of project. Long delivery period. International project between Hull 2017 & Aarhus 2017. | Reputational damage with creative team, stakeholders, creative partners, and general public. | Sam Hunt | 4 | 4 | 16 | Good communication between Blast Theory & H17 on all artistic outputs for H17 elements. Connected to Aarhus as appropriate. Well managed relationships, regular communication & project meetings. Reporting built into payment schedule. | 3 | 3 | 9 | Open
4 | Multiple partners & cross department working on the project causes miscommunication and / or delays in decision making. | Relationships sour with partners. Decisions are delayed due to delays in approvals. Additional pressure on creative process & project management. | Lindsey Alvis | 4 | 4 | 16 | Organogram to outline multiple partner relationships & identify manager of each relationship. Key responsibilities of each partner outlined in contracts. Pre-agreed working practices & processes for approvals. | 4 | 4 | 16 | Open
5 | Blast Theory's failure to deliver safely and efficiently. | Significant legal, finacial, and reputational repercussions for all partners. | Sam Hunt / Tech & Ops lead? | 4 | 5 | 20 | Clear responsibility of Blast Theory for all project & event management, producing ESMP & RA and taking these through the ESAG process for filming & live elements. | 3 | 5 | 15 | Open
6 | Blast Theory's failure to deliver work with children and young adults safely and effectively. | Significant legal, financial, and reputational repercussions for all partners. | Sam Hunt | 5 | 5 | 25 | Clear responsibility for Safeguarding outlined in contract. Experience delivering cultural exchanges and working with children and young people. Advice on industry standard from qualified professionals when preparing Safeguarding documentation for Young People's Exchange & Workshops. Clear roles & responsibilities outlined in project team. | 3 | 5 | 15 | Open
7 | Blast Theory's failure to work with H17 volunteers according to our codes of practice. | Relationships sour with volunteers. | Hannah Williams Walton | 4 | 4 | 16 | Blast Theory to work closely with H17 Volunteering team to ensure working to codes of practise. Volunteer needs to be outlined early in process. | 3 | 3 | 9 | Open
8 | H17 staff insufficent experience, limited availability, miscommunication or absence. | Failure to deliver, delayed decision making, detrimental impact on project. | Sam Hunt / Lindsey Alvis TBD | 4 | 4 | 16 | SH lead EP on the project. Experienced project team. Clear roles & responsibilities. Regular project team meetings in the diary. Business contingency plan for staff absences due to illness to be developed. Other project commitments to be reviewed for autumn 2017 period. | 4 | 4 | 16 | Open
9 | Overspend on budget retained by H17. Overspend on budget held by Blast Theory. | Blast Theory goes over budget or project costs must be recouped from elsewhere. | Lindsey Alvis | 4 | 4 | 16 | Retained budget managed by LA - experienced in managing significant project budgets. Blast Theory experienced managing significant budgets. Blast Theory to report regular budget revisions to H17 as per payment schedule. Regular budget updates to be provided at project team meetings. | 3 | 4 | 12 | Open
10 | Failure to attract audiences. | Project does not meet audience targets. Reputational damage due to lesser audience experience. | Sarah Moore TBD | 4 | 4 | 16 | Clear MarComms plan to be agreed well in advance with regular creative updates. Audience expectations to be managed with clear project messaging. High audience attendance for othe H17 events. | 4 | 4 | 16 | Open
11 | Failure to market the project & incorrect PR messaging. | Audience expectations out of sync with work. Audiences left disappointed. | Sarah Moore / Alix Johnson TBD | 4 | 4 | 16 | Clear MarComms plan with messages and deliverables agreed. Regular project team meetings. Briefings direct with artist to avoid miscommunication. | 3 | 3 | 9 | Open
12 | Failure to engage participants in workshops & project as a whole. | Project does not meet engagement targets | James Maguire | 4 | 4 | 16 | Clear engagement plan to be agreed in advance. JM to act as Community Liason between H17 & Blast Theory to work with local groups. | 3 | 3 | 9 | Open
13 | Audience demand exceeds capacity for the taxi interative journey | Frustrated audiences and reputational damage. | Sarah Moore TBD | 5 | 5 | 25 | Correct management of communications for interactive element. Clear BO messaging | 5 | 4 | 20 | Open
14 | Blast Theory's failure to deliver site management of film locations or secure desired locations | Relationships sour with local residents, local councillors and audiences. | Tech & Ops Lead? | 4 | 4 | 16 | Blast Theory to work with experienced Production Manager to source and secure locations. H17 to provide a Tech & Ops contact to link up with local residents & councillors. | 4 | 4 | 16 | Open
15 | Project documentation not managed centrally | Files out of sync, using different versions, no single source | Hannah Williams Walton | 4 | 4 | 16 | Blast Theory to have a centralised Dropbox folder with controlled access. HWW to keep H17 filing up to date. | 2 | 3 | 6 | Open
15 | [5 empty] | 0 |  |  |  | 0
16 | [5 empty] | 0 |  |  |  | 0
17 | [5 empty] | 0 |  |  |  | 0
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...

## Key
Key for Risk Register
Organisations
Slung Low | Slung Low | Producing organisation
H17 | Hull UK City of Culture 2017 | Commissioning organisation
People |  | Role
MG | Martin Green | CEO & Director, Hull 2017
LA | Lindsey Alvis | Producer, Hull 2017
MA | Martin Atkinson | Assistant Producer, Hull 2017
DW | David Watson | Head of Digital, Hull 2017
GH | Gareth Hughes | Head of Production, Hull 2017
PB | Phil Batty | Director of Marketing, Hull 2017
BM | Ben McKnight | Director of Communications, Hull 2017
AL | Alan Lane | Artistic Director, Slung Low
JR | Joanna Resnick | Producer, Slung Low
Creative Partners
BBC | BBC Arts | Part 3 - Live Broadcast
Space | Space | Part 1 - short film & digital activity
Other
Corner Shop PR |  | Freelance PR consultancy