## Sheet1
PROJECT NAME | BALLAD OF BIG LIL BY MAXINE PEAKE
DATE | 16.12.16 | updated HD
Rehearsal Schedule |  |  |  |  | Times | Technical in Guildhall | Notes
W/C | Note | Space | Activity | #
2017-07-03 |  | Rehearsal Space 2 | Recruit Community Cast - Hull |  | TBC - to include evenings |  | exact week to be determined by creative team availability
2017-07-10 |  | Reh Sp 2 | Recruit Community Cast - Hull |  | TBC - to include evenings
2017-07-17
2017-07-24
2017-07-31 |  | Reh Sp 2 | Community Cast rehearsals Intensive Weekend 1 | 2 | Saturday 10am - 4pm Sunday 10am - 1pm |  | rehearsal space for comm cast to explore - Hull College; Trinity Academy; Holy Apostles; more options to explore
2017-08-07
2017-08-14
2017-08-21
2017-08-28
2017-09-04 |  | Reh Sp 2 | Community Cast rehearsals Intensive Weekend 2 | 2 | Saturday 10am - 4pm Sunday 10am - 1pm
2017-09-11
2017-09-18 |  | Reh Sp 2 | Community Cast rehearsals Intensive Weekend 3 | 2 | Saturday 10am - 4pm Sunday 10am - 1pm
2017-09-25 |  | Reh Sp 2 | Community Cast rehearsals Intensive Weekend 4 | 2 | Saturday 10am - 4pm Sunday 10am - 1pm
2017-10-02 | Rehearsal Week 1 | RET Swan St | Professional Cast rehearse in Manchester |  | 10am - 6pm |  | Composer / MD rehearse in Manchester (1-2 Days)
|  | Reh Sp 2 | Community Cast rehearsals (1 X EVENING/1 X SAT) | 2 | 1 x Weekday Eve - 6-9pm Saturday 10am - 1pm
2017-10-09 | Rehearsal Week 2 | RET Swan St | Professional Cast rehearse in Manchester |  | 10am - 6pm |  | Composer / MD rehearse in Manchester (2 Days)
|  | Reh Sp 2 | Community Cast rehearsals (2 X EVENING/1 X SAT) | 3 | 2 x Weekday Eve - 6-9pm Saturday 10am - 1pm
2017-10-16 | Rehearsal Week 3 | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm |  | Composer / MD rehearse in Hull (2 Days)
2017-10-17 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm
|  | Guildhall | Joined by Community Cast in the evening | 1 | 6 - 9 pm |  | NB First time for whole company to be together - professional & community cast
2017-10-18 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm
2017-10-19 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm |  | Full Council Meeting 9am - 4pm Chamber
|  | Guildhall / Reh Sp 2 | Joined by Community Cast in the evening | 1 | 6 - 9 pm
2017-10-20 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm
2017-10-21 |  | Guildhall / Reh Sp 2 | Professional Cast rehearse in Hull |  | 10am - 5pm
|  | Guildhall / Reh Sp 2 | Joined by Community Cast all day | 1 | 10am - 5pm
2017-10-22 |  |  | FREE |  | No Call
2017-10-23 | Rehearsal Week 4 | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Fit Up starts | Composer / MD rehearse in Hull (1 day- plus see Thurs/Fri)
2017-10-24 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Install
|  | Guildhall / Reh Sp 2 | Joined by Community Cast in the evening | 1 | 6 - 9 pm
2017-10-25 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Install
2017-10-26 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Install
|  | TBC | Full Band Call - TBC
|  | Guildhall / Reh Sp 2 | Joined by Community Cast in the evening | 1 | 6 - 9 pm
2017-10-27 |  | Guildhall | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Install
|  | Guildhall & Reh Sp 2 | Full Band Call - Hull |  | 2 - 9pm |  | Noise & timings to be confirmed with Guildhall; Guildhall business in process to 4pm
|  | Guildhall & Reh Sp 2 | Joined by Community Cast in the evening | 1 | 6 - 9 pm
2017-10-28 |  | Guildhall & Reh Sp 2 | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Install | No Weddings - Guildhall to keep clear of bookings
|  | Guildhall & Reh Sp 2 | Joined by Community Cast all day | 1 | 10am - 5pm; 6 - 9pm
2017-10-29 |  |  | FREE |  |  | Technical Work TBC | Would require special opening arrangements with Guildhall
2017-10-30 | Tech Week | Reh Sp 2 | Professional Cast rehearse in Hull |  | 10am - 5pm; 6 - 9pm | Technical Work | Composer/MD rehearse in Hull (full week)
|  | Reh Sp 2 | Joined by Community Cast | 1 | 5 - 9pm
2017-10-31 |  | Reh Sp 2 - AM Guildhall - PM | Technical Rehearsals: Professional Cast |  | 10am - 5pm; 6 - 9pm | Tech Sessions | call times for community cast TBC - as many will be working during day
|  | Guildhall | Joined by Community Cast | 1 | 5 - 9pm
2017-11-01 |  | Guildhall | Technical Rehearsals: Professional Cast |  | 10am - 5pm; 6 - 9pm | Tech Sessions
|  | Guildhall | Joined by Community Cast | 1 | 5 - 9pm
2017-11-02 |  | Guildhall | Technical Rehearsals: Professional Cast |  | 10am - 5pm; 6 - 9pm | Tech Sessions
|  | Guildhall | Joined by Community Cast | 1 | 5 - 9pm
|  | Guildhall | Full Band Call |  | 10am - 5pm; 6 - 9pm |  | Noise & timings to be confirmed with Guildhall; Guildhall business in process to 4pm
2017-11-03 |  | Guildhall | Dress Rehearsal - Full Company Call (Cast, Band, Community) |  | 1 - 5pm | Tech Session AM | Noise & timings to be confirmed with Guildhall; Guildhall business in process to 4pm No Weddings - Guildhall to keep clear of bookings
|  | Guildhall | Performance PREVIEW | 1 | 7.30 or 8pm
2017-11-04 |  | Reh Sp 2 | Full Company Call |  | 1 - 3.30pm | Technical Work | Weddings in C1 only; 1 - 3.30pm. No other bookings to be taken.
|  | Guildhall | Full Company Call |  | 3.30 - 5pm
|  | Guildhall | Performance PREVIEW | 1 | 7.30 or 8pm
2017-11-05 |  |  | FREE | 2
2017-11-06 | Performance Week 1 | Guildhall | Tech Work; |  |  | Technical Work
No call Professional cast, community cast, band.
2017-11-07 |  | Guildhall | Technical Rehearsals: Professional cast and community cast |  | 2 - 5; 6 - 9pm |  | No Weddings - Guildhall to keep clear of bookings
2017-11-08 |  | Guildhall | Technical Rehearsals: Professional cast and community cast |  | 2 - 5pm |  | No Weddings - Guildhall to keep clear of bookings
|  |  | Performance | 1 | 7.30 or 8pm
2017-11-09 |  | Guildhall | Performance PRESS | 1 | 7.30 or 8pm |  | No Weddings - Guildhall to keep clear of bookings
2017-11-10 |  | Guildhall | Performance | 1 | 4pm |  | Show Call approx 2-3 hours before curtain up
|  | Guildhall | Performance | 1 | 8pm |  | No Weddings - Guildhall to keep clear of bookings
2017-11-11 |  | Guildhall | Performance | 1 | 2 or 4pm |  | No Weddings - Guildhall to keep clear of bookings
|  | Guildhall | Performance | 1 | 7.30 or 8pm
2017-11-12 |  |  | FREE | 6
2017-11-13 | Performance Week 2 |  | No Call
2017-11-14 |  |  | No Call
2017-11-15 |  | Guildhall | Performance | 1 | 7.30 or 8pm
2017-11-16 |  | Guildhall | Performance | 1 | 2pm |  | No Weddings - Guildhall to keep clear of bookings
|  | Guildhall | Performance | 1 | 7.30 or 8pm
2017-11-17 |  | Guildhall | Performance | 1 | 4pm |  | No Weddings - Guildhall to keep clear of bookings
|  | Guildhall | Performance | 1 | 8pm
2017-11-18 |  | Guildhall | Performance | 1 | 2 or 4pm |  | No Weddings - Guildhall to keep clear of bookings
|  | Guildhall | Performance FINAL | 1 | 7.30 or 8pm
2017-11-19 |  |  | GET OUT | 7
2017-11-20 |  |  | GET OUT CONT
2017-11-21
2017-11-22
2017-11-23
2017-11-24
|  |  | Community Rehearsal Days / Sessions | 13
|  |  | Professional and Community Rehearsal Days / Sessions | 11
|  |  | Performances in total | 15
Composer / Music