**Production Schedule**

**Into the Light**

**Tuesday 24th July 6pm- 8pm Full Cast Rehearsal in QVS**

**Wednesday 25th July 6pm- 8pm Full Cast Rehearsal in QVS**

|  |  |  |  |
| --- | --- | --- | --- |
|  | |  |  |
| **Friday 28th July** | |  | **Notes** |
|  | |  |
| **Time** | |  |  |
| 1pm |  | Move costumes to The Duckie Shop |  |
|  | | Kirsty/Hannah |  |
|  | |  |  |
|  | | Clear Horncastle spaces |  |
|  | |  |  |
| 5pm | | Meet Dresser/ Volunteers |  |
|  | |  |  |
| 5:00pm – 5:45pm | | Meet Full Cast at The Duckie Shop |  |
|  | | Change into costumes |  |
| 6:00pm – 8:00pm | | Dress Rehearsal |  |
|  | | Band Sound check |  |
|  | |  |  |

|  |  |  |
| --- | --- | --- |
| **Saturday 29th July** |  |  |
| 9:30am | All Cast to meet at The Duckie Shop |  |
|  | Rehearsal in the Square |  |
| 11:00am | Back Chat Brass Band arrive | Based ?? |
|  | Marshal Volunteers arrive (25)  Into the Light Production Meeting  (Including YD staff) Not cast/dancers | Sarah to meet and greet |
| 11:45am | Full run of the show with Brass Band  Marshals |  |
| 12:15pm | Lunch – clear the square  Volunteer lunches provided by Hull 2017 (Marshals/dressers) |  |
|  | Best of Fiends – Band set up |  |
| 1:00pm | Costumes/ Makeup/Hair | Duckie Shop |
| 2:00pm | Half hour call for cast and both bands |  |
| 2:20pm | Parade from Duckie Shop to QVS  Lead by Brass Band  Cue Best of Fiends  Amy Lame – Introduce the work | Full Cast |
| 2:30pm | Arrive in QVS  Perform “Into the Light” |  |
| 3:00pm | Walk back to The Duckie Shop  Route: Along Ferrens Way |  |
| 3:00pm – 3:30pm | De brief on the performance |  |
| 3:30pm – 4:30pm | Break |  |
| 5:00pm | Final half hour call for the performance |  |
| 5:30pm | Parade from Duckie Shop to QVS  Lead by Brass Band  Cue Best of Fiends  Amy Lame – Introduce the work |  |
| 5:40pm | Arrive in QVS  Perform “Into the Light” |  |
| 6:10pm | Finish “Into the Light”  Finale moment!!!! |  |
|  |  |  |

**Marshal plan:**

1. Parade –(there and back) 5 at the back/ 5 at the front at the sides/ 5 in the middle/ 10 waiting at QVS
2. Marshals to be assigned to one member of YD staff who will direct them to what they need to do throughout the day.

**Yorkshire Dance Staff**

Manage 10 people and 6 Marshalls each

Depending on what work happens around the podiums

Kirsty Redhead

Antony Dunn

April Skipp

Sarah Shooter

**One to One support on the day (to review)**

* Henry
* Alix
* Liam (Under 18)
* Andie/Frank (Under 18) ????