## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | HANA | 3 | 5 | 15 | Keep the spendings within the budget | 2 | 5 | 10 | Open
2 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | HANA/Hymers/Rooted | 3 | 5 | 15 | Insurance requirements for Hymers still to be finalised, HANA and Rooted already have public liability, traders will have cover (min 1 mil) and community groups will not be allowed to participate without cover which many already have | 2 | 4 | 8 | Open
3 | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | HANA | 4 | 4 | 16 | Detailed project plan developed all aware that no additional budget is available for extra activities, outside those in budget | 2 | 4 | 8 | Open
4 | Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | HANA | 3 | 4 | 12 | Updated performers contract to provide guidelines and requirements for each group participating in the Multicultural Festival (MCF) | 2 | 2 | 4 | Closed
5 | insufficient promotion for the event | Audience levels lower than expected causes friction with traders and or community groups who can't sell their goods | Hymers | 3 | 5 | 15 | Promotion of the event through all means available facebook, twitter, Hull city of culture 2017 team, flyers/posters and word of mouth. | 2 | 3 | 6 | Open
6 | Weather or natural environment | Inability to deliver project as intended | HANA/Hymers/Rooted | 2 | 4 | 8 | Weatherproofing, indoor alternatives, Main Hall reserved (fashion show), all other functions apart from football to be held indoors, Food stalls to have gazebos | 2 | 2 | 4 | Open
7 | Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | HANA | 2 | 5 | 10 | Making more experienced staff available for support, training if required, staff meetings | 2 | 3 | 6 | Open
8 | Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | HANA | 2 | 4 | 8 | reliable access to all documentation (Dropbox MCF folder) to avoid a single point of failure, advance planning for capacity & planned leave | 1 | 1 | 1 | Open
9 | Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | HANA | 3 | 5 | 15 | Use of single Dropbox folder administerd by HANA for all teams (Dropbox MCF folder) | 1 | 1 | 1 | Closed
10 | Partners fail to support/deliver as expected | Additional pressure on internal project team | HANA | 3 | 4 | 12 | Clear roles & responsibilities, contracts where required, regular updates | 2 | 2 | 4 | Open
11 | Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | HANA | 3 | 5 | 15 | Roles & responsibilities defined, regular use of project managment tools, regular project team updates and/or meetings | 1 | 3 | 3 | Open
12 | Insufficient budget | Inability to deliver project | HANA | 4 | 5 | 20 | accurate forecasts, management of expectations | 3 | 5 | 15 | Open
13 | Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | HANA | 2 | 4 | 8 | Thorough planning, Constant update of the project plan with input from all teams | 1 | 2 | 2 | Open
14 | Failure to secure necessary permissions or licences | Inability to delivery project | HANA | 3 | 5 | 15 | Early involvement of Tech & Ops team, appropriate slot at ESAG | 2 | 4 | 8 | Open
15 | Failure to secure appropriate venue | Inability to deliver project | HANA/Hymers | 1 | 5 | 5 | early discussions, backup plans | 1 | 1 | 1 | Closed
16 | Failure to engage creative team | Inability to deliver project | HANA/Hymers/Rooted | 3 | 5 | 15 | Keep in contact, answer emails, attend meetings and workshops provided by the creative team. | 3 | 5 | 15 | Open
17 | Failure to contract all parties effectively | Inability to deliver project | HANA | 4 | 5 | 20 | Use of standard templates, inform all groups from the interest phase that they must be contracted to be a part of the project | 3 | 3 | 9 | Open
18 | Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | HANA | 2 | 5 | 10 | Coordination with Hymers/rooted on all aspect of the project | 2 | 2 | 4 | Open
19 | Decision making causes delays | Additional pressure on internal project team | HANA | 2 | 5 | 10 | Foreseeing required decisions (greenlight, on sale etc) and scheduling them in | 1 | 3 | 3 | Open
20 | Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | HANA | 3 | 5 | 15 | Well planned, all parties know the budget and stay within in it | 2 | 3 | 6 | Open
21 | Gold Plating inflates scope | Project team add their own featuers that aren't required or change requests | HANA | 3 | 4 | 12 | Prevent scope drift by setting strict guidelines/event descriptions for each event. Sufficient mangement. | 1 | 4 | 4 | Open
22 | Dependencies are inaccurate | Dependencies impact the project beyond intial prediction | HANA | 4 | 5 | 20 | Set clear cut of points for those not meeting requirements, Provide clear guidlines and full detail of all requirements to all parties. Secure all neccesary equipment in advance. | 2 | 5 | 10 | Open
23 | Change managment overload | Large numbers of changes increase complexity of the project and disract key resources | HANA | 3 | 3 | 9 | Project plan to be followed, each event discription details all planned areas of activity within each event, where change is required clear guidlines set up to implement it. Delegation of each task | 1 | 2 | 2 | Open
24 | Resource shortfall | Inability to secure sufficient resources for the project | HANA | 3 | 5 | 15 | Evaluate the required amount of payed resources and traget community groups for volunteers as well as using HCOC volunteers. | 2 | 3 | 6 | Open
25 | Resource performance issues | Resources perform below expected levels | HANA | 2 | 5 | 10 | Mange expectations, make sure resrouces are properly assigned to tasks | 2 | 4 | 8 | Open
26 | Low team motivation | Lack of motiviation, Particular risk for long running projects | HANA | 4 | 5 | 20 | Strong leadership, break up of large task into small manageble task with an end goal in sight, Promote postivity within the work group. Empover the team members | 3 | 4 | 12 | Open
27 | Decisions are incomplete | Issue resolitions that don't adress the issue or create more issues | HANA | 3 | 5 | 15 | Decisions based on solid data, decision made by those with experience/knowledge and with forethought, clear communication between partners | 2 | 3 | 6 | Open
28 | Legal or regulatory changes impact project | Compliance senstive areas limit project | HANA | 4 | 5 | 20 | Strict deadlines for project completion leaving time for adjustments if needed, clear communication of requirements for all participants and deadline information | 2 | 5 | 10 | Open
29 | Project negativly affects reputation | Project gereates negative publicity and/or damages relationships | HANA | 3 | 5 | 15 | Silence is ok, if situation calls for it hire PR/ask for help from PR office, listen to complaints and act rationally if ever replying to the anyone, communication | 3 | 4 | 12 | Open
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...