## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | Matilda | 2 | 5 | 10 | Suppliers made aware of 30-day payment terms and all been set up on system already. POs raised and awaiting approval. Project budget includes detailed projected cashflow and Finance team are aware. | 2 | 3 | 6 | Open
2 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | Matilda and Sarah | 3 | 5 | 15 | Not yet determined insurance requirements - on agenda for meeting in April. | 3 | 5 | 15 | Open
3 | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | Jeff | 4 | 4 | 16 | Scope of project signed off at SLT at greenlight. Detailed project brief attached to commissioning & production agreement. All aware that no additional budget is available for extra activity. | 2 | 4 | 8 | Open
4 | Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | Matilda | 2 | 5 | 10 | well managed creative process, management of expectations. Flexible rehearsal process allowing extra time to be added when needed. Project updated via social media to showcase the progress of the project |  |  | 0 | Open
5 | Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | Matilda and Sarah | 4 | 4 | 16 | Thorough planning, reliable quotes. Obtaining contingency funds from corporate sponsors. |  |  | 0 | Open
6 | Decision making causes delays | Additional pressure on internal project team. Delays in production deadlines. | Sarah | 3 | 3 | 9 | foreseeing required decisions (greenlight, on sale etc) and scheduling them in. Setting realistic deadlines. |  |  | 0 | Open
7 | Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 | Matilda and Sarah | 3 | 5 | 15 | Ensuring the marketing comms plan is stuck to; and planning of performance times are complementary to other 2017 productions that are active on these dates. |  |  | 0 | Open
8 | Failure to secure necessary permissions or licences | Inability to delivery project | Matilda and Sarah | 2 | 5 | 10 | ensuring all work is orginal and inceeping within copywright laws. Planning for any other permits that may be required i.e noise permits |  |  | 0 | Open
9 | Insufficient budget | Inability to delivery project as planned | Sarah and Matilda | 3 | 5 | 15 | Ensuring contingencies are put into place |  |  | 0 | Open
10 | Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | Matilda and Sarah | 2 | 5 | 10 | roles & responsibilities defined. Regular use of Artifax inc milestones, regular project team updates and/or meetings. Maintain comunication of what has been done and what needs to be done. |  |  | 0 | Open
11 | Partners fail to support/deliver as expected | Additional pressure on internal project team | Matilda and Sarah | 3 | 5 | 15 | structured contingency plans in place incase we are let down by partners. Put in place written agreements with clear outlines of what is exspected from both parties |  |  | 0 | Open
12 | Procurement process causes delays | delays to prodcution and instialtion of set | Sarah | 4 | 3 | 12 | Deadlines for deliveries arranged with time to spare. Maintaining communication with suppliers to ensure deliveries will be on time. |  |  | 0 | Open
13 | Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | Matilda | 4 | 3 | 12 | Upload all docments onto project management site to have shared acesses between Matilda and Sarah. |  |  | 0
14 | [5 empty] | 0 |  |  |  | 0
15 | [5 empty] | 0 |  |  |  | 0
16 | [5 empty] | 0 |  |  |  | 0
17 | [5 empty] | 0 |  |  |  | 0
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...