## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
[5 empty] | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Project | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | HERCHA | Insufficient budget for both events but desire to carry on. Risk of not happening safely or at scale. | Reputational impace and potential impact on scale of second event - the Mel | Cheryl | 2 | 4 | 8 | CD to email Digital & Media to advise low profile | 2 | 4 | 8 | Open
2 | Song for Hull | Project lead long term sick | Project delivery | Cheryl | 3 | 4 | 12 | New project lead appointed, Cheryl to keep in contact | 1 | 4 | 4 | Closed
3 | Acorn Festival | Management of potentially large scale event | Unable to control large audiences and impact (noise, litter etc) | Cheryl | 2 | 5 | 10 | Cheryl to maintain contact and liaise with Events Team | 2 | 5 | 10 | Open
4 | Albemarle Saturdays | Marketing - project are struggling with this | Impact on size of audience | Mel | 4 | 3 | 12 | Melissa to support and advise | 4 | 3 | 12 | Closed
5 | Art in the Park | Worry about the scale and lack of information on this project | Reputational risk. One of few projects happening in this area | Cheryl | 2 | 3 | 6 | Cheryl met with project team, part of whole weekend of activity with Ganton. More information now available. | 2 | 2 | 4 | Open
6 | Boulevard | Now in Hull but lack of communication/clarity | Delayed project and lack of engagement with community | Cheryl | 4 | 4 | 16 | Arrange another catch up with project after Easter break to check progress | 3 | 4 | 12 | Open
7 | Bransholme 50 | No communication and marketing of events. Lack of planning and no confirmed programme. | Repuational damange. Lack of opportunity and involvement for community | Cheryl | 5 | 4 | 20 | Continual efforts to meet and communicate with project. Project cancelled meeting last week (7/4/17) | 4 | 4 | 16 | Open
8 | Bantu | Funds now received from BL but under investigation | project lead distancing themselves, poor community engagement and delivery | Cheryl | 4 | 4 | 16 | BL & us to meet with Cathrine after Easter break. Cheryl to continute to support and monitor | 4 | 4 | 16 | Open
9 | 5 senses | Poor marketing but now appear to have their own target audience after first event | Not drawing in new audiences and 'going it alone' | Mel/Cheryl | 3 | 3 | 9 | CO/MP to continue to support and promote use of Hull 2017 Volunteers for next events | 2 | 2 | 4 | Open
10 | Fuzzfeed | Our digital coverage isn't supporting them | Lack of views for the project | Claire | 3 | 4 | 12 | Meeting arranged with Education/Digital and wider CCP Team after Easter break to discuss | 2 | 3 | 6 | Open
11 | Refugee week | Lack of planning and communication | Reputational damage, unsafe event etc | Cheryl | 4 | 5 | 20 | Cheryl to attend next committee meeting and report back. Ensure they are talking to ESAG. Nothing back from HPSS | 4 | 5 | 20 | Open
12 | Freetown | Lack of communication and unknown group . | Reputational damage, quality and safety of event and level of community engagement | Cheryl | 3 | 4 | 12 | project now more responsive but lack of community engagement. Set up on HBO as free event. | 3 | 3 | 9 | Open
13 | Handmade | Building and traffic problems - council communication | Reduction in scale of event and delay in timeline | Claire | 3 | 4 | 12 | Alternative venue has been agreed and HCC highways team are now communicating |  |  | 0 | Closed
14 | Mad Pride | BL Funds now received but appear to be doing their own thing/closed workshops, unaccessible venues | No new audiences or opportunities for people to get involved. Doing too much and unclear what we are funding | Cheryl | 4 | 5 | 20 | Cheryl continuing to support and pressing for information/clarity of workshops. | 4 | 4 | 16 | Open
15 | Hansel and Gretel | Lack of producer capacity because of internal structure change. Poor community engagement | Low audiences/no shows. Project team very small, events unmanageable and unplanned | Cheryl | 3 | 3 | 9 | Cheryl meeting and keeping supporting, their venue has been confirmed which was the biggest risk | 2 | 2 | 4 | Open
16 | Reading Rooms | Need clarity of workshops and how public can get involved | project happening with established groups and not accessible to 'public' | Cheryl | 4 | 5 | 20 | Cheryl to continue to support and press for itinerary | 4 | 4 | 16 | Open
17 | Noah | Risk of scale not being as big as planned | low profile of project and community involvement |  | 3 | 2 | 6 | Cheryl to continue to support | 2 | 2 | 4 | Open
18 | Trevor Keys | Lack of confirmed plan - changes to project that can't be delivered | Reputational imapct, risk of project being cancelled | Cheryl/Henri | 3 | 5 | 15 | Introductions have been made but still lack of clarity and timescales for delivery | 3 | 5 | 15 | Open
19 | [6 empty] | 0 |  |  |  | 0
20 | [6 empty] | 0 |  |  |  | 0
21 | [6 empty] | 0 |  |  |  | 0
22 | [6 empty] | 0 |  |  |  | 0
23 | [6 empty] | 0 |  |  |  | 0
24 | [6 empty] | 0 |  |  |  | 0
25 | [6 empty] | 0 |  |  |  | 0
26 | [6 empty] | 0 |  |  |  | 0
27 | [6 empty] | 0 |  |  |  | 0
28 | [6 empty] | 0 |  |  |  | 0
29 | [6 empty] | 0 |  |  |  | 0
30 | [6 empty] | 0 |  |  |  | 0
31 | [6 empty] | 0 |  |  |  | 0
32 | [6 empty] | 0 |  |  |  | 0
33 | [6 empty] | 0 |  |  |  | 0
34 | [6 empty] | 0 |  |  |  | 0
35 | [6 empty] | 0 |  |  |  | 0
36 | [6 empty] | 0 |  |  |  | 0
37 | [6 empty] | 0 |  |  |  | 0
38 | [6 empty] | 0 |  |  |  | 0
39 | [6 empty] | 0 |  |  |  | 0
40 | [6 empty] | 0 |  |  |  | 0
41 | [6 empty] | 0 |  |  |  | 0
42 | [6 empty] | 0 |  |  |  | 0
43 | [6 empty] | 0 |  |  |  | 0
44 | [6 empty] | 0 |  |  |  | 0
45 | [6 empty] | 0 |  |  |  | 0
46 | [6 empty] | 0 |  |  |  | 0
47 | [6 empty] | 0 |  |  |  | 0
48 | [6 empty] | 0 |  |  |  | 0
49 | [6 empty] | 0 |  |  |  | 0
50 | [6 empty] | 0 |  |  |  | 0
Note on C2: Crawford James: What might happen?
Note on D2: Crawford James: What would be the result of that happening?
Note on E2: Crawford James: Who is responsible for managing this risk?
Note on F2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on G2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on I2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on J2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on K2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on M2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...