|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Anna Coromina |
| **Name of Project** | Boulevard Mad Yard Art |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** |  |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| 1st February 2016 | 1st May of 2016 | General Design of the project |  |  |
| 1st May 2016 | 1st July of 2017 | Research funding |  |  |
| 1st January 2017 | 1st June of 2017 | Designing the Calendar of activities: programming workshops and specific activities |  |  |
| 1st April 2017 | 1st June of 2017 | Website construction, Marketing and developing audience |  |  |
| 1st June of 2017 | 20th June of 2017 | Closure of the Budget |  |  |
| 1st July of 2017 | 30th September of 2015 | BMYA activities, 5 days a week (3 workers full time) |  |  |
| 21st September of 2017 | 24th September of 2017 | Festival Boulevard Mad Yard Art |  |  |
| 25th September of 2017 | 30th September of 2017 | Ending Evaluation, Economical Closure, post-production |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances