- Appendix 23: Venue Partner Consultation

  - Introduction

Venue Partners for Look Up were those organisations who managed the various public buildings, structures or spaces utilised within the project either directly or in support of the project.

In order to gain feedback from Venue Partners, consultation was undertaken once the Look Up artwork to which they were connected had completed. In total, five responses were received from key individuals at:

- The Deep (Washed Up Car-Go; Bleached; and Floe)

- Environment Agency (City Speaks)

- Princes Quay (Elephant in the Room)

- Hull Paragon Interchange (The Train Track and The Basket)

- Hull Minster (A Hall for Hull).

The data collection methodology employed was a quantitative and qualitative questionnaire. Venue Partners were emailed a link to an online survey. The template for the interview is provided in Appendix 23.

The focus of this research was to undertake two types of evaluation:

- Process Evaluation: motivations; key learnings, successes and challenges of project development and delivery; and the effectiveness of the partnership with Hull 2017 and the broader team.

- Outcomes Evaluation: personal and organisational development, including skills and knowledge gained; collaboration and partnership development; interest in being involved with the hosting or commissioning of public art in future; and confidence levels in being part of similar projects in future.

  - Process Evaluation

In order to inform the planning, development and delivery of future projects, a series of questions were asked linked to the process of Look Up. These concentrated primarily on:

- Motivations: What attracts venue partners to get involved in projects such as Look Up?

- Project Development and Delivery: What were the most exciting and challenging parts of being involved in the Look Up projects, and what key learning’s do they take from the process?

- Partner Performance: How did they feel the Hull 2017 team (internal and external consultants contracted the project), and the commissioned artists performed as a partner throughout the course of their involvement and how could this be improved?

    - What Was It About Look Up?

Hull’s ‘UK City of Culture’ status appears to have been a significant factor for the majority of partners in their decision to work on Look Up:

- Four out of five partners said it ‘completely’ influenced their decision

- One out of five partners said it had been a significant influence, giving a score of 7 out of 10.

This led to an average score of 9.4 out of 10 in regard to the influence of UK City of Culture status as a motivation to be involved.

Partners were also asked to share their key motivations for working on the project, with the opportunity to provide up to three. Key motivations that were common across delivery partners were:

- To be a part of the City of Culture year (three of five);

- The appeal of the artwork (three of five);

- To increase the profile of their venue (three of five);

- To demonstrate commitment to Hull and its community (two of five);

- To attract footfall to their venue (two of five);

- To take part in a collaborative experience (one of five); and

- The proposed location for the artwork (one of five).

‘Continuing our support to Hull and the community.’ 
(Venue Partner)

‘We wanted to be part of the story and success.’ 
(Venue Partner)

‘We wanted to draw more attention to our structure.’
(Venue Partner)

‘Beauty and aesthetic interest.’ 
(Venue Partner)

‘Keen to collaborate.’ 
(Venue Partner)

    - Project Development and Delivery

Delivery partners were asked about the most exciting and challenging aspects of being part of Look Up, as well as their key learning’s for taking forward to future projects.

Challenges

The most frequently cited challenges were those linked to the logistics of the install (two of five partners). Other challenges mentioned included the artwork not measuring up to expectations due to technical issues; the difficulties of marketing a long running installation; and the logistical aspects of the installation.

‘The project being totally underwhelming once installed due to lighting issues.’
(Venue Partner)

‘Following the installation having continued regular support advertising the project.’
(Venue Partner)

‘Health and safety logistics for art installation.’
(Venue Partner)

‘Installation at a busy [venue].’ 
(Venue Partner)

Excitement

The excitement of being involved in Look Up was primarily the impact of the artwork itself, and the subsequent positive reaction of the public to it. Also mentioned was simply being a part of the story of Hull 2017.

‘Seeing our building being used as a canvas and seeing the thousands of people walking around town engaging with different things.’
(Venue Partner)

‘Being part of the whole success of Hull 2017. It has been a fantastic year.’
(Venue Partner)

‘Unveiling the artwork and positive reaction from public and staff.’
(Venue Partner)

‘The wow factor.’
(Venue Partner)

Key Learnings

Learnings from each venue partner differed, with the exception of aspects linked to communication (whether between team members on the project or with the public). Learnings unique to partners included how the scale and positioning of the artwork has an impact on its success; and a need to identify how the full vision of an artwork can be realised in future.

‘Making sure that a legal agreement and communications protocol were in place at the start.’
(Venue Partner)

‘Be more clear about operating times and restrictions as sound and motion did affect our activity - some visitors were unhappy.’
(Venue Partner)

‘Large scale art works do better, smaller scale and artworks in [part of our venue] are lost and slightly out of the way.’
(Venue Partner)

‘Ensuring full deliverance of project is carried out.’
(Venue Partner)

    - Partner Performance

Project Management

Venue partners viewed the project management of Look Up positively, with an average score of 4.4 out of 5:

- Three of five gave a full score of 5 out of 5;

- One of five gave a score of 4 out of 5; and

- One of five gave a score of 3 out of 5.

When rating aspects of Look Up’s project management, partners praised all aspects (see Figure 1):

- Look Up explained the Look Up project well (concept, aims and objectives) – two stated strongly agree, two agree and one neither disagree nor agree.

- Look Up clearly outlined the potential benefits of our involvement as a host venue – one stated strongly agree, three agree and one neither disagree nor agree.

- Look Up provided a clear project plan (i.e. project schedule and resources required) – one stated strongly agree, three agree and one neither disagree nor agree.

- Look Up clearly outlined organisational roles and responsibilities – one stated strongly agree and four agree.

- Look Up communicated well throughout the project – three stated strongly agree, one agree and one neither disagree nor agree.

Figure 1: Project Management of Look Up

In terms of how project management could have been improved there was limited response. One partner felt being solely a host for an artwork did not stimulate the same level of involvement with the artwork, as it did when being involved in the commissioning process. The need to consider the ongoing promotion of artworks installed for a long period of time, to keep interest and awareness levels up, was also cited.

‘We only really had full involvement with [one artwork] which was our favourite…Not being involved in the process of commissioning [the others] felt that they were more removed in terms of our connection with them.’
(Venue Partner)

‘Offered assistance on promoting the project on a regular basis.’
(Venue Partner)

Project Delivery

Venue partners were asked to provide their opinion of a number of project delivery elements. Again, the scores provided were high, indicating that overall satisfaction levels were high (see Figure 2). In response to the question ‘How far do you agree or disagree with the following statements in relation to the artwork you hosted for Look Up?’:

- The installation of the artwork was done to a high standard - four stated strongly agree and one agree.

- The interpretation (information boards, printed materials, etc.) linked to the artwork were of a high standard – four stated strongly agree and one neither disagree nor agree.

- The technical and operations crew were professional and supportive - five stated strongly agree.

Overall Partnership Performance

Venue partners, on the whole, were favourable towards the nature of the partnership between themselves, Hull 2017 and the commissioned artists (see Figure 3).

- Three strongly agreed and two agreed their ‘partnership with Hull 2017 was positive’.

- Three strongly agreed, one agreed and one neither disagreed nor agreed their ‘partnership with Hull 2017 was effective’.

- Three strongly agreed and two agreed their ‘partnership with the commissioned artist for the Look Up project hosted was positive’.

- Three strongly agreed, one agreed and one neither disagreed nor agreed their ‘partnership with the commissioned artist for the Look Up project hosted was effective.

Figure 2: Project Delivery of Look Up

Figure 3: Effectiveness of Project Partnerships

  - Outcomes

The key areas of focus in terms of the outcomes that Look Up had on delivery partners, included:

- Personal and organisational development: impact of involvement on the organisation and its staff, on the profile of the venue, and audience development.

- Skills and knowledge development: new and existing skills, knowledge and learning gained and developed, as a result of working on Look Up.

- Collaboration and partnerships: new and existing collaborations and partnerships built or developed as a result of working on Look Up.

- Future intentions towards public art projects: interest and likelihood of the organisation being involved in further public art projects; and their confidence in doing so.

    - Personal and Organisational Development

Venue partners all agreed that through being involved in Look Up they and / or their organisation had enjoyed the experience. More varied were the levels of agreement with how the project had impacted on their organisations’ profile and audience development (see Figure 4):

- Five partners agreed (three strongly agreed and two agreed) that ‘I / my organisation enjoyed working on the Look Up project’.

- Three partners agreed (one strongly agreed and two agreed) that ‘Our organisation’s profile has agreed’.

- Two partners agreed (one strongly agreed and one agreed) that ‘Our organisation successfully attracted larger audiences to our venue than we normally would have at this time of year’;

- Two partners agreed (one strongly agreed and one agreed) that ‘Our organisation successfully attracted new audiences to our venue’.

    - Skills and Knowledge Development

It appears that hosting an artwork did not have any real impact on the skills and knowledge development of venue partners, which may link to their not having a direct role in the delivery side of the project. Only one partner cited an area where their knowledge had increased to some extent.

‘Links to emancipation from the Hull perspective and the historical influences the city has made to the world.’
(Venue Partner)

Figure 4: Personal and Organisational Development

Confidence

Three of five partners stated that they would be extremely confident in working on a similar project in future (10 out of 10), whilst two were somewhere in the middle (5 or 6 out of 10).

Figure 5: Confidence to Work on a Similar Project

For those whose confidence had increased significantly, reasons were that they were already in discussions to do so. Where confidence was lower it seemed to link to a belief that the funding required could be a significant barrier:

‘We are in negotiation to continue.’
(Venue Partner)

‘Not sure if the parent company will provide funding for this in the current economic climate’
(Venue Partner)

    - Collaboration and Partnerships

Three of five partners stated that working on Look Up had enabled them to build new relationships with other individuals and/or organisations that they had not come across before (see Figure 6).

Four of five partners stated that working on Look Up had enabled them to develop existing relationships with other individuals and/or organisations, i.e. a deepening of partnerships that pre-date Look Up (see Figure 6).

Partners had:

- Created new relationships with artists, local arts organisations, and suppliers: growing their networks within the cultural sector; and expanding other professional connections.

- Built additional trust and professional respect with those who they had previously worked, including local arts organisations and the local authority.

Figure 6: Partnership Development on Look Up

‘Looking to build relationship with Freedom Festival’
(Venue Partner)

‘We have been involved for many years with events such as the Freedom Festival. We also have a long established working relationship with Hull City Council.’
(Venue Partner)

‘Working with [a sign makers] who installed the artwork and with artists.’
(Venue Partner)

‘We have engaged with artists, curators who could contribute to our work in future.’
(Venue Partner)

In terms of the future of any partnerships gained or developed during the process of working on Look Up, three of five partners were looking to continue their involvement in arts related projects. This was through looking into possible joint funding bids; continuing to be open to approaches for public art installation; and the possibility of commissioning work.

‘Possible joint funding bids for arts/environment messaging.’
(Venue Partner)

‘[Our venue] to be available for future art projects.’
(Venue Partner)

‘Future arts and cultural projects, perhaps installations and new commissions.’
(Venue Partner)

    - Future Intentions Towards Public Art

All venue partners were very interested in being a host venue for future public art installations (see Figure 7); whilst the likelihood of commissioning public art was more varied across organisations (see Figure 8).

Figure 7: Future Intentions Towards Hosting Public Art

Figure 8: Future Intentions Towards Commissioning Public Art

When asked ‘On a scale of 0-10, where 0 is Not at all and 10 is Completely, how interested are you in being a host venue for public artwork(s) in future, as a result of your experience on Look up’:

- Three of five partners gave a score of 10;

- One partner gave a score of 9; and

- One partner gave a score of 8.

When asked ‘On a scale of 0-10, where 0 is Not at all and 10 is Completely, how likely would you be to commission public artwork(s) in future, as a result of your experience on Look up’:

- Three of five partners gave a score of 10;

- One partner gave a score of 7; and

- One partner gave a score of 5.

When asked to provide a reason for their scores, venue partner interest in hosting public artwork(s) in future differed by organisation. One partner was in discussions about the possibility; two would if the proposed projects(s) could meet their requirements; one feeling they had an ideal venue; and one because they enjoyed Look Up so much.

‘Absolutely, if we can make it work within our working requirements.’
(Venue Partner)

‘We are already in discussion with Hull 2017 to continue being a host venue for public artwork.’
(Venue Partner)

‘The project would need to deliver following project confirmation and be fully supported advertising wise.’
(Venue Partner)

‘Because we loved it!’
(Venue Partner)

In terms of commissioning public art, the slightly lower average score links to funding. Where venue partners were very likely to commission work, it was because they already had, or because they believed art has an important role to play in the city.

‘Funds may not allow.’
(Venue Partner)

‘Would require a partner.’
(Venue Partner)

‘We already do with galleries and artwork events.’
(Venue Partner)

‘Because we think art is important to the community.’
(Venue Partner)

In the case of Floe, The Deep were also considered a Delivery Partner. Where questions were the same within this survey and the Delivery Partner Survey, The Deep’s responses have been included in the Delivery Partner analysis (see Appendix 19).