|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Local Works Ltd/ Greatfield Residents Association -GRIN |
| **Name of Project** | Why Couldn’t They Be Like We Were |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
| September | Dec 2016 | Bring together community organisations to put together the project | COMPLETE / ON-TIME / BEHIND |  |
|  |  | Research, gathering of materials, interviews etc. |  |  |
|  |  |  |  |  |
| January 2017 | March 2017 | Bring information together along with display materials, music , maps, photographic evidence and videos etc. |  |  |
|  |  |  |  |  |
| April 2017 | April2017 | First event –the 1947 teenage |  |  |
|  |  |  |  |  |
| May 2017 | May 2017 | Seconf event the 1957 teenager |  |  |
|  |  |  |  |  |
| June 2017 |  | Third event The 1960’s teenage |  |  |
|  |  |  |  |  |
| June/July 2017 | July 2017 | The modern teenage –are we that different |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances