## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Conflicting priorities of the multiple Flood partners and commissioners. Partners fail to support/deliver as expected. Decision making causes delays to project delivery. | Ineffective working causes additional pressures on production team. Decision making causes delays to project delivery. Potential impact on wider project delivery - financial and human. | Alan Lane, Joanna Resnick & Lindsey Alvis | 3 | 3 | 9 | Regular communication with the various partners - team meetings, email updates, phone conversations. Clear priorities and goals set from the start of the start of the project. Key milestones, lines of communication to be clearly identified. | 2 | 3 | 6 | Open
2 | Scope creep: uncontrolled additions to the project. | Additional pressure on internal project team; core components of project put at risk. | Alan Lane & Joanna Resnick | 3 | 3 | 9 | Regular communication with the various partners - team meetings, email updates, phone conversations. Clearly defined project scope, clear process for managing change. | 2 | 3 | 6 | Open
3 | Reduced budgets from The Space and BBC Performance Live. | Additional pressure on internal project team. Inability to deliver project as intended. Impact on wider project resources - human and financial. | Alan Lane & Joanna Resnick | 5 | 3 | 15 | Management of partner expectations. Modification of plans to ensure project delivery. Budgets now confirmed with partners. Additional money raised for the project - Slung Low financial contribution. | 1 | 3 | 3 | Closed
4 | Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed. | Alan Lane & Joanna Resnick | 3 | 4 | 12 | Thorough planning, reliable quotes. Regular accounting and budget updates. | 1 | 4 | 4 | Open
5 | Suppliers fail to deliver | Delays to project. Inability to deliver project as intended | Alan Lane & Joanna Resnick | 3 | 3 | 9 | Clear delivery dates, terms to be agreed. Additional time to be factored in with key items, set as contingency. Working with Slung Low's established suppliers. References requested for all new suppliers. | 2 | 3 | 6 | Open
6 | Reduced availability of project team (due to capacity, illness etc) | Additional pressure on internal project team | Alan Lane & Joanna Resnick | 3 | 3 | 9 | Advance planning for capacity. Reliable documentation to allow others to pick up in someone's absence. Staff to practise good hygiene on site, chef to provide nutritious meals during production periods. Additional staff recruited in recent months to provide further capacity to event management. | 2 | 2 | 4 | Open
7 | Frustration / disappointment from those unable to secure tickets to a performance in April. | Negative responses from residents to cause additional pressures on production team. Increased potential for non-bookers turning up to a show without a ticket. | Alan Lane & Joanna Resnick | 3 | 3 | 9 | Performances to be restaged in October providng further opportuntites to see the show. Slung Low to provide other opportunities (free workshops, contribution to the July Fun Day) for people, particularly residents, to feel involved. Potential for October events to be live streamed / live shows may be extended. | 2 | 3 | 6 | Closed
8 | Non-bookers turning up to the performance without a ticket. | Site unable to cope with large crowds of people, insufficient FOH staff, toilets and parking provision. Impact on audience experience. | Alan Lane & Joanna Resnick | 3 | 3 | 9 | The ticketed event is sold out. 1 ticket = 1 pair of headphones only. Marketing to communicate that there will be no tickets/returns sold on site and no additional spaces available for walk ups on the night of the event. Passers-by will not be able to hear the show without using Slung Low’s headphone system so from previous experience those who turn up typically leave within 5 mins. No reported walk-ups in April 2017. | 2 | 3 | 6 | Open
9 | Increased congestion, parked vehicles around Victoria Dock during production periods and performances. | Relationships with residents sour resulting in addititional pressures on production team for later parts of the project. Access for emergency services reduced. | Alan Lane & Joanna Resnick | 4 | 3 | 12 | Free audience parking at The Deep unless pre-arranged blue badge holder. Marshalls to cover South Bridge Road to re-direct those attending a performance to the appropriate parking spaces. Large number of volunteers to assist with way-finding, directing audiences to site. Production team to car pool where possible. TV team to stay at hotel within walking distance of the performance site - personal vehicles not required. TV trucks to be positioned near swing bridge on site. | 2 | 3 | 6 | Open
10 | Bad weather - heavy rain. | Inability to deliver project as intended. Potential damage to equipment. | Alan Lane & Joanna Resnick | 4 | 2 | 8 | During fit-up and rehearsals crew and cast are prepared to work outdoors with appropriate clothing/PPE. Indoor, sheltered green room spaces available. During performances audiences had been briefed that the event will go ahead in bad weather. Advised to wear waterproofs, warm layers. Show operators to be under shelter. Equipment to be appropriately waterproofed as necessary. | 4 | 1 | 4 | Open
11 | Bad weather - high winds. | Inability to deliver project as intended. Potential damage to equipment. | Alan Lane & Joanna Resnick | 3 | 3 | 9 | During fit-up and rehearsals crew and cast are prepared to work outdoors with appropriate clothing/PPE. Indoor, sheltered green room spaces available. During performances audiences had been briefed that the event will go ahead in bad weather. Advised to wear waterproofs, warm layers. Show operators to be under shelter. Any large set elements to be structurally sound enough to cope with wind loadings. Risk assessments to take into account impact of high winds e.g. pyrotechnic, helicopter, crane etc. | 3 | 2 | 6 | Open
12 | Bad weather - thunder and lightning storm. | Inability to deliver project as intended. Potential damage to equipment. | Alan Lane & Joanna Resnick | 2 | 4 | 8 | At times when an electrical storm is forecast we will exercise vigilance with the Director responsible for the decision to clear the metal structure. When compared with fibreglass or wooden yachts, all-metal boats are rarely damaged by lightning and injuries are uncommon. | 2 | 3 | 6 | Open
13 | Vandalism or theft. | Loss or damage to equipment. Delays to project, financial implications. Potential inability to deliver project as intended. Time consuming for staff responding to incidents. | Alan Lane & Joanna Resnick | 3 | 3 | 9 | Police briefed about the event and to be notified about any incidents on site. Team to be aware of site layout and the potential for a small proportion of the attendees / passersby to seek mischief. Proactive approach required in order to prevent incidents escalating. Regular activity and presence on site. Equipment to be store securely overnight. Additional security measures in place in recent months including new anti-snap/anti-bump locks. | 2 | 3 | 6 | Open
14 | Significant changes to water level in half tide basin | Damage to equipment / set. Inability to close the gates when the pontoon is raised by water level. | Alan Lane & Joanna Resnick | 3 | 3 | 9 | Liasing with Hull City Council to manage the water level via the pump control system. Slung Low now have been trained to turn pumps on and off and less reliant on council staff availability / action. | 1 | 3 | 3 | Open
15 | Blue green algae | Inability to deliver project as intended. | Alan Lane & Joanna Resnick | 4 | 4 | 16 | June 2017 water quality tests indicates that blue green algae is not a concern. Regular lab water testing to be carried out and visual monitoring on site as the warmer weather approaches. Operating under advice taken from leading experts in water quality management. The Water Feature company (on behalf of Hull City Council ) are taking preventative actions with the use of an aerator and blue pond dyes. Slung Low has purchased a second aerator to double the Council's activity. Good hygiene practises on site. | 2 | 4 | 8 | Open
16 | Terrorism attack | Casualties, panic. Inability to deliver project as intended. | Humber Police, Alan Lane & Joanna Resnick | 3 | 5 | 15 | In the event of a specific risk of terrorism to a specific project members of the Police service would inform the event organiser and would advise on specific control measures. Staff on site to be vigilant for unusual activity and to call the Anti-Terrorist Hotline: 0800 789 321 with tip offs/ confidential information or 999 for warnings about possible bombs or other urgent threats. | 2 | 5 | 10 | Open
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...