## Theatre_Social_-_10_Nov
Hull Theatre Social

Event Planning

Item	Detail	Action

DATE	Thursday 10 November

SCHEDULE	5 - 7pm
LOCATION	TBC - A bar, large enough open space, exclusive use during event hours;	MA/HIPI

TECH REQ	PA Required, ideally radio mic hand held	MA/HIPI
	Possible requirement for Projector & Screen	MA/HIPI

PURPOSE OF EVENT	Hull 2017 to host an informal social to gather the Theatre makers of Hull.	HD
	a) To introduce the newly appointed person, Helen Goodman, to lead the Hull Independent Producer Initiative - The HIPI
	b) To introduce Justine Potter, new head of BBC Writer's Room
	c) For Andrew Jones, British Council lead for Drama & Dance, to update Hull sector
	d) 2-3 Hull artists to present plans for 2017
	e) To network and make plans for the future.

HOST	Hull 2017

GUEST LIST	Full sector list - to be confirmed by Hull 2017, City Arts, Uni & Truck

RSVP	To Martin Atkinson by 7 Nov	MA/HIPI

INVITATION	No Design required: simple email.
	Copy:
	HULL THEATRE SOCIAL
	Hull 2017 invite you to join us for a Hull Theatre Social on Thursday 10 November from 5 - 7pm at xxxx location.

	PROGRAMME
	The HIPI. Hull 2017, City Arts, Hull Truck Theatre and the University of Hull are delighted to introduce the lead for the Hull Independent Producer Initiative.
	BBC Writer's Room's new head, Justine Potter
	British Council's Andrew Jones
	Introducing Hull Truck's ChangeMaker - Amanda Huxtable

	Drinks & Nibbles

	7.30pm Akala Performance at Humber Mouth Festival - Central Library. We have 20 tickets for this event for attendees of the Hull Theatre Social - first come first served - max 1 per person.

	RSVP Martin Atkinson on martin.atkinson@hull2017.co.uk by 7 Nov

SPEAKERS	Justine Potter to confirm	HD
	Andrew Jones to confirm	HD
	Amanda Huxtable / Truck to confirm	HD

## HIPI_Briefing
Hull Independent Theatre Initiative - THE HIPI

Briefing Notes - Tuesday 25 October 2016

Agenda	Detail	Action

10am	Induction to Hull 2017 offices	Martin Atkinson, Claire Drury - Hull 2017
	Systems, Email, Hull 2017 Induction Check Sheet

11.30 - 1pm	1) Review of HIPI - context	Henri, Hull 2017, Louise Yates - City Arts
	2) Confirm HIPI objectives:
	To support and grow Hull Independent Theatre Sector
	To mentor, transfer knowledge & expertise to Hull Independent Theatre Sector
	To access, raise and identify new funding and investment for Hull Independent theatre sector
	To network artists, companies, venues & promoters locally, nationally & internationally

	First Quarter Priorities:
	a) Meet all HIPI Partners
	b) Meet core artists/ companies active in Hull
	c) Work with Roaring Girls to develop touring strategies and funding for Weathered Estates
	d) Work with Silent Uproar to develop production plans, touring strategies and funding for Bold Knights of Britain
	e) Help organise Hull 2017 theatre sector social - 10 Nov
	f) take over and build theatre sector 'CRM'

2pm	Possible meetings with Rowan Rutter at Truck and Tim Skelly at University	HIPI

	Familiarise with Hull 2017 systems and project background information.

	Pick up event arrangements for 10 Nov.