## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Level of Co-ordination required for different parties becomes very high | additional resources needing to be channelled towards administration and communications | Holy Trinity (Jane/Kia) | 4 | 4 | 16 | Put planning in place to delegate more administration responsibilities should the load become too great. Be mindful of flexible bidgeting so that HT can increase the number of dedicated administration hours as required as part of the package they contribute to the project | 2 | 3 | 6 | Open
2 | A contributing artist withdraws due to unforeseen circumstances | the day long event may become slightly shorter, or give more space to the other contributors | Holy Trinity (Jane/Kia) | 2 | 2 | 4 | Planning what communications will respond to such an instance, so that immediate and robust action can be taken to fill the gap. Number of parties partaking maximised so that many hands make light work. |  |  | 0 | Closed
3 | Scope Creep | The scope of the delivery is broadened, more people may become engaged, capacity is stretched | Holy Trinity (Jane/Kia) | 4 | 3 | 12 | Capacity is made stretchable by the ensureing that sufficient resources and support are in place when a new contributor comes on board. There is an agreed method of engaging in a new contributor relationship | 3 | 1 | 3 | Open
4 | Decision making delays caused by a large number of voluntary contributors | As the whole process is strictly timebound, delays in meeting might cause delays in casting, script approval payment and any number of other areas | Holy Trinity (Jane/Kia) | 4 | 4 | 16 | Planning meetings a long way in advance, and regular update channels to be maintained without meeting so that decisions can be made by coonsensus without meeting. Open communications by maintaining a quality database of contact inforamtion to prevent this. Clear timescales for action and decision making agreed to and written down. If decisions can be made outside of meetings this reduces the impact as deicisions can be made quickly if needs be. | 2 | 2 | 4 | Open
5 | Unable to secure sufficient funding | Need to downscale the original planning and change the feel of the event, possibly reducing particular contributors ability to be included | Holy Trinity (Jane/Kia)/ Ben Pugh | 3 | 3 | 9 | High and low budget planning is in place so that all parties are clear about what will happen if only minimum funding is secured. The minimum funding plan still incorporates all contributors to their satisfaction to provide something, if not the original planned contribution, at the outset. | 2 | 2 | 4 | Closed
6 | Failure to attract audience | Many contributors make it possible that the contributors outnumber the audience, having a damaging impact on the public profile of the event, effecting the hoped for legacy impact of the project | Holy Trinity and all contributing artists | 2 | 4 | 8 | advanced and detailed PR planning using many sources. appointment of external experienced graphic design department to create good quality literature. Making full use of online advertising made available by CoC, making full use of all school sources to attract parents of participants, quality program to be made available on the day free of charge, use of CoC Volunteers on the day to direct audience towards us and use of CoC whats on Volunteers to make tourists aware of us a week in advance, Noah Wagon parade part of the performance to attract local tourists at point of sale, free entry, church congregation engagement (including Hull wide churches network) to invite participation in the form of a Flash Mob. | 1 | 4 | 4 | Open
7 | Cost forecasting inaccurate | budgets need reallocating which takes budget from elsewhere, could then have implications for partner organisations | Holy Trinity (Jane/Kia) | 2 | 4 | 8 | all expenditure is cleared in advnace of the expenditure being incurred. Clear process of claiming expenses for all participating organisations. Budgets regularly reviewed to ensure we are not creeping too close to our limit faster than we should. Deliberate budget undershoot, leaving a margin to be spent at the end IF the margin is not used for corrective budgeting. | 1 | 2 | 2 | Open
8 | Insufficient Insurance Cover | activities have to be curtailed to what an be insured at short notice. | All participants | 3 | 5 | 15 | Detailed plans of activity to be compiled in April and Submitted to insurance provided to obtain written consent on planning before it becomes problematic to make changes. All contributing organisations are made fully aware that they are responsible for their own insurance needs, but HT requests a copy of their policy document to ensure transparency throughout. | 2 | 3 | 6 | Open
9 | Project Management Lacking | CO-ordination and Communications fail and cohesion between parties is lost, deadlines are missed and the final production loses focus, or fails to produce the desired outcome | Holy Trinity | 3 | 5 | 15 | Holy Trinity Administration and Project staff allocated exclusively to the project on flexible contract terms. Holy Trinity committed to meeting these costs so that the adminstration base is reliable and able to rise to need. HT holding quality information for all parties and has a clear table of deadlines to be met. HT to be clear and transparent about what it is ableto provide so that any challenges in this respect can be identified and dealt with early. | 1 | 3 | 3 | Open
10 | Weather is foul on the day | The project becomes arduous, poor turnout, public experience is diminished, legacy effected, partners disheartened | Holy Trinity | 3 | 4 | 12 | Wet weather planning put in place from an early stage, Church building open and culture of encouragement and positivity adopted amongst contributors, wet weather options discussed at open meeting | 2 | 3 | 6 | Open
11 | [5 empty] | 0 |  |  |  | 0
12 | [5 empty] | 0 |  |  |  | 0
13 | [5 empty] | 0 |  |  |  | 0
14 | [5 empty] | 0 |  |  |  | 0
15 | [5 empty] | 0 |  |  |  | 0
16 | [5 empty] | 0 |  |  |  | 0
17 | [5 empty] | 0 |  |  |  | 0
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...