MADE IN HULL 2017

BUILD & BREAK

PHASED PLAN

CONTENTS

| Page 3 | Overview |
| --- | --- |
| Page 4 | Core Operations Team |
| Page 5 - 12 | Schedule Breakdown - Build |
| Page 13 | Rehearsal Days - 29/12/16 - 30/12/16 |
| Page 14 | Show Days 01/01/17 - 07/01/17 |
| Page 15 - 18 | Schedule Breakdown - Break - 07/01/17 |
| Page 19 | Appendices |
| Page 20 | Appendix 1 - Show Plans |
| Page 21 | Appendix 2.1 QVS Show Plan |
| Page 22 | Appendix 2.2 Underpass Show Plan |
| Page 23 | Appendix 2.3 The Deep Show Plan |
| Page 24 | Appendix 2.4 Zebedees Yard Show Plan |
| Page 25 | Appendix 2.5 Scale Lane Staith Show Plan |
| Page 26 | Appendix 3 - Structural Drawings |
| Page 27 | Appendix 3.1 QVS Projection Platforms |
| Page 28 | Appendix 3.2 QVS Front of House Tower |
| Page 29 | Appendix 3.3 QVS Projection Tower |
| Page 30 | Appendix 3.4 QVS Cable Pylon |
| Page 31 | Appendix 3.5 Zebedees Yard Lighting Tower |
| Page 32 | Appendix 3.6 C4DI (The Deep) Projection Platform |
| Page 33 | Appendix 3.7 Underpass Screen Support Small |
| Page 34 | Appendix 3.8 Underpass Screen Support Large |
| Page 35 | Appendix 4 - Hull Production Suppliers |
| Page 36 | Appendix 5 - Plant Schedule |
| Page 37 | Appendix 5 - Plant Schedule continued |

OVERVIEW

The purpose of this document is to provide a brief for Hull city council and individual venues with a brief guide to the production schedule for the build and de-rig of Made In Hull; the launch event for Hull 2017.

Should there be any queries on the contents of this brief, please direct all correspondence through Chris Clay in the first instance to be directed to the person(s) responsible for the area with which the matter concerns.

To accompany the brief there are also appendices outlining:- plant movement, temporary structure drawings, site plans & plant working zones to be referenced at will. We have also drawn up technical production information packs for each venue, detailing specific technical specifications. These are available at request.

CORE OPERATIONS TEAM

SCHEDULE BREAKDOWN: – BUILD

19/12/2016

QVS

-Initial fencing off of working areas begins. There will also be a 7.5t truck unloading scaffolding ready for the first structures to be built.

Whitefriar Gate

No activity scheduled.

Zebedee's Yard

No activity scheduled.

Scale Lane Staith

-Building of projection tower in the yard of the Lion & Key pub, delivered by a 7.5t truck.

The Underpass

No activity scheduled.

The Deep

-Building of modular deck system on the 3rd floor balcony of C4Di, delivered by a 18t truck.

20/12/2016

QVS

-Building of projection platforms on the monument plinth in the centre of the square.

-Siting of twinset generators, 7m tele handler.

-Delivery of 10m PA towers, 7.5t truck.

-Tower light delivery.

Whitefriar Gate

-External cleaning of units 6a,6,8,9,16,17,20,23

Zebedee's Yard

No activity scheduled.

Scale Lane Staith

No activity scheduled.

The Underpass

No activity scheduled.

The Deep

No activity scheduled.

21/12/2016

QVS

-Erection of 10 PA towers, 7m tele handler.

Whitefriar Gate

No activity scheduled.

Zebedee's Yard

No activity scheduled.

Scale Lane Staith

No activity scheduled.

The Underpass

No activity scheduled.

The Deep

No activity scheduled.

22/12/2016

QVS

-Screen windows (externally) of Maritime, City Hall & Ferens with vinyl, truck mounted access platform.

-Audio cable install, cable runs across roof tops of all 3 buildings.

-Architectural LED install on facia of Martime Museum and City Hall.

Whitefriar Gate

-Screen the window (internally) of unit 9 with contra-vision.

Zebedee's Yard

-Delivery and erection of 12m z towers for lighting, 7m tele handler.

-Fencing install.

-Generator delivery.

Scale Lane Staith

No activity scheduled.

The Underpass

Delivery of all rigging, 7.5t truck.

The Deep

No activity scheduled.

23/12/2016

QVS

-Screening of windows using a truck mounted access platform at all civic buildings.

Whitefriar Gate

-Test projection run in Unit 8.

Zebedee's Yard

No activity scheduled.

Scale Lane Staith

No activity scheduled.

The Underpass

-Rigging install, 17m tele handler and man basket.

-Generator drop, 17m tele handler.

The Deep

No activity scheduled.

27/12/2016

QVS

-Lighting load in on square and rooftops, LWB vans.

-Projector load in, 40' artic truck.

-Audio load in, LWB van.

Whitefriar Gate

-Projector install.

-Lighting install.

-Audio install.

Zebedee's Yard

-Lighting install, 60ft cherry picker.

Scale Lane Staith

-Projector install, 7m tele handler.

-Generator drop, 17m tele handler.

The Underpass

-Install projectors, 17m tele and man basket.

The Deep

-Build PA risers, delivered in LWB van.

28/12/2016

QVS

-Technical system checks.

-Overnight projection line up.

Whitefriar Gate

-Install audio. Delivered in LWB van.

-Overnight projection line up.

Zebedee's Yard

-Install audio. Delivered in LWB van.

-Overnight projection line up.

Scale Lane Staith

-Install audio. Delivered in LWB van.

-Overnight projection line up.

The Underpass

-Install lighting. Delivered in LWB van.

-Install audio. Delivered in LWB van.

-Overnight projection line up.

The Deep

-Install lighting in the nose. Delivered in LWB van.

-Install audio. Delivered in LWB van.

-Generator drop. 17m tele handler.

-Overnight projection line up.

29/12/2016 – 30/12/2016

-Noise propagation at all site 10:00 – 12:00.

-Sound checks across all sites 12:00 – 16:00.

-Production rehearsals across all sites 16:00 – 21:00.

01/01/2017 – 07/01/2017

-Live activation across all sites 16:00 – 22:00.

SCHEDULE BREAKDOWN: – BREAK

07/01/2017

QVS

-Strike all video, 40ft artic.

-Strike all lighting, 40ft artic.

-Strike all audio, 40ft artic and 60ft cherry picker.

-Strike projection platforms on monument plinth, 7.5t truck.

-Strike PA and cable towers, 7m tele handler and 7.5t truck.

08/01/2017

Whitefriar Gate

-Strike all video, LWB van.

-Strike all lighting, LWB van.

-Strike all audio, LWB van.

Zebedee's Yard

-Strike all lighting, LWB van & 60ft cherry picker.

-Strike all audio, LWB van.

-Strike towers, 7.5t & 17m tele handler.

Scale Lane Staith

-Strike video, LWB van & 7m tele handler.

-Strike audio, LWB van.

-Strike projection tower, 7.5t truck and 7m tele handler.

The Underpass

-Strike lighting, 60ft cherry picker and LWB van.

-Strike audio, 60ft cherry picker and LWB van.

-Strike projection, 17m tele handler with man basket and LWB van.

-Strike structures and rigging, 7.5t truck and 60ft cherry picker.

The Deep

-Strike audio, 7m tele handler and 40ft artic.

-Strike lighting, 40ft artic.

-Strike projection, 40ft artic.

-Strike structures, 7.5t truck.

09/01/2017

QVS

-Strike PA towers, 17m tele and 7.5t truck.

Zebedee's Yard

-Strike lighting towers, 17m tele and 7.5t truck.

APPENDICES

APPENDIX 1 – SHOW PLANS

APPENDIX 2.1 QVS SHOW PLAN

APPENDIX 2.2 UNDERPASS SHOW PLAN

APPENDIX 2.3 THE DEEP SHOW PLAN

APPENDIX 2.4 ZEBEDEES YARD SHOW PLAN

APPENDIX 2.5 SCALE LANE STAITH SHOW PLAN

APPENDIX 3 – STRUCTURAL DRAWINGS

APPENDIX 3.1 QVS PROJECTION PLATFORMS

APPENDIX 3.2 QVS FRONT OF HOUSE TOWER

APPENDIX 3.3 QVS PROJECTION TOWER

APPENDIX 3.4 QVS CABLE PYLON

APPENDIX 3.5 ZEBEDEES YARD LIGHTING TOWER

APPENDIX 3.6 C4DI (THE DEEP) PROJECTION PLATFORM

APPENDIX 3.7 UNDERPASS SCREEN SUPPORT SMALL

APPENDIX 3.8 UNDERPASS SCREEN SUPPORT LARGE

APPENDIX 4

| HULL - PRODUCTION SUPPLIERS |  |  |
| --- | --- | --- |
| ROLE | COMPANY | SITE CONTACT |
| AUDIO | Tube | Melv Coote |
| LIGHTING | DBN | Nick Walton |
| PROJECTION & VIDEO | Bluman Associates | Simon Hudson |
| STRUCTURES & RIGGING | Star Events | Pete Holdich |
| POWER | Midas | David Noble |

APPENDIX 5 – PLANT SCHEDULE

| DATE | DEPARTMENT | ACTIVITY | LOCATION | PLANT REQUIRED | REQUIRED FROM | REQUIRED UNTIL |
| --- | --- | --- | --- | --- | --- | --- |
| 19/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 19/12/2016 | STAR EVENTS | TRUCK CROSSLOADING | BONEYARD | 926 | 11:00 | 12:00 |
| 19/12/2016 | STAR EVENTS | TRUCK UNLOADING | SLS | 7M | 13:00 | 16:00 |
| 19/12/2016 | STAR EVENTS | TRUCK UNLOADING | QVS | 7M | 19:00 | 20:00 |
| 20/12/2016 | STAR EVENTS | TRUCK UNLOADING | QVS | 7M | ALL DAY | ALL DAY |
| 20/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 21/12/2016 | PRODUCTION | WINDOW SCREENING | QVS | TRUCK MOUNT | ALL DAY | ALL DAY |
| 21/12/2016 | STAR EVENTS | TRUCK UNLOADING | QVS | 7M | ALL DAY | ALL DAY |
| 21/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 22/12/2016 | TUBE | CABLE INSTALL | QVS | 17MW/BASKET | 08:00 | 18:00 |
| 22/12/2016 | STAR EVENTS | TRUCK UNLOADING | ZEBEDEE'S YARD | 7M | 08:00 | 13:00 |
| 22/12/2016 | STAR EVENTS | TRUCK CROSSLOADING | BONEYARD | 926 | 18:00 | 18:30 |
| 22/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 23/12/2016 | STAR EVENTS | RIGGING INSTALL | UNDERPASS | 17MW/BASKET | 08:00 | 13:00 |
| 23/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 27/12/2016 | BLUMAN | PROJECTOR INSTALL | UNDERPASS | 17MW/BASKET | 12:00 | 16:00 |
| 27/12/2016 | BLUMAN | PROJECTOR INSTALL | SLS | 7M | 12:00 | 16:00 |
| 27/12/2016 | DBN | LX INSTALL | ZEBEDEE'S YARD | 60'PICKER | 13:00 | 19:00 |
| 27/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 28/12/2016 | TUBE | AUDIO INSTALL | THE DEEP | 7M | 08:00 | 10:00 |
| 28/12/2016 | DBN | LX INSTALL | UNDERPASS | 17MW/BASKET | 14:00 | 19:00 |
| 28/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 29/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 30/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 07/12/2016 | ALL | TRUCK LOADING | QVS | 7M&17M | 21:00 | 04:00 |
| 08/02/2017 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 08/02/2017 | BLUMAN | PROJECTOR DERIG | UNDERPASS | 17MW/BASKET | 09:00 | 11:00 |
| 08/02/2017 | DBN | LX DERIG | UNDERPASS | 60'PICKER | 09:00 | 11:00 |
| 08/02/2017 | TUBE | AUDIO DERIG | THE DEEP | 7M | 09:00 | 11:00 |
| 08/02/2017 | BLUMAN | PROJECTOR DERIG | SLS | 7M | 11:00 | 13:00 |
| 08/02/2017 | STAR EVENTS | TRUCK LOADING | SLS | 7M | 11:00 | 13:00 |
| 08/02/2017 | DBN | LX DERIG | ZEBEDEE'S YARD | 60'PICKER | 11:00 | 13:00 |
| 09/02/2017 | STAR EVENTS | TRUCK LOADING | ZEBEDEE'S YARD | 7M | 08:00 | 14:00 |
| 09/02/2017 | STAR EVENTS | PA TOWER DERIG | QVS | 7M | 14:00 | 17:00 |
| 09/02/2017 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 10/02/2017 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |