## production calendar - Project V
| MONDAY |  | TUESDAY |  | WEDNESDAY |  | THURSDAY |  | FRIDAY |  | SATURDAY |  | SUNDAY |  |  |  |  | WK
MAR | 6 |  | 7 | TS Oxford | 8 | TS Oxford | 9 | TS Oxford | 10 | TS Oxford | 11 | TS Oxford | 12 | TS Oxford |  |  |  | 10
| 13 |  | 14 |  | 15 | Contract Sign | 16 |  | 17 |  | 18 |  | 19 |  |  |  |  | 11
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  |  |  |  | 12
| 27 |  | 28 |  | 29 | Skype Meeting 2pm | 30 |  | 31 |  | 1 |  | 2 |  |  |  |  | 13
APR | 3 |  | 4 | Potential Hull Trip | 5 |  | 6 |  | 7 | Budget Sign off day | 8 |  | 9 |  |  |  | APR | 14
Thor Away
| 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | INSTITUTE PressL |  |  | 15
Thor Away
Chloe Away
| 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | Periplum Herlad |  |  | 16
R&D & Prototyping for Vearos & VD
| 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | Periplum odds |  |  | 17
| R&D & Prototyping for Vearos & VD | [9 empty] | Chloe Away
MAY | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | PERIPLUM SHOW |  | MAY | 18
R&D & Prototyping for Vearos & VD
Chloe Away
| 8 |  | 9 |  | 10 | Chloe to design Volunteer Training | 11 |  | 12 |  | 13 | Josh Herald/workshop? | 14 | Workshop? | Joshua Herald |  |  | 19
r&d & Prototyping for Vearos & VD
| 15 | G&N depart | 16 |  | 17 | Chloe to design Volunteer Training | 18 |  | 19 |  | 20 | Volunteer Training | 21 |  |  |  |  | 20
| Fabrication week one - beckenham | [7 empty] | Chloe & Thor Travel |  | Chloe & Thor in Hull
THEO
| 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | Lone Twin Herald! |  |  | 21
Fabrication week two - beckenham
THEO
| 29 |  | 30 |  | 31 | G&N return | 1 |  | 2 |  | 3 |  | 4 |  |  |  |  | 22
Fabrication week three - beckenham
THEO
JUN | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  |  |  | JUN | 23
Fabrication week four - brixton
| 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 | Josh Open Shop | 18 | Father's Day | JOSH SHOP OPEN |  |  | 24
Fabrication week five - brixton
| 19 |  | 20 |  | 21 | Chloe to design rehearsal weekend | 22 | YORKSHIRE WATER DIG HOLE -PERFORMER DAY 1 | 23 | 2A ReRe HERALD - Crate extracted Performer Day 2 | 24 |  | 25 |  | Herald#1-Aswarm |  |  | 25
|  | Fab week 6 - brixton |  |  | Thor & Performer in Hull
| 26 | H17 Budget & Schedule update | 27 |  | 28 | Chloe to design rehearsal weekend | 29 |  | 30 |  | 1 | REHEARSAL 10-6PM 6.30-9 WITH VOLUNTEERS | 2 | REHEARSAL 11-7PM WITH VOLUNTEERS, 6-7PM PHOTOSHOOT | VEARO |  |  | 26
[9 empty] | Chloe & Thor Travel |  | Chloe/ Thor, Joe and Brian in Hull
JUL | 3 | 2B VEARO 1st run | 4 | 2B VEARO 1st run | 5 | 2B VEARO 1st run | 6 | 2B VEARO 1st run | 7 | edit & test VEAR data | 8 | edit & test VEAR data | 9 | edit & test VEAR data | VEARO |  | JUL | 27
| Chloe/thor/joe & brian |  | Thor/Joe/Brian in Hull | [5 empty] | Rig Installation for testing in space (London)
| 10 | edit & test VEAR data | 11 | Test’s inform 2nd run | 12 | 2B VEARO 2nd run | 13 | 2B VEARO 2nd run | 14 | 2B VEARO 2nd run | 15 | 2B VEARO 2nd run | 16 | 2B VEARO 2nd run | VEARO |  |  | 28
|  |  | chloe travel |  | chloe-direct, Joe VEARO |  |  |  | chloe & Joe as VEAROS + Vols
Rig Installation for testing in space (London)
| 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | Lone Twin Event |  |  | 29
Thor Away working in Kosovo with Phone Box
| 24 | Edit & SD | 25 | Edit & SD | 26 | Edit & SD | 27 | Edit & SD | 28 | Edit & SD | 29 | Edit & SD | 30 | Edit & SD | RR & Institute call out |  |  | 30
| 31 | Edit & SD | 1 | pak away | 2 | Aswarm AWAY | 3 |  | 4 |  | 5 |  | 6 |  |  |  |  | 31
AUG | 7 | Aswarm AWAY | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  |  |  | AUG | 32
| 14 | Aswarm AWAY | 15 |  | 16 |  | 17 |  | 18 |  | 19 | JOSH Close Shop>PARADE | 20 |  | Josh PARADE |  |  | 33
| 21 | Aswarm AWAY | 22 |  | 23 | Show Norway | 24 | Show Norway | 25 | Show Norway | 26 | Show Norway | 27 | Show Norway | RR & Institute call out |  |  | 34
| 28 | Show Norway | 29 | Show Norway | 30 | Show Norway | 31 | Show Norway | 1 | Show Norway | 2 |  | 3 |  | RR & Institute call out |  |  | 35
SEP | 4 | Access to Staples - Re build system | 5 | Edit, SD & Test runs | 6 | Edit, SD & Test runs | 7 | Edit, SD & Test runs | 8 | Edit, SD & Test runs | 9 | Edit, SD & Test runs | 10 | Vol Audience to Staples for testing | Herald#2 & VEARO 3C |  |  | 36
|  | DRIVE & UNLOAD |  | SORT VEARA | HERALD #2 VEARO 3rd Hessle |  | VEARO 3rd Hessle (Performers & Volunteers)
[5 empty] | Chloe in Hull 6-12th |  | (can be VEARO if needed) | [5 empty] | Chloe in Hull
4th - 10th Sept Outdoor Space for VD testing in Hull
| 11 |  | 12 |  | 13 |  | 14 | Master | 15 | Master | 16 |  | 17 |  | VEARO |  |  | 37
Chloe in Hull
Edit, SD & Test runs
11th-17th Sept Indoor Space for VD testing in Hull
| 18 | pack &travel | 19 | Install PikPark | 20 | Install PikPark | 21 | Install PikPark/ rehearsal | 22 | Soft launch & adjust Insitu | 23 | VEAR 4B OPEN | 24 |  | Aswarm: PickPark |  |  | 38
Chloe in Hull 20th-1st October
Install & run in Pickering Park
| 25 |  | 26 | Turner PRize | 27 |  | 28 | BBC spokenWordFest>2nd | 29 | BBC | 30 |  | 1 | derig | Aswarm: PickPark |  |  | 39
Chloe in Hull 20th-1st October
Run & Derig in Pickering Park
OCT | 2 | BBC | 3 |  | 4 |  | 5 |  | 6 |  | 7 | HULL FAIR | 8 | HF | LP Herald |  |  | 40
| 9 | Hull FAIR | 10 | Hull FAIR | 11 | Hull FAIR | 12 | Hull FAIR | 13 | Hull FAIR | 14 | HF & LP OPEN | 15 | HF & LP OPEN | LP-OPEN | Hull FAIR |  | 41
| 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | Little People? |  |  | 42
| 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 | HALF TERM | 29 | HALF TERM | Little People? |  |  | 43
| 30 | HALF TERM | 31 | Halloween | 1 | HALF TERM | 2 | HALF TERM | 3 | HALF TERM | 4 | HALF TERM | 5 | HALF TERM | MAC prep |  |  | 44
NOV | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 | PARADE | 12 |  | MACNAS PARADE |  |  | ?
© www.calendarlabs.com

## sept
| MON |  | TUES |  | WED |  | THURS |  | FRI |  | SAT |  | SUN
SEP | 4 | Access to Staples - Re build system | 5 | Edit, SD & Test runs | 6 | Edit, SD & Test runs | 7 | Edit, SD & Test runs | 8 | Edit, SD & Test runs | 9 | Edit, SD & Test runs | 10 |  | Herald#2 & VEARO 3C
|  | DRIVE & UNLOAD |  | SORT VEARA | VEARO 3rd Hessle - Chloe & Joe plus Vols | [5 empty] | chloe VEARO solo out |  | chloe solo out
|  |  | Chloe to Hull |  | Chloe in Hull
[9 empty] | THOR AWAY - WEDDING |  |  |  | Thor Nick travel
| 11 |  | 12 | Vol Aud to Staples for testing?? | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | VEARO
Chloe in Hull
Edit, SD & Test runs
11th-17th Sept Indoor Space for VD testing in Hull
| 18 | staples | 19 | staples | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | Aswarm: PickPark
[6 empty] | pack & move to park |  | install |  | install |  | install | 3-6 aft vol rehearsal | none performer tech run eve
[9 empty] | nick travel |  | nick |  | nick
Chloe in Hull 20th Sept -2nd October
| 25 |  | 26 | Turner PRize | 27 |  | 28 | BBC spokenWordFest>2nd | 29 | BBC | 30 |  | 1 | derig | Aswarm: PickPark
| tinkering onsite |  | tinker | 6-9 soft launch | run | run | run | run | run | run | run | run | run | derig eve
| nick |  | nick |  | nick travel
MON 2/10
| derig & pack |  | Come and see Re-Rediffusion Voice Park - a place to play with the voice of Hull. Come and help Re-Rediffusion Distil the Power of Hull's Voice #ProjectVEAR