## Sheet1
Aswarm
From calendar and specification sent: 23.02.17 - Thor
Sepcification of requirements |  |  | OWNER
2017-06-24 | Site management - Rediffusion location - Beverley Road | Permission | GH
| Set design | ?? | ??
| Crates | Numbers? | GH
|  | Animation? | GH
2017-06-26 | 2 day venue hire for VEARO training | Location? | LY
| 6x Volunteer performers | Times? | LY/EB
|  | Facilities? | LY/EB
|  | Specific days? | LY/EB
1 - 5 July | 6x Volunteer performers |  | LY
| High access management - ladders? | Times? | AL
|  | Locations? | AL
|  | Materials, fixings, method? | AL
12 - 16 July | 6x Volunteer performers |  | LY
| High access management - ladders? | Times? | AL
|  | Locations? | AL
|  | Materials, fixings, method? | AL
09 - 13 Sept | Site management - Pcikering Park | Permission | GH
| Set design | ?? | ??
| Crates | Numbers? | GH
|  | Animation? | GH
| Crates | In and around Hessle Road | GH
|  | Locations? | GH
2017-09-09 | 1 day venue for VEARO refresher training | Hessle Road | LY/EB
| 6x Volunteer Performers | Same as round one? | LY/EB
18th Sept | Drain and clean pool | Parks Dept | GH
19th - 21st Sept | 2x local crew riggers | Pickering Park | AL
08:00 - 18:00?
19th Sept - 1 Oct | Power and distro | locations and amounts? | AL
| Site lighting | Safety or Effect | AL
19th Sept - 2 Oct | Security | 24hr | AL
22 Sept to 1 Oct | X Volunteer Guides | Times? | EB
|  | Numbers? | EB
| Volunteer Lead | Each with half day on site training? | EB
19th Sept - 2 Oct | Working Lights (Rig & Derig) |  | AL
| Site Lights (i.e. ambient safety during install and or overnight security) |  | AL
| Ballast (water Butt) To rig poles for 2x suspended Big Bassy pods (tripod system_ |  | AL
| Cable Ramp |  | AL
| Herris Fencing (part of overnight security) |  | AL
| Cherry Picker Hire (2 day rig & tests ,1 day derig) |  | AL