## Sheet1
In what ways, if any, could the project management of Made in Hull be improved?
Respondents | Response Date | Response Text | Categories
1 | 2016-12-31 15:23 | More indians less chiefs
2 | 2016-12-23 14:08 | I felt like it was big engine steamrolling ahead and I'd probably like a bit less of that in future if possible. Would like more creative freedom and input without having such a big team.
3 | 2016-12-21 16:32 | Accessibility to peers - they don't all live in Hull, which means availability for meetings has been quite limited. But I guess that can be expected on a project of this scale.
4 | 2016-12-21 10:38 | More time given to me as Producer
5 | 2016-12-20 15:15 | Initial creative impetus was very strong. Mix of internal and external voices was strong. Form was good. Making the opening event open and inclusive was a good idea. First 6 months - developed strong ideas. Moving the trail was a strong decision. The creative process was positive. Weaknesses: Lack of communications in terms of a project plan, timescales etc - felt it was all in the heads of the 2017 senior team. Late appointment of the Producer. Secrecy - local community could have been used more effectively - ownership has stayed with the artists rather than the local community. Consultation over content - local artists were never commissioned. Towards the end the Producer was making decisions without the input of the rest of the team. They were mainly down to budget I think but they still affected the rest of the project so they should have been flagged.