## Sheet1
Date | Activity | Person | PRSF Composer Residencies | Completed
2017-04-19
2017-04-20 | Creative Brief Distributed to artist/designer | Gail/Martin |  | Y
2017-04-21
James Redwood: CPD session - 10am-4:30pm at Albemarle (with local music leaders, and residency students)
| Final Production schedule sent to artists. | Gareth/Martin/Carys |  | y
2017-04-22
2017-04-23
2017-04-24 |  |  | Jason Singh meeting with supporting artists in urban group before 2pm. Workshopping with Hull Freedom Chorus 7-9pm
2017-04-25 |  |  | Jason Singh at The Warren., 11am-3:30pm
2017-04-26 |  |  | Jason with colours of music leaders - full day devising
2017-04-27 |  |  | Jason with colours of music leaders - full day devising
2017-04-28 | All images and updated copy collected for website and design | Gail |  | y
| Final quote for Clare for residencies performance. | Gareth/Clare/Carys
2017-04-29
2017-04-30
2017-05-01
2017-05-02 | Tech Spec Update | Gareth/Martin/Carys
2017-05-03 |  |  | Jason Singh workshop cancelled
2017-05-04 |  |  | Brian Irvine: Buckingham Day Centre 12:45-1:45pm, 3:30 The Crossings time tbc
2017-05-05 |  |  | Brian Irvine: 10:30-12pm Pickering and Ferens Homes - Big Elastic Band, at Broadway Pavillion
2017-05-06
2017-05-07
2017-05-08 | First draft wayfinding plan. | Gail
| Art work/Identity for PRSF complete. | Gail
2017-05-09 |  |  | Sam Lee in Hull. Chris to capture.
2017-05-10 | Box Office Setup forms complete with increeased capacity | Martin/Gareth |  |  | Holy Trinity
2017-05-11 | Volunteer Meeting to identify requests | Gareth/Martin/Gail/Clare
| Budget Update | Gareth/Sam/Martin
2017-05-12 | Hannah Peel additional performance to go on sale | Martin/Chris
| Contract completed with Fruit and City Hall with regards to additional requirements from venues. | Gareth/Carys/Martin
2017-05-13
2017-05-14
2017-05-15 | Evaluation techniques | Elinor/Pippa/Martin/Gail/Naomi B
2017-05-16 | Submit volunteer requests
2017-05-17
2017-05-18 | Tickets on sale for all gigs | Martin/Chris
2017-05-19 | Secure EMs/SMs for each venue | Gareth/Carys/Martin
2017-05-20
2017-05-21
2017-05-22 | Art work complete. Applied and sent to printers. | Gail/Designer
2017-05-23
2017-05-24 | First draft booklet and map
2017-05-25 |  |  | Errollyn Wallen in Hull: AM with open doors. PM ThorsEby Primary.
2017-05-26 |  |  | THORESBY Primary with ERROLLYN
2017-05-27
2017-05-28
2017-05-29 | Budget Update | Martin/Gareth/Sam
Final Tech Specs Received
2017-05-30
2017-05-31 | 2nd Draft booklet and Map | Gail/Designer
2017-06-01 | Review Hospitality - after show parties. | Jenny/Martin/Sam
2017-06-02
2017-06-03
2017-06-04
2017-06-05 | Review Press/invites/VIPs/Coverage | Ben/Susie/Martin/Sam
2017-06-06
2017-06-07 | Revisit and EMs and SMs | Gareth
2017-06-08
2017-06-09 | Final draft of booklet and map | Gail/Designer
| Booklet sent to printers | Gail/Designer
2017-06-10
2017-06-11
2017-06-12 | Accreditation: Delivered | Martin/Gareth
2017-06-13
2017-06-14
2017-06-15
2017-06-16 | Booklet returned | Gail
2017-06-17
2017-06-18
2017-06-19 | Budget Update | Martin/Gareth/Sam
2017-06-20
2017-06-21
2017-06-22
2017-06-23
2017-06-24 | Residencies performance at City Hall | Clare and team!
2017-06-25
2017-06-26
2017-06-27
2017-06-28 | Wayfinding installed on streets | Gail/Carys
| Residency supergroup rehearsals | Clare
2017-06-29 | Wayfinding/Site dressing installed | Gail/Gareth/Carys
| Residency supergroup rehearsals | Clare
2017-06-30 | PRSF NMB
| Residency supergroup rehearsals | Clare
2017-07-01 | PRSF NMB
2017-07-02 | PRSF NMB
2017-07-03
2017-07-04
2017-07-05
2017-07-06
2017-07-07
2017-07-08
2017-07-09
2017-07-10

## Sheet2
Date [Happening]
2017-04-01
2017-04-02
2017-04-03
2017-04-04
2017-04-05
2017-04-06
2017-04-07
2017-04-08
2017-04-09
2017-04-10
2017-04-11
2017-04-12
2017-04-13
2017-04-14
2017-04-15
2017-04-16
2017-04-17
2017-04-18
2017-04-19
2017-04-20
2017-04-21
2017-04-22
2017-04-23
2017-04-24
2017-04-25
2017-04-26
2017-04-27
2017-04-28
2017-04-29
2017-04-30