## Guidance
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
security incident on parade | public safety, reputational damge | stewarding crash-team response
security incident in event arena | public safety, reputational damge | stewarding crash-team response
oversubscribed event (over capacity in event arena) | heigtened risk of behavioural incidents, reputational damage | employ professional help with event planning
artist fails to appear | Reputational damage with creative team, stakeholders and general public | social media and communications planning
bad weather | poor attendance, gate figures down, loss of takings for vendors, lesser impact for sponsors | make better use of covered spaces, give alternative activities until better weather returns via social media
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | early involvement of Legal team, use of standard templates
Insufficient budget | Inability to deliver project | accurate forecasts, management of expectations
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | roles & responsibilities defined, regular review of milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | contracts where required, regular updates
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | thorough agreements/contracts

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | Jeff | 3 | 5 | 15 | Suppliers made aware of 30-day payment terms and all been set up on system already. POs raised and awaiting approval. Project budget includes detailed projected cashflow and Finance team are aware. | 2 | 3 | 6 | Open
2 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | Jeff | 3 | 5 | 15 | Not yet determined insurance requirements - on agenda for next project team meeting. | 3 | 5 | 15 | Open
3 | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | Jeff | 4 | 4 | 16 | Scope of project signed off at SLT at greenlight. Detailed project brief attached to commissioning & production agreement. All aware that no additional budget is available for extra activity. | 2 | 4 | 8 | Open
4 | [5 empty] | 0 |  |  |  | 0
5 | [5 empty] | 0 |  |  |  | 0
6 | [5 empty] | 0 |  |  |  | 0
7 | [5 empty] | 0 |  |  |  | 0
8 | [5 empty] | 0 |  |  |  | 0
9 | [5 empty] | 0 |  |  |  | 0
10 | [5 empty] | 0 |  |  |  | 0
11 | [5 empty] | 0 |  |  |  | 0
12 | [5 empty] | 0 |  |  |  | 0
13 | [5 empty] | 0 |  |  |  | 0
14 | [5 empty] | 0 |  |  |  | 0
15 | [5 empty] | 0 |  |  |  | 0
16 | [5 empty] | 0 |  |  |  | 0
17 | [5 empty] | 0 |  |  |  | 0
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...