## Activity plan.txt
Start date | End date | Activity or task details | Task lead
2016-09-12 | 2017-09-08 | Company Meeting - 1 per month | Paul Smith
2016-09-12 | 2017-09-08 | Core Team Work Day & Recap - 1 per week | Mungo Arney
2016-09-26 | 2016-09-26 | Casting Complete for Dancing Dead | Paul Smith
2016-10-01 | 2016-10-01 | Five Years R&D Contracts Completed | Mungo Arney
2016-10-01 | 2016-10-01 | Contracts completed - The Dancing Dead | Mungo Arney
2016-10-03 | 2016-10-03 | Advertisement Deadline - The Dancing Dead | Jamie Potter
2016-10-03 | 2016-10-03 | Board Meeting 1 | Mungo Arney
2016-10-10 | 2016-10-10 | Dancing Dead Draft Deadline | Paul Smith
2016-10-10 | 2016-10-15 | Composition - The Dancing Dead | Paul Smith
2016-10-17 | 2016-10-17 | Dancing Dead Design Deadline | Paul Smith
2016-10-17 | 2016-10-17 | Print Design & Distribution Deadline - The Dancing Dead | Jamie Potter
2016-10-17 | 2016-10-27 | The Dancing Dead - Rehearsals | Paul Smith
2016-10-28 | 2016-10-28 | The Dancing Dead - Performance | Mungo Arney
2016-10-31 | 2016-11-04 | Evaluation - The Dancing Dead | Mungo Arney
2016-11-07 | 2016-11-11 | Five Years R&D | Paul Smith
2016-11-14 | 2016-11-18 | Evaluation - Five Years R&D | Mungo Arney
2016-11-18 | 2016-11-18 | Marketing Strategy Meeting 1- Five Years | Jamie Potter
2016-11-20 | 2016-11-20 | Creative Team Contracts Completed - Five Years | Mungo Arney
2016-12-12 | 2016-12-12 | Decision on Designer - Five Years | Paul Smith
2016-12-31 | 2016-12-31 | Submission of Company Accounts | Mungo Arney
2017-01-16 | 2017-01-16 | Board Meeting 2 | Mungo Arney
2017-01-16 | 2017-01-16 | Draft 1 Deadline - Five Years | Paul Smith
2017-01-23 | 2017-01-23 | Marketing Strategy Meeting 2- Five Years | Jamie Potter
2017-02-13 | 2017-02-24 | Company Member Development Period | Paul Smith
2017-02-24 | 2017-02-24 | Production & Distribution of Company Flyer | Jamie Potter
2017-02-24 | 2017-02-24 | Refresh of Website Deadline | Jamie Potter
2017-03-13 | 2017-03-13 | Marketing Strategy Meeting 3- Five Years | Jamie Potter
2017-03-13 | 2017-03-17 | Preparation & Submission of Interim Report | Mungo Arney
2017-04-03 | 2017-04-03 | Board Meeting 3 | Mungo Arney
2017-05-10 | 2017-05-10 | Rehearsal Draft Deadline - Five Years | Paul Smith
2017-05-19 | 2017-05-19 | Sign off of Marketing Plan - Five Years | Jamie Potter
2017-05-22 | 2017-05-26 | Auditions - Five Years | Paul Smith
2017-06-05 | 2017-06-05 | Performer Contracts Completed - Five Years | Mungo Arney
2017-06-12 | 2017-06-12 | Selection of Performing Bands | Mungo Arney
2017-07-03 | 2017-07-03 | Composition Deadline - Five Years | Paul Smith
2017-07-03 | 2017-07-03 | Design Deadline - Five Years | Paul Smith
2017-07-04 | 2017-07-04 | Board Meeting 4 | Mungo Arney
2017-07-17 | 2017-08-11 | Five Years - Rehearsals | Paul Smith
2017-07-17 | 2017-07-17 | Invite List Confirmed - Five Years | Mungo Arney
2017-07-17 | 2017-07-17 | Advertisement Deadline - Five Years | Jamie Potter
2017-07-21 | 2017-07-21 | Print Design & Distribution Deadline - Five Years | Jamie Potter
2017-08-13 | 2017-08-23 | Five Years - Performances | Mungo Arney
2017-08-28 | 2017-09-08 | Evaluation - Five Years | Mungo Arney