## PID
Project name | New Music Biennial 2017
Last updated | 2016-03-10 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | Y
[8 empty] | national |  | Y
Dates | [7 empty] | international |  | Y
Project start date | 2016-03-04 |  | Project live date |  | 2017-07-01 |  |  | children (<16) |  | Y
End of Live date | 2017-07-03 |  | End of eval. date |  |  |  |  | young people (16-25) |  | Y
[8 empty] | families |  | Y
Categories | [7 empty] | older people (60+) |  | Y
Type | Funded (presenting) |  |  | Strand |  | PRS New Music Biennial |  | self-identify as disabled
Season | Freedom |  |  | Digital requirements |  | Medium |  | BME
NEET
Finance | [6 empty] | # temporary jobs created
Total project budget |  | 370300 |  |  |  |  | # freelance contracts created
Hull 2017 contribution |  | 0 |  |  |  |  | # participation opportunities
Analysis/project code(s) | [6 empty] | of which for school age
[7 empty] | # commissions |  | 10
[7 empty] | Objective |  | Met? | Notes
Build an audience in Hull for New Music
People | [6 empty] | Empower and enable local schools and individuals to deliver training and asessions on making new music.
Project Lead | Jenny Harris |  |  | Volunteering lead
Producer | Sam Hunt |  |  | Education lead |  |  | Let an audience discover more of the city's spaces through performances in multiple spaces,
Assistant Producer | Martin Atkinson |  |  | Marketing lead
Production Manager |  |  |  | Community Eng lead
Evaluation lead
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
Hull2017 will be working with numerous partners to deliver this project. Hull University, BBC, Communinty Groups, Schools, Freedom Choir, Hull Music Service. Main partner will be PRS. | [6 empty] | The event will take place in different locations around the Old Town and city centre. These will be identified as per the artist's requirements.
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
James Redwood will be working with communities to deliver workshops. Gogo Penguin, Eliza Carthy and Sam Lee will be working in the city with local partners to create their new compositions.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
PRS: Naomi Belshaw [Naomi@prsformusicfoundation.com] Grants and Programmes Manager. Jenny Harris: New Music Biennial Composer Residency Project Director. PRS not yet contracted. BBC Radio 3: Paul Frankl, Producer. Southbank: Gillian Moore – Director of Music. Many toher commissioning partners including: Brian Carson - Moving on Music; Tim Stevens – BFI; Andrew Burke – London Sinfonietta; Jo Ross – Oxford Contemporary Music; Emma Nicolson - Atlas Arts; Ally Rosser - Mahogany opera; David Porter – JNights; Mikey Martins – Freedom Festival; Errol Francis - Cultural Co-operation; Dominic Gray – Opera North; Ben Frith – Gould Piano Trio; Sian Roberts – BBC Philharmonic; Kevin Appleby – Turner Sims; Victoria Bosher – Oxford Contemporary Music. | [6 empty] | Building networks with composers/makes and music organisations and a programme of training with the University to ensure skills remain in the region. Workshops will be delivered throughout numerous point of the year around core skills of artisitc leadership within school and community settings.
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
30-50 Volunteers on 1 & 2 July to assist audience at venues and make sure people know where they are going and to possibly assist with some running. | [6 empty] | The New Music Biennial includes new music from across all genres: from classical and chamber opera to jazz, folk, electronic and music for brass band and organ. Many of the winning new commissions such as Errollyn Wallen’s Mighty River orchestral work that draws inspiration from the work of William Wilberforce in Hull and GoGo Penguin’s Abstractions of the Industrial North resonate with one of the themes of Hull UK City of Culture (Made in Hull, Roots and Routes, Freedom, Tell the World). Several of the commissioning partners including Freedom Festival, Jnight and Opera North are based in Hull or the surrounding region. Yorkshire born composers such as Daniel Elms, Gavin Bryars and Eliza Carthy, who has strong family links to the city, are working on new pieces which explore the identity of the city and surrounding landscape and Mercury Prize-nominated folk singer and song collector Sam Lee exploring vernacular folk song in Hull City. Other commissions featured in the New Music Biennial simply reflect the exceptional talent and breadth of composers in the UK. This includes composer Simon Holt’s new clarinet concerto for 2006’s BBC Young Musician of the Year Mark Simpson commissioned by BBC Philharmonic Orchestra, Emily Hall’s new Opera for children and Tom Jenkinson’s (Squarepusher) The Secret Life of Organs showcasing the potential for these incredible instruments beyond traditional organ music. The performances will take place in a number of venues across the city centre.
Version control
Date | Changes and/or approvals
1899-12-31
2016-04-08 | General updates
Note on Q17: Direct employee of Hull 2017 or partner organisation
Note on Q18: Including creative teams etc

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize