|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Time** | **Action** | **24/7 Security?** |
| Sunday 6th August |  |  |  |
| PM | Adam on site – mark out | N |
| Monday 7th August | AM | Trackway Delivered and layed  Barriers and fencing delivered | y |
| PM | Continue Trakway | y |
| Tuesday 8th August | AM | Continue trakway  Build compound  Generators delivered  Marquees delivered and erected | y |
| PM | Install power – production & show compound  Finish trakway  CirkVOST Arrive  Mark out | y |
| Wednesday 9th August | AM | Unload | y |
| PM | Begin build | y |
| Thursday 10th August | AM | Continue build  Crane on site | y |
| PM | Continue build  Begin lighting install  Focus and plot lighting – Could be late! | y |
| Friday 11th August | AM | Set-up deckchairs  Sound on site – set-up and soundchecks | y |
| PM | Light and Sound Rehearsal – lighting could go late | y |
| Saturday 12th August | AM | Work as required | y |
| PM | SHOW 21:30 | y |
| Sunday 13th August | AM | Work as required | y |
| PM | SHOW 21:30  22.30 – 0100 – get-out sound, deckchairs and some lighting | y |
| Monday 14th August | AM | 0800. Main get-out, crane on site | y |
| PM | Continue get-out. Cirk Vost off site by 1700  Continue production get-out | y |
| Tuesday 15th August | AM | Trakway out  Strike fencing/barriers  Marquee collected  Generators off site | y |
| PM | Finish trakway get-out  Barriers collected | n |