|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Time** | **Action** | **24/7 Security?** |
| Sunday 6th August  |  |  |  |
| PM  | Adam on site – mark out | N |
| Monday 7th August | AM | Trackway Delivered and layedBarriers and fencing delivered | y |
| PM | Continue Trakway  | y |
| Tuesday 8th August | AM | Continue trakway Build compoundGenerators deliveredMarquees delivered and erected  | y |
| PM | Install power – production & show compoundFinish trakwayCirkVOST ArriveMark out  | y |
| Wednesday 9th August | AM | Unload  | y |
| PM | Begin build  | y |
| Thursday 10th August | AM | Continue buildCrane on site | y |
| PM | Continue build Begin lighting installFocus and plot lighting – Could be late! | y |
| Friday 11th August | AM | Set-up deckchairsSound on site – set-up and soundchecks | y |
| PM | Light and Sound Rehearsal – lighting could go late | y |
| Saturday 12th August | AM | Work as required  | y |
| PM | SHOW 21:30 | y |
| Sunday 13th August | AM | Work as required  | y |
| PM | SHOW 21:3022.30 – 0100 – get-out sound, deckchairs and some lighting  | y |
| Monday 14th August | AM | 0800. Main get-out, crane on site  | y |
| PM | Continue get-out. Cirk Vost off site by 1700Continue production get-out | y |
| Tuesday 15th August | AM | Trakway outStrike fencing/barriersMarquee collected Generators off site  | y |
| PM | Finish trakway get-out Barriers collected  | n |