**V2.0-HULL CITY OF CULTURE – PRODUCTION SCHEDULE**

|  |  |  |  |
| --- | --- | --- | --- |
| **Weds 21st Dec** | 8am – 6pm | Whitefriar Gate | Production - Internal clean all shop interiors |
|  |  |  |  |
|  |  |  |  |
| **Thurs 22nd Dec** | Midday – 6pm | Whitefriar Gate | Production - Install Projection film to windows in shop units 9, 16 & 17 |
|  |  |  |  |
|  |  |  |  |
| **Fri 23rd Dec** | Midday – 10pm | Whitefriar Gate | Production/Creative & Video – Projection test to window cubes in unit 8 |
|  |  |  |  |
|  |  |  |  |
| **Sat 24th Dec** | **XMAS EVE** | **Holidays** |  |
|  |  |  |  |
|  |  |  |  |
| **Sun 25th Dec** | **XMAS DAY** | **Holidays** |  |
|  |  |  |  |
|  |  |  |  |
| **Mon 26th Dec** | **BOXING DAY** | **Holidays** |  |
|  |  |  |  |
|  |  |  |  |
| **Tues 27th Dec** | 8am – 11am | The Deep | Steelworkers build PA towers |
|  | 9am - Midday | The Deep | Lighting deliver and install |
|  | 10am – 2pm | Queen Victoria Square | Video install projectors and control |
|  | 10am – 2pm | The Deep | Video install projectors and control |
|  | 11am – 8pm | Queen Victoria Square | Graphics apply window vinyls to City Hall, Ferens & Maritime Museum |
|  | 11am – 8pm | Whitefriar Gate | Graphics apply window vinyls to shop units |
|  | Midday – 4pm | The Underpass | Video install projectors and control |
|  | Midday – 4pm | Scale Lane Staith | Video install projectors and control |
|  | Midday – 6pm | Queen Victoria Square | Lighting deliver and install rooftop fixtures and control |
|  | Midday – 7pm | The Underpass | Lighting deliver and install fixtures and control |
|  | Midday – 8pm | The Underpass | Production install screens |

|  |  |  |  |
| --- | --- | --- | --- |
| **Tues 27th Dec** | 1pm – 4pm | Queen Victoria Square | Audio install PA |
| **(continued)** | 2:30pm – 6pm | Whitefriar Gate | Video install projection into shop units |
|  | 4pm – 8pm | **ALL SITES** | Video carry out system checks and tests |
|  | 5pm – 7pm | Queen Victoria Square | Lighting deliver and install fixtures and control to Monument area |
|  |  |  |  |
| **Weds 28th Dec** | 8am – 1pm | Zebedees Yard | Lighting deliver and install fixtures and control |
|  | 8am – 3pm | Queen Victoria Square | Graphics complete window vinyls to City Hall, Ferens & Maritime Museum |
|  | 8am – 6pm | The Underpass | Audio install PA |
|  | 8am – 6pm | The Deep | Audio install PA |
|  | 8am – 6pm | Whitefriar Gate | Audio install PA |
|  | 8am – 6pm | Zebedees Yard | Audio install PA |
|  | 8am – 6pm | Scale Lane Staith | Audio install PA |
|  | Midday – 6pm | Whitefriar Gate | Audio install window speakers into shop units 16,17 & 20 |
|  | 2pm – 7pm | The Underpass | Lighting deliver and install fixtures and control |
|  | 4pm – 4am | **ALL SITES** | Video – initial line up all projectors |
|  | 4pm – 10pm | The Underpass | Lighting – programme intelligent fixtures |
|  | 5:30pm – 7pm | Whitefriar Gate | Lighting deliver and install fixtures and control in shop units |
|  |  |  |  |
| **Thurs 29th Dec** | **09:00** |  | **ALL ARTISTES ON SITE** |
|  | 10am – Midday | **ALL SITES** | All Departments - System checks and fine tuning |
|  | Midday – 4pm | Zebedees Yard | Audio – Sound check |
|  | 4pm – 7pm | Whitefriar Gate | Audio & Video – System checks |
|  | 4pm - Midnight | Queen Victoria Square | Lighting – programme intelligent fixtures |
|  | 4pm - Midnight | Queen Victoria Square | Audio & Video – System checks |
|  | 4pm - Midnight | Whitefriar Gate | Audio & Video – System checks |
|  | 4pm - Midnight | The Deep | Audio & Video – System checks |
|  | 4pm - Midnight | The Underpass | Audio & Video – System checks |
|  | 4pm - Midnight | Scale Lane Staith | Audio & Video – System checks |

**HULL CITY OF CULTURE – PRODUCTION SCHEDULE**

|  |  |  |  |
| --- | --- | --- | --- |
| **Fri 30th Dec** | Midday – 4pm | **ALL SITES** | Production & Event Management – Noise level checks for Hull CC approval |
|  | Midday – 9pm | Zebedees Yard | Lighting – programme intelligent fixtures |
|  | Midday – 10pm | Queen Victoria Square | Audio & Video – System checks |
|  | Midday – 10pm | The Underpass | Audio & Video – System checks |
|  | Midday – 10pm | Scale Lane Staith | Audio & Video – System checks |
|  | Midday – 10pm | The Deep | Audio & Video – System checks |
|  | 9pm – 10pm | Zebedees Yard | Audio – Sound check |
|  | 9pm – 11pm | The Deep | Lighting – programme intelligent fixtures |
|  | **11pm – Midnight** | **ALL SITES** | **DRESS REHEARSALS** |
|  |  |  |  |
| **Sat 31st Dec** | **CONTINGENCY** |  |  |
|  |  |  |  |
|  |  |  |  |
| **Sun 1st Jan** | 2pm | **ALL SITES** | Technical and Production crews – Show Standby |
|  |  |  |  |
|  |  |  |  |
| **Mon 2nd Jan** | 3pm | **ALL SITES** | Technical and Production crews – Show Standby |
|  |  |  |  |
|  |  |  |  |
| **Tues 3rd Jan** | 3pm | **ALL SITES** | Technical and Production crews – Show Standby |
|  |  |  |  |
|  |  |  |  |
| **Weds 4th Jan** | 3pm | **ALL SITES** | Technical and Production crews – Show Standby |
|  |  |  |  |
|  |  |  |  |
| **Thurs 5th Jan** | 3pm | **ALL SITES** | Technical and Production crews – Show Standby |
|  |  |  |  |
|  |  |  |  |

**HULL CITY OF CULTURE – PRODUCTION SCHEDULE**

|  |  |  |  |
| --- | --- | --- | --- |
| **Fri 6th Jan** | 3pm | **ALL SITES** | Technical and Production crews – Show Standby |
|  |  |  |  |
|  |  |  |  |
| **Sat 7th Jan** | 3pm | **ALL SITES** | Technical and Production crews – Show Standby |
|  |  |  |  |
|  |  |  |  |
| **Sun 8th Jan** | ALL DAY | **ALL SITES** | DISMANTLE |
|  |  |  |  |
|  |  |  |  |
| **Mon 9th Jan** | ALL DAY | **ALL SITES** | DISMANTLE |
|  |  |  |  |