## split list
LAND OF GREEN GINGER: OUTLINE TIMELINE |  |  |  | Creative
Structural
Community
Stage One: Oct 15 - Jan 16 | CREATIVE | STRUCTURAL | COMMUNITY
| Develop narrative | Draft budget | Begin to scope neighbourhood "sites" and networks/organisations
| Draw up artist brief | Confirm funding make up
| Research and draw up long-list of artists to approach | Agree Steering Group structure / meetings
| Draw up strategy for open call | Agree structure of Delivery Team
| Approach writer/s | Identify key team members
Stage Two: Feb 16 - March 16
| Approach artists / open call released - start of period | Producer and Project Assistant start | Develop community links - communities team roadshow
Commission 1 artist to create something - Visuals? Teaser? - for road show
Artists submit EOIs - end of period
Stage Three: Apr 16 - May 16
| Artists selected |  | Community sites and initial groups secured
Initial creative session for all artists (orientation - meeting each other)
Artists submit proposals for initial R&D "interventions"
Proposals developed with Producer / lead creative
Early R&D of citywide interventions
Scope options for "Culmination"
Stage Four: June 16 - Aug 16
| Artists deliver R&D interventions |  | Further community and audience development work
Second creative session for all artists together
Stage Five: Sept 16 - Dec 16
| Artists develop full project proposals for Neighbourhood Projects | Detailed budgets for all "sub-projects" | Specific community links strengthened
| Proposals developed with Producer / lead creative | Detailed production planning
Citywide projects further development
Stage Six: Throughout 17
Neighbourhood projects delivery
Further artist link ups - project review and reframe as necessary
Citywide projects delivery
Culmination project development
Stage Seven: March 18
| Culmination project unveiled | Evaluation