## Guidance
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays |  | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Timescale for show content development under pressure due to project demands on the writer-producers. | Show content fails to realise potential | RC & GB | 2 | 5 | 10 | Prioritise time for script development each week throughout May & June. Delegate further tasks where viable to Asst Producer | 2 | 3 | 6 | Open
2 | Ronson family input into audio reminiscence lacking to date. | Negative impact on authenticity & range of audio tesimony and knock on effect on show content | RC & GB & KJ | 1 | 5 | 5 | Recent meeting with Maggi Ronson (sister) has secured her support for the project and willingness to be recorded. Ensure recording takes place within May. Prioritise other family members for recordings within a realistic time scale | 3 | 5 | 15 | Open
3 | Higher than anticipated IP costs for film clips within show require rethink of film content element | this element of show content fails to realise potential | RC & GB | 2 | 4 | 8 | Revision film clip content with greater focus on stills. Commission film content maker to adapt stills and create more impactful clip sections. Pursue with BBC idea of obtaining permission for interview sections of their films thus avoiding multiple copyright holder issues for these sections | 2 | 4 | 8 | Open
4 | Some musicians still to be recruited | Music potential of live show not fully realised | RC & GB | 2 | 4 | 8 | Prioritise recruitment of remaining musicians within May & June |  |  | 0
5 | Higher than anticipated PRS costs | Music potential of live show not fully realised | KJ & Rc & GB | 2 | 4 | 8 | Prioritise submission of likely live tracks within show to PRS to secure precise costings |  |  | 0
6 | Film content maker fee not included in original budget. | Negative impact on quality of show | RC & GB | 2 | 4 | 8 | Ongoing project promotion to maintain current level of ticket sales over the next 2 months. This will result in higher than budgeted box-office income allowing funding of Film Content Maker |  |  | 0
7 | Project demands on core team expanding as project progresses | Project elements not adequately delivered | RC | 2 | 4 | 8 | Communicate monthly and weekly priorities to core team members. Explore additional voluntary support in project work areas e.g. show production period Dropbox shared folder system has been established to facilitate shared planning priorities and document sharing |  |  | 0
8 | Securing sponsorship for additional high cost items in exhibition is proving highly time-consuming | Project elements not adequately delivered | KJ | 2 | 4 | 8 | A risk assessment of the Exhibition venue will have to be carried out as part of obtaining an insurance quote for the Exhibition. A Condition Report and security details have been obtained from the venue and passed to potential insurance company. Measures to protect and secure iconic items loaned to TFS will have to be planned and executed prior to obtaining items offered for loan. Establish cut-off point for mid June to secure sponsorship. Exhibition without these high cost items is viable and in line with original artistic vision. |  |  | 0
9 | [5 empty] | 0 |  |  |  | 0
10 | [5 empty] | 0 |  |  |  | 0
11 | [5 empty] | 0 |  |  |  | 0
12 | [5 empty] | 0 |  |  |  | 0
13 | [5 empty] | 0 |  |  |  | 0
14 | [5 empty] | 0 |  |  |  | 0
15 | [5 empty] | 0 |  |  |  | 0
16 | [5 empty] | 0 |  |  |  | 0
17 | [5 empty] | 0 |  |  |  | 0
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...