NNT – 13/6/16

Henri, Lou, Ian, James M, Martin

|  |  |  |  |
| --- | --- | --- | --- |
| **Agenda** | **Action** | **who** | **Deadline** |
| **Admin** | Job description to be completed | Henri to send to Lou | Yes |
| **Partnership Agreements** | To include – free venue, local team requirements, use of hcoc logo – bespoke for schools & social venues | Henri | Henri meeting Will this week |
| **Contacts** | Venue contact spreadsheet to be lifted from ACE bid | Martin | June |
| **Branding** | To include – Brochure, Name, Description, partner venues, highlights | All | ASAP – 11th July content deadline |
| **Inform Venues & set up area meetings** | Try to sign up venues by 4th July so they can be named in brochure. Individual meetings rather than in clusters | Ian & Lou – schools  James & Lou community | 4th July |
| **Monthly partner meetings dates** | **Meeting 1** – Louise to book Rollitz meeting room, Wed 14th July 4-6pm | Lou | ASAP |
| **Consultant Brief** | To include meeting dates & day either side – 20 days available in budget | Lou | Yes |
| **Inflatable Screen** | Jane Earnshaw possibly has inflatable screen for YF project | Martin | June |
| **Circus** | Joint projects and programme from circus budget | Lou | Ongoing Lou to attend meetings |