turner prize, HULL 2017 – key deadlines

|  | Task Description | Deadline | Responsible |
| --- | --- | --- | --- |
| 1 | Title logo lock-up provided by Tate to Hull | June 2015 | Tate |
| 2 | Private Reception/Opening event for Glasgow Turner Prize 2015 to be attended by relevant Hull staff | 30 September 2015 | n/a |
| 3 | Turner Prize Hull 2017 project team meeting in Glasgow | 01 October 2015 | Tate |
| 4 | Turner Prize 2017 Jury selected | April/ May 2016 | Tate |
| 5 | Hull Turner Prize Marketing Plan submitted to Tate for review | June 2016 | Hull |
| 6 | Hull City of Culture 2017 programme announcement | September 2016 | Hull |
| 7 | Select/ agree top three awards ceremony presenters | January 2017 | Tate/ Hull |
| 8 | Write copy for nominations on Tate web page | March 2017 | Tate |
| 9 | Announce call for public nominations | March 2017 | Tate |
| 10 | Public nominations close, list sent to the jury | April 2017 | Tate |
| 11 | Jury submit long list (six artists) for discussion | April 2017 | Tate |
| 12 | Tate Curator research suggested artists and brings together information on all 6 artists for review by jury members | April 2017 | Tate |
| 13 | Jury meet to select/ nominate Turner Prize artists | April/ May 2017 | Tate |
| - 14 | - Artists participation agreed | May 2017 | Tate |
| - 15 | - Research artists, write and sign off press release and artist biographies. Tate and artists to sign off materials. | May 2017 | Hull |
| - 16 | - Lead press & marketing images selected and copyright cleared. Tate and artists to sign off materials. | May 2017 | Hull |
| - 17 | - Internal press briefing pack compiled and circulated | May 2017 | Hull/ Tate |
| - 18 | - Press conference to announce the four shortlisted artists | May 2017 | Tate |
| 19 | Artists briefing meeting including Ferens site visit | May 2017 | Hull/ Tate |
| 20 | Artist contracts signed | June 2017 | Hull |
| 21 | Marketing identity developed and signed off by Tate | June 2017 | Hull |
| 22 | Exhibition content discussed with artists and agreed | End June 2017 | Hull |
| 23 | Loan letters sent | End June 2017 | Hull |
| 24 | Awards ceremony presenter confirmed | End June 2017 | Tate |
| 25 | Exhibition design submitted to Tate for review | Mid July 2017 | Hull |
| 26 | Deadline for copy for the Tate Members Guide (September release) | Mid July 2017 | Hull |
| 27 | Artist films made | June/ August 2017 | Hull |
| 28 | Essays sent to artists for approval. Images for publication approved | Mid August 2017 | Hull |
| 29 | Publications layouts sent to Tate and artists for approval | Mid August 2017 | Hull |
| 30 | Deadline for copy for Tate Members E-Bullitin (September release) | Mid August 2017 | Hull |
| 31 | Publication sent to print | End August 2017 | Hull |
| 32 | Press event and opening night reception planned | August 2017 | Hull |
| 33 | Events guest lists compiled | Mid July 2017 | Hull/ Tate |
| 34 | Invitations to opening events designed and sent | 24 August 2017 | Hull |
| 35 | Curatorial media training (if required) | August 2017 | Hull |
| 36 | Exhibition build (3 weeks) | End August/ Early September 2017 | Hull |
| 37 | Exhibition installation (3 weeks) | Mid-end September 2017 | Hull |
| 38 | Exhibition installation photography to be shot (given to press as part of the press pack) | End September 2017 | Hull |
| 39 | Preview of exhibition for broadsheet weekend editorials | End September/ early Oct 2017 | Hull |
| 40 | Press Preview Event for the Exhibition (am) | End September/ early Oct 2017 | Hull |
| 41 | Tate Patrons Tour of exhibition with Hull curators (pm) | End September/ early Oct 2017 | Hull/ Tate |
| 42 | Private Reception/Opening event for the Exhibition (evening) | End September/ early Oct 2017 | Hull |
| 43 | Exhibition opens to the public | End September/ early Oct 2017 | Hull |
| 44 | Awards ceremony planned | 1 Oct – 1 Dec 2017 | Hull |
| 45 | Awards ceremony guest lists compiled | 02 October 2017 | Hull/ Tate |
| 46 | Invitations to opening events designed and sent | 19 October 2017 | Hull |
| 47 | Awards ceremony detailed event schedule and briefing pack signed off | 27 November 2017 | Hull/ Tate |
| 48 | Jury meet to decide Turner Prize winner (am) Awards Ceremony (pm) | Early December 2017 | Hull |
| 49 | Exhibition closes | Early January 2018 | Hull |