## Sheet1
What are the key lessons learnt from working on Made in Hull, which you'll take forward into your future work?
Respondents | Response Date | Response Text | Categories
1 | 2017-01-27 16:45 | Working at scale, with the public is very rewarding
2 | 2017-01-27 12:12 | Better time management and better communication.
3 | 2017-01-26 16:47 | To be in full control of my work. To question more. Not to be completely trusting of what I'm told will happen, and to make it happen myself. To remember others have their own agenda, and ultimately I am not their priority. It was a steep but good learning curve.
4 | 2017-01-26 14:53 | Holding our ground on budget, pushing harder to have commissioning team work with our process, have more input on tech setup even if it's not our responsibility.
5 | 2017-01-26 12:24 | Planning, planning, planning!
6 | 2017-01-25 19:10 | It's given me such a huge confidence boost, I now feel confident to voice my opinions and suggest big ideas and think on a grander scale. Very motivating experience.
7 | 2017-01-24 21:44 | expect the unexpected
8 | 2017-01-23 10:46 | Communicating with the logistics and operations team as early as possible, to discuss delivery requirements, is very important. If you haven't been asked it doesn't always mean it is not necessary and therefore you should have your own foresight. The team are dealing with many projects and things can be forgotten.
9 | 2017-01-20 18:58 | To be thorough throughout, and continually communicate with the people you're working with.